# OLDCASTLE FIRE STATION UPGRADE  (OLDFS - 22/01)

# Project Master Plan (PMP) / Project Execution Plan (PEP)

# September 2025

OLDFS-22_01-PMP-R0

Document Control:

Names removed

| Revision | Date | Project / Filename | OLDCASTLE FIRE STATION UPGRADE (OLDFS – 22/01) OLDFS-22_01-PMP-R0 |  |  |
| --- | --- | --- | --- | --- | --- |
| R0 | 18th September 2025 | Description | Initial DRAFT Rev. 0 |  |  |
|  |  |  | Prepared by | Checked by | Approved by |
|  |  | Name |  |  |  |
|  |  | Signature |  |  |  |
| Revision | Date |  |  |  |  |
|  |  |  | Prepared by | Checked by | Approved by |
|  |  | Signature |  |  |  |
| Revision | Date | Project / Filename |  |  |  |
|  |  | Description |  |  |  |
|  |  |  | Prepared by | Checked by | Approved by |
|  |  | Name |  |  |  |
|  |  | Signature |  |  |  |

- TABLE OF CONTENTS

1.	Project Lifecycle & Capital Works Management Framework (CWMF)	8

1.1.	Project Lifecycle	8

1.1.1.	Definition or preinvestment phase	8

1.1.2.	Execution or Implementation phase	8

1.1.3.	Commissioning phase	8

1.1.4.	Operational phase	8

1.1.5.	Disposal or abandonment phase	9

1.2.	The Capital Works Management Framework (CWMF)	9

2.	Project Master Plan	11

2.1.	Definition of the Project	11

2.1.1.	Scope of Work	11

2.1.1.1.	Project Identification	11

2.1.1.2.	Brief Project Description	11

2.1.1.3.	Contract Data	14

2.1.1.4.	Constraints and Conditions	14

2.1.1.5.	Stakeholder Responsibilities	15

2.1.1.6.	Definition of Work	15

2.1.1.7.	Decisions Already Made	15

2.1.2.	The Specifications	16

2.1.2.1.	Building Information Modelling (BIM)	17

2.2.	Conceptual Design & Project Brief Requirements	18

2.2.1.	Site Location & Layout	18

2.2.2.	Preliminary Building and Development Specification	19

2.2.2.1.	Building Layout	20

2.2.3.	Schedule of Accommodation –	24

2.2.3.1.	Car Parking Provision	24

2.2.4.	Climate Change and Energy Efficiency	24

2.2.4.1.	EU Legislation and Standards	25

2.3.	Project Time Schedule & Milestones	29

2.4.	Project Brief and Project Parameters	31

3.	Roles, Responsibilities and Authority	32

3.1.	Role & Responsibilities	32

3.1.1.	Building Control (Amendment) Regulations	34

3.2.	Project Contact List	34

4.	Finance & Project Budget	35

4.1.	Costs	35

4.1.1.	Cost Limits & Basic Building Costs (BBC)	35

4.1.2.	Site Costs	35

4.2.	Project Budget & Summary of Costs	35

4.2.1.	Project Budget	35

4.3.	Value Engineering (VE)	36

4.4.	Cost Management Procedures	36

5.	Contract Strategy	37

5.1.	Procurement of Consultants	37

5.1.1.	Framework for Multidisciplinary and Integrated Design Team Services	37

5.1.2.	Oldcastle Fire Station Upgrade - Design Team Services	38

5.1.3.	Suitability Assessment Questionnaire (SAQ)	42

5.1.4.	Professional Indemnity Insurance	42

5.1.5.	Contract Award Criteria	42

5.1.6.	Green Public Procurement	42

5.2.	Procurement of Works Contractor	43

5.3.	Procurement Schedule	43

6.	Project Control and Administration	44

6.1.	Overview	44

6.2.	Project Governance	44

6.3.	Handover & Commissioning	44

6.4.	Project Evaluation	44

6.4.1.	Project Status Reports	44

6.4.2.	Evaluation report	44

7.	Communication Plan	46

8.	Quality Plan	48

9.	Health & Safety, Environmental Management	49

9.1.	Health & Safety	49

9.1.1.	Particular Risks	49

9.1.2.	Asbestos Survey	49

9.1.3.	MCC Safety Management System	50

9.2.	Environmental Management	51

9.2.1.	Invasive Weeds	52

9.2.2.	Waste Management Plans	52

10.	Risk Management	53

10.1.	Risk Register	53

10.2.	Continuity of Operations	53

List of Figures

Figure 1 - Location of Meath County Council Fire and Rescue Service Fire Stations

Figure 2 – Oldcastle Fire Station Catchment Area

Figure 3 – Oldcastle Fire Station Front Elevation

Figure 4 – Oldcastle Fire Station Satellite Map View

Figure 5 – Oldcastle Fire Station Site Layout Map with additional land

Figure 6 – Project Organisation Chart

Figure 7 - Suitability assessment tasks for the open procedure

Figure 8 - Overview of Guidance Note 1.6 for Procurement of Consultants

List of Tables

Table 1 - Notes on Phasing and Stages for Preparation of the Project Master Plan (PMP)

Table 2 - Building Information Modelling (BIM) implementation adoption timeline.

Table 3 – Project Time Schedule Overview

Table 4 - Project Parameters in support of the Project Brief

Table 5 - Project Roles & Responsibilities

Table 6 - Project Contact List

Table 7 – Project Budget Overview

Table 8  – Capital Projects Summary Tracker Overview

Table 9  – Service Providers (Principal and Specialist)

Table 10 – Procurement Schedule

Table 11 – Reporting Requirements

Table 12 – Meeting Schedule

Table 13 – Quality Process Summary

List of Appendices

Appendix “A” - Extract from the CWMP detailing the Main Project Processes

Appendix “B1” – Site Layout Map with Additional Land

Appendix “B2” - Oldcastle Fire Station - Topo - 200 ITM15 - Rev2

Appendix “B3” - Oldcastle Fire Station - Topo Elevations

Appendix “C” - OLDFS_22-01_Schedule of Accommodation

Appendix “D” - OLDFS_22-01_Programme Activity Overview

Appendix “E1” - Planning  Design Guidelines and Financial Procedures for Fire Station Projects

Appendix “E2” - NIFRS Fire Station Design Principles - Draft V1

Appendix “E3” - Wold - Fire Station Design

Appendix "F” – Sample Photographs of Oldcastle Fire Station

Appendix “G” – Risk Register

EXECUTIVE SUMMARY

Meath County Council Fire and Rescue Service wish to oversee the upgrade of Oldcastle Fire Station.

This document is the Project Master Plan (PMP) / Project Execution Plan (PEP) and is presently structured in ten sections, with the main body of the plan contained in Section 2.

Capital Works Management Framework (CWMF) Guidance Note (GN) 1.2 is titled “Project Definition and Development of the Definitive Project Brief”.  GN 1.2 sets out how the Project Brief is developed from a Preliminary Output to a definitive Project Brief and Final Output Specification. The purpose of the Definitive Project Brief represents the detailed accumulated knowledge about a project in output terms and is categorised under sixteen project parameters. These 16 Project Parameters are included in this Plan. Specifically, Section 2.4 of this plan includes a summary of these 16 project parameters and references where the detail of these project parameters is contained within this PMP.

In drafting this plan, it is envisaged that the PMP is a “live” document and that any changes in assumptions that underpin the project and as the project progresses will prompt a revision or change to the PMP. Its purpose is to provide a Project Reference framework which can be used as a project management tool for the delivery of the project. This framework is for the use of all those directly engaged during the design, procurement, implementation and handover of the project, and who are tasked with delivering the project to the required specifications within the project capital budget and to a set timeframe.

Appropriate Appendices are contained at the rear of the plan and are referenced within the body of the plan.

Project Lifecycle & Capital Works Management Framework (CWMF)

Project Lifecycle

There are 5 phases in the lifecycle of a project namely:

- Definition or preinvestment phase

- Execution or implementation phase

- Commissioning phase

- Operational phase

- Disposal or abandonment phase

Definition or preinvestment phase

The project is conceived during this period. A need is identified, and a potential solution is developed. An opportunity or feasibility study may initially be carried out to determine whether the concept is feasible.

For this project, Meath County Council Fire and Rescue Service (MCCFRS) has carried out a feasibility assessment and has determined that there is a need and justification for the Oldcastle Fire Station Upgrade project to proceed.

MCCFRS have engaged with the Department of Housing, Local Government and Heritage (DoHLGH) and the particular Approval Section namely the National Directorate for Fire and Emergency Management (NDFEM). The NDFEM have confirmed that they are supportive of the Project and have advised “The Council is now approved to progress to Part VIII application”.

Execution or Implementation phase

The implementation phase starts where the preinvestment phase ends and includes:

- Conceptualisation

- Detailed Design

- Procurement

- Fabrication

Commissioning phase

The commissioning phase consists of:

- Inspection and Testing

- Product Handover

- Initial Operation

- Performance Test

Operational phase

Generally speaking it is no longer a project but an operation.

In the context of the Fire Station, Meath County Council Fire and Rescue Service through the support of the NDFEM are running the Fire Station as a day to day operation.

Disposal or abandonment phase

The project lifecycle is complete.

With respect to the Fire Station, the projected design life is expected to be a minimum of 50 years.

The Capital Works Management Framework (CWMF)

The Capital Works Management Framework (CWMF) is a structure that has been developed to deliver the Irish Government’s objectives in relation to public sector construction procurement reform. It consists of a suite of best practice guidance, standard contracts and generic template documents that form four pillars that support the Framework; the pillars are:

- A suite of standard forms of construction contracts and associated model forms, dispute resolution rules, model invitations to tender, forms of tender and schedules.

- The standard conditions of engagement for consultants, dispute resolution rules, model invitations to tender, forms of tender and schedules.

- Standard templates to record cost planning and control information; and for suitability assessment; and

- Extensive guidance notes covering the various activities in a project delivery process.

The aforementioned standard forms, templates and guidance notes are available at:

http://www.constructionprocurement.gov.ie/.

This project and the procurement of the consultants and contractor will be managed by utilising the templates, standard forms and guidance notes from this information source.

Meath County Council have a Procurement Section who will assist with the publication of the appropriate tender documents via etenders.

Refer to Appendix “A” for an extract from the CWMF detailing the Main Project Processes.

Table 1 overleaf details the inter-relationship between the 5 Phases of the Project Lifecycle and the 4 Project stages noted in the CWMF framework and the associated design services stages which are detailed in the Standard Conditions of Engagement. These Project Stages are the building blocks that underpin the Project Programme Activity Overview (Revision 0) which is contained in Appendix “D”.

Note:  Table 3 in Section 2.3 includes an Overview of the Project Time Schedule

| 5 Phases of the Project Lifecycle |  | Project Stages - (from CWMF1) |  | Design Services (from CWMF & Standard COE2) |
| --- | --- | --- | --- | --- |
| Phase 1- Definition or Preinvestment Phase |  | Stage 1 - Appraisal & Definition |  |  |
|  |  | Approval in Principle |  | Stage (i) Feasibility /Preliminary Report |
|  |  | and |  | Stage (i) Feasibility /Preliminary Design with output of Definitive Project Brief |
|  |  | Stage 1 - Planning Initial |  |  |
| Phase 2- Execution or Implementation Phase |  | Stage 2 - Planning Developed |  | Stage (ii) Design |
| Includes: |  |  |  | Stage (ii a) Developed Sketch Design / Outline Design |
| Conceptualisation (PMP is produced at end of this) |  |  |  | Stage (ii b) Statutory Process Design (Planning and FSC, DAC etc) |
| Detailed Design |  |  |  | Stage (ii c) Detailed Design and Preparation of Tender Documents |
| Procurement |  |  |  | Stage (iii) Tender Action, Evaluation, Award |
| Fabrication |  |  |  | Stage (iii) Tender Action, Evaluation, Award |
| Phase 3- Commissioning Phase |  | Stage 3 - Implementation |  | Stage (iv) Construction |
| Includes: |  |  |  | Stage (iv) Construction i.e. implementation |
| Inspection and Testing |  |  |  |  |
| Product Handover |  |  |  | Stage (v) Handover of Works |
| Initial Operation |  |  |  | Stage (v) Handover of Works & Final Account |
| Performance Test |  |  |  |  |
| Phase 4- Operational Phase |  | Stage 4 - Project Review |  | (a) This is the operational phase (i.e. the Fire Station is run and managed by the Meath County Council Fire and Rescue Service) |
| No longer a project but an operation. |  |  |  |  |
| Phase 5- Disposal or abandonment phase |  | CWMF denotes Capital Works Management Framework. COE Denotes Standard Conditions of Engagement |  |  |
| The Project lifecycle is complete |  |  |  |  |

Table 1 - Notes on Phasing and Stages for Preparation of the Project Master Plan (PMP)

Project Master Plan

During the conceptualisation period the project has been developed to a degree of detail that will permit the design of the project. At the end of conception, the Project Master Plan (PMP) is produced.

The Project Master Plan (PMP) consists of the following elements:

- Definition of the project

- Conceptual design

- Project time schedule

- Project estimated budget cost

- Contract strategy

Definition of the Project

The definition of the project consists of three elements:

- Scope of work (SOW)

- The Specifications

- Project Milestones

Scope of Work

The Statement of Work or Scope of work which sets out what needs to be done, underpins the Planning, Scheduling and Control of every project.

The Scope of Work normally contains:

- Project Identification

- Brief Project Description

- Contract Data

- Constraints and conditions

- Stakeholder responsibilities

- Definition of work

- Decisions already made

Project Identification

Oldcastle Fire Station Upgrade (OLDFS – 22/01).

Brief Project Description

Meath County Council Fire and Rescue Services (MCCFRS) with support of Appointed Design Team to project manage the delivery of the project namely Upgrade of Oldcastle Fire Station and handover the upgraded Fire Station to the Meath County Council Fire and Rescue Services Operations Team and Oldcastle Fire Station Service.

Profile

Meath County Council is the Fire Authority for the total county of Meath including the municipal districts of Ashbourne, Kells, Laytown- Bettystown, Navan, Ratoath, and Trim operating under the Fire Services Acts 1981.

One such service that Meath County Council delivers is the provision of an emergency response to incidents. Meath County Council Fire and Rescue Service delivers its services via (7no) seven brigades located in Navan, Trim, Kells, Dunshaughlin, Oldcastle, Nobber and Ashbourne and currently employs 88 firefighters throughout the county.

Figure 1 - Location of Meath County Council Fire and Rescue Service Fire Stations

Oldcastle Fire Brigade which was constructed in 1980 is currently located on the Millbrook Road, Oldcastle with an operational area of 192KM2  currently served by 12 firefighters. The design and construction of the station in 1980 was to cater for 9 firefighters only.

Figure 2 – Oldcastle Fire Station Catchment Area

Figure 3 – Oldcastle Fire Station Front Elevation

Note: Refer to Appendix "F” for sample Photographs of Oldcastle Fire Station

Works Description

One of the main limitations of the station is the size of the current footprint which does not cater for crewing levels of 12 personnel and the storing of fire resources required by the demands of the operational area. The parking facilities at the station do lend itself to quick turnout times.

The inadequacies with the existing fire station site are as follows: -

- The existing location is unsuitable to ensure a rapid response to incidents due to the lack of parking at the station.

- There is insufficient room for parking on site – there are now 12no staff based in Oldcastle Fire Station.

- The Muster Bay area for staff is not adequate, can only cater for 10.

- The accommodation for vehicles is not adequate to house the vehicles required for Oldcastle fire station.

- The existing male welfare facilities such as toilets and showering facilities are not adequate.

- There is an insufficient heating system that is leaking.

- There are no welfare facilities such as toilets and showering facilities for females.

- There are inadequate canteen facilities.

- The training room and resources within are not adequate.

The primary function of a fire station is to facilitate the speedy response of a fire brigade to incidents. Additional functional requirements of a fire station can be summarised as follows:

- To facilitate the emergency turn-out of the fire brigade.

- To accommodate fire brigade appliances and equipment, in a state of permanent readiness for use.

- To provide appropriate facilities for fire brigade personnel, commensurate with the level of fire brigade activity.

- To facilitate routine testing and maintenance of appliances and equipment.

- To facilitate ongoing training of fire brigade personnel.

- To provide a modern facility capable of meeting the current operational needs of its fire fighters.

- Maximise environmentally sustainable technologies to minimise building running costs in terms of heating, lighting, water usage and CO2 emissions.

- To increase the functional life of the station to serve the community into the future.

Additional land has been purchased at the rear of the fire station to accommodate future expansion and address the inadequacies as indicated above. Refer to Figure 4 below for Satellite photo showing extent of additional land and Figure 5 and Appendix “B1” for map.

Figure 4 – Oldcastle Fire Station Satellite Map View

Contract Data

In terms of future contracts, Meath County Council Fire & Rescue Service envisage that they will enter into 2 key contracts. These will be:

- 1 contract for Design Services (Multi-Disciplinary Design Team)

- 1 contract with a Main works contractor

Note: Localised Site Investigation works will be carried out as determined by the Design Team.

Note: With respect to Archaeology, no particular Archaeological impacts envisaged. Screening Report to be carried out by Design Team prior to planning application being submitted.

Note: Refer to Section 5 below on Contract Strategy

Constraints and Conditions

The principal constraint will be to ensure continuity of Fire Station during upgrade works. Design Team to consider if it is possible to continue Fire Service operations whilst upgrade works are being carried out (in some phased or managed way) or will it be necessary to decant and relocated either on another part of the site or at an alternative location.

The other principle constraint is the  requirement to provide 2 Number appliance bays. Ideally these should be placed side by side as distinct to a long bay with Appliance 1 located at the front and Appliance No.2 located behind Appliance No. 1. Access to the rear of the Fire Station will need to be provided which will impact on feasibility of locating 2 New appliances side by side. Perhaps the existing appliance bay can be modified to suit Appliance No.1 and a new dedicated second appliance bay is constructed at the side.

Additional land has been purchased by Meath County Council from the adjacent Credit Union to allow for upgrade and expansion works. The following included as a condition of sale to this purchase:

- “There is a surface water drainpipe underground, on the sold lands for the benefit of the retained lands in Folio MH9939F and the vendor (Oldcastle Credit Union)  will require an easement for the continued use, upkeep and repair of the said surface water pipe, but the purchaser (Meath County Council) shall be at liberty to alter the course of the surface water pipe in any future development of the sold land.”

The DoHLGH with support of the NDFEM have published “Planning & Design Guidelines and Financial Procedures for Fire Station Development Projects” . These guidelines are included as Appendix “E” of this PMP and provide details on functional requirements and recommended sizing for the various rooms. Appendix 2 of these guidelines provides a Schematic Layout for a Fire Station.

Compliance with these guidelines and procedures will be necessary

Stakeholder Responsibilities

Refer to Section 3 for Roles and Responsibilities.

Meath County Council Fire and Rescue Services (MCCFRS) with support of Appointed Design Team to project manage the delivery of the project namely Upgrade of Oldcastle Fire Station and handover the upgraded Fire Station to the Meath County Council Fire and Rescue Services Operations Team and Oldcastle Fire Station Service.

Once the design team has been appointed, the  (MCCFRS) will initiate and deliver presentation / briefing reviews of the Design at particular stages to representatives from Fire Service Operations and to representatives as necessary from the NDFEM.

MCCFRS will act reasonably and will consider proposals / questions that arise from or at said reviews.

The CMWF Main Project Processes contained in Appendix “A” detail the recommended Project Reviews which are to be carried out.

Definition of Work

- Meath County Council Fire and Rescue Services (MCCFRS) with support of Appointed Design Team to project manage the delivery of the project namely Upgrade of Oldcastle Fire Station and handover the upgraded Fire Station to the Meath County Council Fire and Rescue Services Operations Team and Oldcastle Fire Station Service.

- Project to be delivered in accordance with NDFEM published “Planning & Design Guidelines and Financial Procedures for Fire Station Development Projects”

- The Works Contractor will be procured and appointed in accordance with the CWMF using a 2 stage restricted process (See Contract Strategy -  Section 5 below)

Decisions Already Made

- Refer to Section 2.1.1.4 – Constraints and Conditions above.

- Meath County Council Fire and Rescue Services (MCCFRS) have engaged the services (in 2022) of an Architect to provide an outline Preliminary proposal. This proposal included an overview cost plan.

- On the basis of the aforementioned proposal, the Department of Housing, Local Government and Heritage (DoHLGH) represented by the National Directorate for Fire and Emergency Management (NDFEM) have provided approval to proceed with the engagement of Consultants for the Project.

- The appointed Consultants and Design Team are required to provide the full range of services through Stage 1 – Preliminary Design to Stage 5 – Handover.

- For the avoidance of doubt, the appointed consultants are required to provide their own Stage 1 Preliminary Design, in other words the previous Preliminary Design is not being progressed.

- Additional land behind the existing site has been purchased to allow for Upgrade Works.

  - Refer to Figure 5 for Map of Site which is also included as

  - Appendix “B1” – Site Layout Map with Additional Land

- A Topographical Survey has been carried out by Apex Surveys in 2021 for McGarry Ní Éanaigh Architects as part of the development and preparation of the previous Preliminary Design Proposal. The Contents of this Topographical Survey are included as:

  - Appendix “B2” - PMP Appendix B1_Oldcastle Fire Station - Topo - 200 ITM15 - Rev2

  - Appendix “B3” - PMP Appendix B2_Oldcastle Fire Station - Topo Elevations

- MCCFRS have prepared a Schedule of Accommodation Requirements. This schedule aligns with the NDFEM publication “Planning & Design Guidelines and Financial Procedures for Fire Station Development Projects”. Refer to Section  2.2 below and:

  - Appendix “C” - OLDFS_22-01_Schedule of Accommodation

- MCCFRS have prepared an Outline Programme which includes a Summary of the Principal Task Activities included for the Project. Refer to Section  2.3 for details:

  - Appendix “D” - OLDFS_22-01_Programme Activity Overview

The Specifications

All specifications and designs will comply with current Building Regulations and codes of practice.

Detailed specifications and drawings which will form part of the documents to be issued to prospective works contractors at tender stage will be aligned with the recommended standards and design guidelines published by the National Directorate for Fire and Emergency Management.

As noted above, the NDFEM have issued a publication titled “Planning & Design Guidelines and Financial Procedures for Fire Station Development Projects”.

The Current Draft Version of the aforementioned Guidelines (DRAFT 1.8 – 27 August 2025) is included as:

- Appendix “E1”_Planning  Design Guidelines and Financial Procedures for Fire Station Projects

Section 2.3 – Fire Station Layout and Zones of these Guidelines notes the following (in blue text in italics):

Fire station design and layout can assist with reducing exposure to lingering contaminants from the products of combustion following attendance at an incident involving carbonaceous burning. Designating different zones within fire stations is good practice, to help reduce exposure when working in fire stations. This is best achieved by moving personnel from zones of higher contamination to zones of low to no contamination.

Red zones, also called hot zones, have the highest level of contaminants. These are the areas firefighters first enter when they return to the station after an incident, and where dirty undergarments and equipment are washed and cleaned, and where contaminated PPE is stored. It is assumed that contaminated PPE will be appropriately bagged at the incident site in a manner that prevents exposure to contaminants upon return to the station. Appliance bays are considered a red zone. The layout of the fire station should be clearly delineated with appropriate signage, as much as practicable, for the areas where dirty or contaminated equipment or PPE is permitted.

Yellow zones are transition zones that firefighters enter after the red zone. They offer a buffer between red zones and green zones, and a second chance to ensure no contaminants enter a green zone. Yellow zones will include the muster bay and drying room.

Remaining areas within the station are considered green zones. They have the lowest level of contaminants and can be free of all contaminants and carcinogens when part of a zoned approach to the station’s design.

Design features help ensure that each zone remains isolated from the other.

The Northern Ireland Fire & Rescue Service have prepared a short paper which is included as:

- Appendix “E2” - NIFRS Fire Station Design Principles - Draft V1

These Design Principles are informed by research prepared by WOLD which is included as:

- Appendix “E3” - Wold - Fire Station Design

Building Information Modelling (BIM)

The Capital Works Management Framework (CWMF) have noted on the CWMF portal at the link below the following Building Information Modelling (BIM) implementation adoption timeline:

https://constructionprocurement.gov.ie/bim/public-sector-bim-adoption-timeline/#

| Extract from CWMF | Correlation with Month Schedule |
| --- | --- |
|  | Month 0 – 1st January 2024 Month 12 - 1st January 2025 Month 18 - 1st July 2025 Month 24 - 1st January 2026 Month 30 - 1st July 2026 Month 36 - 1st January 2027 Month 42 - 1st July 2027 |

Table 2 - Building Information Modelling (BIM) implementation adoption timeline.

The Department of Public Expenditure Infrastructure Public Service Reform and Digitalisation have confirmed that the aforementioned  “Timeline for BIM implementation is current and is on schedule for BIM Adoption”. They have also commented as follows (in italics):

For your information we are currently at this Implementation stage.

- As of the 1st of July 2025 all projects in that have entered stage 1 appraisal of the CWMF and have a value in excess of €10m are required to have implemented the BIM Mandate for the Design Process.

- As of the 1st of July 2025 all projects in that have entered stage 1 appraisal of the CWMF and have a value in excess of €20m are required to have implemented the BIM Mandate for the Contractor (Provided the Design team have implemented BIM in the Design Stage in accordance with the BIM Mandate).

Given the timeframe and project values noted above, there is no requirement for Design Team to utilise BIM on the Oldcastle Project.

Design Team should note that Works Construction Contract Appointment envisaged by 31st July 2027.

Given same, appointed Works Contractor will be required to utilise BIM and Design Team will need to ensure compliance with this requirement.

Conceptual Design & Project Brief Requirements

Site Location & Layout

The upgraded station is to be built at the existing site location and as noted above, additional land has been purchased to allow for the upgrade of Oldcastle Station.

Figure 5 – Oldcastle Fire Station Site Layout Map (with additional land)

Preliminary Building and Development Specification

- The existing site is of adequate area to accommodate all the functional requirements of upgrading Oldcastle fire station comprising of an extension, car parking to the rear and the internal modernisation to address the issues identified in Section 2.2.  The nature of the site is such that no design or construction problems would be anticipated, and this will be subject to further site investigation.

- The building will be designed to satisfy the functional requirements of the Oldcastle Fire Brigade.

- The Fire Station will be a 2 No. bay design meaning that it will be designed capable of housing 2no fire service vehicles, both of which will be based on a 10 tonnes per axle.

- The size and scope of the building design will be determined by the estimated costs of the project.  However, there will be minimum requirements that must be met to meet the needs of Meath County Council Fire and Rescue Service.  The design team will base preliminary designs based on the following requirements.

Note: Specific requirements may be subject to change.

- This project shall include within the design the In-Building Physical Infrastructure for High-Speed Electronic Communications to ensure that new buildings as defined by Directive 2014/61/EU) are equipped with a high-speed-ready in-building physical infrastructure to facilitate the future installation of cables or wireless devices capable of delivering broadband speeds greater than 30 Mbps.

  - Reference is made to both –

    - European Union (In-Building Physical Infrastructure for High-Speed Electronic Communications) Regulations 2023.

    - European Union Directive 2014/61/EU - Articles 8(1) and 8(2)

  - The client is aware of Client Action Plan 2023 (CAP23) – “Zero Energy Buildings” It is the preference of the client that this design will aspire towards ZEB.  The building(s) shall be designed to achieve a minimum “Nearly Zero Energy Building (NZEB)” Specification. The definition of Nearly Zero Energy Building (NZEB) as defined in directive 2010/31/EU on the energy performance of buildings as: “Nearly Zero Energy Building” means a building that has a very high energy performance, as determined in accordance with Annex 1.  The nearly zero or very low amount of energy required should be covered to a very significant extent by energy for renewable sources, including energy for renewable sources on-site or nearby.”  Guidance on this is available from the Sustainable Energy Authority of Ireland (SEAI), www.seai.ie.  The design shall reference and include an application for STAGE 1 (design) under the ‘Excellence in Energy Efficiency Design (EXEED)’ grant scheme.

  - Reference is made to both –

    - S.I. No. 538 of 2017 - Building Regulations (Part L Amendment) Regulations 2017 and

    - S.I. No. 393 of 2021 - European Union (Energy Performance of Buildings) Regulations 2021 (S.I. No. 393 of 2021).

      - Article 8(1) requires a new building, where technically and economically feasible, to be equipped with self-regulating devices for the separate regulation of the temperature in each room or, where justified, in a designated heated zone of the building unit. Where a heat generator is being replaced in an existing building, where technically and economically feasible, self-regulating devices shall also be installed.

      - Article 8(2) requires a building which has more than 10 car parking spaces, that is new, or undergoing major renovation, to have installed at least one recharging point and ducting infrastructure (consisting of conduits for electric cables) for at least one in every 5 car parking spaces to enable the subsequent installation of recharging points for electric vehicles.

  - The client is aware of PAS 6463: 2022 - Design for the mind – Neurodiversity and the built environment – Guide.  A standard that provides built environment guidance for multiple sensory processing differences and conditions. It aims to help with the design, creation or management of intuitive environments which readily accommodates the neurological variations in the way people perceive, process and organize sensory information received through hearing, sight, touch, smell, taste or movement.  The content of this PAS is aimed at buildings, external spaces and environments for public and commercial use, as well as residential accommodation for independent or supported living.  The content of this PAS is equally applicable to any organization anywhere in the world, irrespective of location, size, type, or sector.  Thoughtful design and management can create places where everyone can flourish equally, and people are provided with an equal opportunity to work, live, and socialize comfortably

Building Layout

New Appliance Bay

- A new additional appliance bay should be of minimum dimensions to house two class B Fire Appliances front to back.

- The appliance bay exit doors will be electrically operated with automatic safety systems.  Most appliance bays will have exits at the front and rear of the building.  Floors will be capable of carrying a loading of not less than 10 tonne per axel. Floors should be slip resistant and falls in floor level and drainage facilities should be provided for any water spillage.

- A vehicle specific exhaust extraction system will be fitted to ensure the welfare of personnel in the new appliance bay.

- EV charging points for vehicles. Electrical facilities are required to ensure continuous charging of batteries, engine heating units and air brakes on appliances.

- The additional appliance bay should be sited to enable the appliance to be moved straight out from the station until it is clear of the building.  The driver(s) should be afforded maximum visibility of the road / footpath onto which the vehicle(s) are emerging.

- The new appliance bay should be so sited to allow cars to drive into the rear of the station to park and to allow fire appliances to drive into the training yard for the purposes of drills and training.

- Exit doors from the new appliance should be capable of withstanding frequent usage under urgent circumstances without losing their smooth action and reliable operation.  The use of doors designed specifically for fire stations is recommended.   Doors may be electrically operated with manually operated fail safe overrides.  Appliance doors should be provided at the rear of the appliance accommodation to facilitate appliance movement.

- The floors of the existing appliance bay and new additional appliance bay shall be capable of carrying the imposed wheel loads of fully laden fire appliances, but not less than 10 tonnes per axle.  The type of floor finish should be consistent with the degree of usage of the fire station.  In most retained stations, a sealed concrete floor is generally adequate.  In exceptional circumstances a floor finish to a higher specification may be considered necessary.  Floors should be slip-resistant and falls in floor level and drainage facilities should be provided for any water spillage.

- The walls of the appliance bays should be finished to a standard consistent with the level of use of the station.  Painted masonry or smooth rendered finish is considered adequate for most fire stations.

- The appliance bays should be provided with an adequate level of artificial lighting for safe working and to illuminate the areas between appliances for access to equipment lockers. PIRs and Switches should be arranged so that relevant lighting can be operated immediately on entry to the station via the normal personnel entrance(s).

- A level of heating should be provided in the appliance bays to prevent freezing of water and damage to pumps and appliances and to reduce the risk of condensation on building surfaces.  For these purposes the appliance bays should be fitted with thermostatically controlled heating to ensure that the air temperature does not fall below 10°C.

- Electrical facilities are required to ensure continuous charging of batteries, EV charging, engine heating units and air brakes on appliances.

- Facilities should be provided to extract exhaust fumes from vehicles starting and idling.  The connections to the appliances for these services should disconnect automatically when the appliance is driven forward.

Muster Bay Upgrade

- The muster bay must be located close to the appliance bay for direct access. The room is required to be of a size to accommodate a crew of 14no firefighters with locker accommodation, etc.

- The muster bay should be adjacent to the appliance bay(s) and directly accessible to firefighters on entry to the station via the normal entrance(s) front and rear.  The muster bay should be large enough to accommodate the fire kits for the full complement on duty at the station, and to allow firefighters to don fire kit in a comfortable manner.  Each firefighter should ideally have individual combined seating space and suitably sized built-in locker accommodation to hold fire kit when not in use and for secure storage of personal effects.  Floor finishes in the muster area should be slip-resistant and easy to clean.

Sanitary Conveniences and washing facilities Upgrade.

- Separate male and female sanitary facilities are to be provided.  One WC / washbasin / shower per 5 no firefighters and UAWC - universal access WC

- Facilities should preferably be provided in non-gender specific individual units, rather than in communal units.

Refreshment Facilities Upgrade

- The existing canteen facilities need to be upgrade and improved to make light refreshments available to retained firefighters after protracted incidents and/or training periods.

- The canteen to include dishwasher, fridge, hob and sink in addition to kitchen units to accommodate storage.

Drying Room

- The drying room is to be preferably accessible from the appliance bay and/or muster bay.

- For the removal of PPE and should contain suitable dehumidifiers / moisture extraction systems to efficiently remove moisture from Fire Kits.  Suitable hanging racks for minimum 14no Fire Kits should be provided.

Lecture room Upgrade.

- The floor area of the lecture room should be approximately 2 square meters per staff and sized to cater for a minimum 25no occupants.  A wall mounted whiteboard board(s) and ceiling mounted overhead projector screen(s) complete with data IS /IT connections for HDMI should also be provided.

- The lecture room should also act as a community space that can be utilised by other members of the Oldcastle community. This will require a review of appropriate levels of security and access.

Storage Facilities – various (wet, dry and contaminated PPE)

- Storage facilities are required for consumable goods, PPE and general storage. Storage facilities should be provided with suitable shelving and storage presses.  There shall be separate stores – accessible from the appliance bay – ventilated and secure.

Electrical Services

- It is important that the requirements in relation to electrical services are taken into account at the design stage.  Adequate consideration should be given to energy efficiency, to the location of light switches, the number and types of lighting fittings (internally and externally), socket locations and communication and mobilisation equipment requirements. Secondary power supplies, UPS, back-up generators to ensure continued serviceability is also required.  Due consideration shall be given to Solar-PV systems and battery storage, where necessary.

Heating system upgrade

- A low-level of heating is required in the appliance bays.  Conditions should be sufficient to maintain equipment and appliances without excessive humidity and at a temperature generally not less than 10°C.  This general requirement extends to other areas of the fire station also.  However specific areas such as the administrative areas need to be capable of being raised to appropriate higher temperatures.  The choice of system used to achieve this will depend on the level of usage.

- Muster bays, washing and toilet areas and training rooms need to be capable of being raised to a temperature of 18-20°C.  The heating system and ventilation for the drying facilities also requires consideration.  To achieve maximum economy, it is important that the heating system operates only when required and controls / switches are located in the correct location for ease of use.  The use of timer-controlled switches and thermostats is recommended.

Ancillary Facilities

- In addition to the building construction, ancillary works are to be carried out to aid the delivery of training to personnel in a safe and secure environment. For this reason, it is appropriate that this project incorporate the upgrade of the existing drill tower, to assist in the management and training of the brigade.

Forecourt Upgrade

- The forecourt will be defined by both kerbing and landscaping if accommodated.

- Provision of three demountable/hinged storm flag poles with internal anti-ligature mechanism for hoisting flags with appropriate lighting.

Car Parking

- A minimum of 14no car parking spaces to the rear of the station with several EV charging points and disabled car parking spaces to be provided to allow for all staff vehicles to be accommodated and thereby ensuring a responding appliance has uninterrupted exit from the fire station.

Station Signage

- Fire stations are important civic buildings.  The station to be marked with a suitable sign to the front and side of the fire station and include the authority’s crest – illuminated and in colour.

- The station shall be provided with exterior LED lighting design - to be multi-coloured for different themed events.

- Station Signage must comply with the Official Languages Act 2003

Artistic Feature

- The provision of an artistic feature can enhance the visual impact of the building in the built environment.  It is important that the artistic feature is planned as an integral part of the design and landscaping of the scheme.  Further details on the scheme for grant-aiding of artistic features are available in Circular Letter No. LS 1/97 (ensure compliance with applicable scheme).

Operational Flow Path

- The range of ancillary accommodation is required to be designed to ensure a smooth operational flow in the firefighter turnout process as detailed below: -

- On Alert to incident

    - Parking for 14no vehicles

    - Access station through designated access point

    - Collect incident details from comms unit in Watch Room

    - Change into PPE in the muster bay.

    - Access appliance bay for vehicles

    - Open appliance bay doors

    - Access vehicle/s

    - Travel to incident.

    - Appliance bays doors automatically close

On Return from Incident

    - Appliance access to drill yard for cleaning

    - Appliance returned to bay via rear access

    - Appliance closedown and connection to vehicle exhaust extraction

    - Access BA Room to clean BA Sets / Refill Cylinders

    - Return to operational readiness all equipment

    - Access drying room to remove wet PPE

    - Access sanitary facilities

    - Access muster bay to change

    - Signed attendance log in Watch Room

    - Incident Debrief in debriefing room if so required

    - Lockup station

Schedule of Accommodation –

Section 2.2.2 above sets out particular requirements with respect to Accommodation Schedule.

As noted above, the DoHLGH with support of the NDFEM have published “Planning & Design Guidelines and Financial Procedures for Fire Station Development Projects” . These guidelines provide details on functional requirements and recommended sizing for the various rooms. Appendix 2 of these guidelines provides a Schematic Layout for a Fire Station.

Broadly speaking these guidelines based on accommodation for 12 personnel. This could be a crew of 10 males and 2 females. In any case, 12 people envisaged. Meath County Council Fire and Rescue service recommend that provision is made for sizing and provision for 14 personnel, i.e. an element of future proofing. Pro-Rata and review of sizing to be done as necessary.

Design Team to comply with these guidelines with respect to Schedule of Accommodation.

- Refer to Appendix “C” - OLDFS_22-01_Schedule of Accommodation

  - Table 1 in Appendix “C” includes details of Existing Accommodation Schedule with current area (measured internally) equating to 187m2.

  - Table 2 in Appendix “C” includes details of Proposed / Required Accommodation Schedule with proposed minimum area (measured internally) equating to 278.8m2.

Notwithstanding existing external space at side and adjacent existing Drill Tower, circa 1,681m2 additional land space at rear has been purchased from the Credit Union and is available. Refer to Site Location Map for details.

A metal shed is located at the rear of the Fire Station to house second fire appliance. This metal shed was utilised by Nobber Fire Station during the upgrade of Nobber Fire Station. Potentially this shed could be moved/utilised for storage of fire appliance during construction upgrade works at Oldcastle.

As noted above, The lecture room should also act as a community space that can be utilised by other members of the Oldcastle community.

Car Parking Provision

As noted above, a minimum of 14 no car parking spaces to the rear of the station with several EV charging points and disabled car parking spaces to be provided to allow for all staff vehicles to be accommodated and thereby ensuring a responding appliance has uninterrupted exit from the fire station.

Climate Change and Energy Efficiency

The Republic of Ireland's climate policy is guided by the Climate Action and Low Carbon Development Act and the Climate Action Plans (published annually), which outline the roadmap to achieving legally binding climate neutrality by 2050 and reducing greenhouse gas (GHG) emissions by 51% by 2030.

Section 2.2.2 above has noted the requirement to comply with current Building regulations, current government Climate Action Plan (CAP) and EXEED.

As noted overleaf in Section 3 – Roles and Responsibilities, the  Mechanical & Electrical Engineer is to include for an Environmental Sustainability and BREEAM Analysis Specialist if expertise & experience is not available in house.

Building Research Establishment Environmental Assessment Method (BREEAM) is a globally recognised sustainability assessment method for buildings and infrastructure, providing a framework and certification for environmental performance. Developed in 1990 by the UK's Building Research Establishment (BRE), it assesses projects in categories like energy, water, materials, and health and wellbeing to reduce environmental impacts and promote responsible design, construction, and operation.  https://breeam.com/about

The Tendering Consultant will be required to develop a  BREEAM rating for the Project. A minimum of “very good rating ≥55” is required. Every effort should be made to achieve a higher rating with “Excellent ≥70” or “Outstanding at ≥85” target ratings.

EU Legislation and Standards

The transposition and implementation of the revised Energy Performance of Buildings Directive (EPBD)  (EU/2024/1275), which was adopted on 24 April 2024, is now under way. This Directive will have wide ranging impacts across the non-residential sector.

The EPBD is a cornerstone of the EU’s European Green Deal and “Fit for 55” targets, and aims to decarbonise the building sector, which accounts for around 40% of energy consumption and emissions in the EU, by 2050. To comply, Ireland will need to enact legislation addressing a wide range of measures, including:

- Requiring public buildings must meet Zero Emission Building (ZEB) standards from 1 January 2028, with the requirement extended to all new buildings by 1 January 2030.

- Adopting of a harmonised EU-wide Energy Performance Certificate (EPC) scale ranging from A (best) to G (worst).

- Phased renovations through Minimum Energy Performance Standards (MEPS) targeting the worst-performing non-residential buildings (16% by 2030 and 26% by 2033).

- Mandatory solar readiness and electric vehicle (EV) charging infrastructure for most new constructions.

The transposition of this Directive will impact the Built environment, including the requirement to have Minimum Energy Performance Standards for commercial buildings. Article 17(15) of the EPBD, which aims to cease public funding for the installation of new fossil fuel boilers, is to be implemented by 1 January 2025. The 2023 Recast Energy Efficiency Directive 86 (EU/2023/1791) requires each Member State to achieve significant additional energy savings by 2030. Ireland is required to transpose this Directive by October 2025.

The revised Renewable Energy Directive (RED) (EU/2023/2413), requires a significant increase in renewable energy by 2030. The Directive establishes a binding target for the share of renewable energy in heating and cooling, as well as indicative targets for district heating, buildings and industry.

Some snippets from the EPBD are included overleaf. Project Team will be required to ensure compliance with the requirements of the EPBD:

Solar Energy:

Optimise the design for Solar Photovoltaic (PV) to be incorporated into the design from the outset. Full utilisation of the south facing roof spaces should be incorporated into the design.

Global Warming Potential:

Requirements for Zero Emissions Buildings (ZEB):

Requirements for Building Management Systems (BMS) and lighting controls

If the heat pumps, ventilation, A/C. total more than 70kW then there will be a need for a BMS to be included.

Sustainable  transport:
Allow for same and install appropriate ducting.

Project Time Schedule & Milestones

An Outline Programme which includes a Summary of the Principal Task Activities is contained in:

  - Appendix “D” - OLDFS_22-01_Programme Activity Overview

A summary of the Principal Task Activities is contained in Table 3 below which provides for circa 37 months duration from Tender Document Issue for Consultant to Completion and Handover to Meath County Council Fire & Rescue Service.

Given that it will take circa 3 months for procurement of Consultants and circa 3 months of service required in Stage 5, then anticipated overall duration for Consultant service delivery is 37 months.

| Ref. | Description | Duration (Working days) | Duration (weeks) | Duration (months) | % Fee based on Duration |
| --- | --- | --- | --- | --- | --- |
| 0.0 | Consultant /Design Team Procurement | 60 | 12 | ~3 |  |
| 1.0 | Stage 1 - Preliminary Design | 87 | 17 | 4 | 11% |
| 2.0 | Stage 2 Detailed Design |  |  |  |  |
| 2.1 | Stage 2(a) - Developed Sketch Design & Planning Application. - Milestone will be to lodge Planning application and Fire Safety Certificate (FSC) and Disability Access Certificate (DAC) | 87 | 17 | 4 | 11% |
| 2.2 | Stage 2(b) - Detailed Design (planning and other statutory permissions and preparation of tender documentation) - Milestone will be successful Notification of Grant of Planning and other statutory permissions. - Milestone will be approval to go to Tender for Works Contractor | 130 | 26 | 6 | 16% |
| 3.0 | Stage 3 - Works Tender (appointment of Contractor) - Milestone will be Appointment of Works Contractor. | 108 | 22 | 5 | 14% |
| 4.0 | Stage 4 - Works Construction (including Contract Administration). - Allowance for 15 months duration - Milestone will be Issue of Certificate of Completion and Handover to MCCFRS | 325 | 65 | 15 | 14% |
|  | OVERALL FROM TENDER DOCUMENT ISSUE TO MCCFRS HANDOVER | 800 | 160 | 37 | 92% |
| 5.0 | Stage 5 - Handover and Final Account - Provide for Final Account 3 months after Completion Cert. - 12 months Defects Liability Period. Design Team will need to provide appropriate level of service to close out on Final Account and Issue of Certificate at end of Defects Liability Period |  |  |  | 8% |
|  | ANTICIPATED OVERALL SERVICE DURATION BY APPOINTED CONSULTANT | 800 | 160 | 37 | 100% |

Table 3 – Project Time Schedule Overview

As noted above, appointed Design Team will need to provide appropriate level of service during the 12 months defect liability period to ensure close out on Final Account and issue of certificate at end of defects liability period.

The Project Team should look to improve on the delivery of the project in this timeframe. Any project delay attributable to poor performance in delivery by the Design Team may lead to a fee adjustment using measures provided for in the Conditions of Engagement (COE 1).

Project Brief and Project Parameters

As noted in the executive summary, the Capital Works Management Framework (CWMF) Guidance Note (GN) 1.2 is titled “Project Definition and Development of the Definitive Project Brief”.  GN 1.2 sets out how the Project Brief is developed from a Preliminary Output to a definitive Project Brief and Final Output Specification. The purpose of the Definitive Project Brief represents the detailed accumulated knowledge about a project in output terms and is categorised under sixteen project parameters. These 16 Project Parameters are included in this Plan. Table 4 below includes a summary of these 16 project parameters and references where the detail of these project parameters is contained in this Project Master Plan.

| Ref: | Project Parameter | Reference in PMP |
| --- | --- | --- |
| 1 | Objectives that the Project should meet | Provide Fire & Rescue Service Delivery for Oldcastle and environs |
| 2 | Purpose | Desired outcome is to improve service delivery and specifically to upgrade the Fire Station to allow for a Crew of 14 people. The lecture room should also act as a community space that can be utilised by other members of the Oldcastle community. |
| 3 | Scope | As outlined above in Section 2.1.1. |
| 4 | Project Deliverables and /or desired outcomes | As outlined above in Section 2.1 and 2.2. Upgrade to provide an Operational Crew of 14 persons. |
| 5 | Performance | Section 1.1.5 notes a 60-year Performance Period for the Building. |
| 6 | Realistic Assumptions | Refer to Section 2.1.1.7 for Decisions already made. |
| 7 | Governance and Reporting Requirements | Refer to Section 3 for Roles and Responsibilities and Section 6 for Project Control and Administration and Section 7 for Communication Plan |
| 8 | Preferred Option | TO BE DEVELOPED AS PART OF INITIAL PRELIMINARY DESIGN THROUGH TO DETAILED DESIGN |
| 9 | Risks | Refer to Section 10 and Appendix “G” Risk Register. Register to be updated as project progresses. |
| 10 | Value Management Strategies | Refer to Section 4.3 |
| 11 | Project Execution Plan | Refer to Section 2.3 for Project Time Schedule & Milestones and Appendix “D” for Activity Overview Schedule |
| 12 | Functional Life of Facility | Minimum of 60 years |
| 13 | Design Restrictions / Requirements | Refer to Section 2.1, 2.2 above |
| 14 | Location | Refer to Section 2.2.1 |
| 15 | Budget | Refer to Section 4 and Table 5. |
| 16 | Constraints | Refer to Section 2.1.1.4 |

Table 4 - Project Parameters in support of the Project Brief

Roles, Responsibilities and Authority

Role & Responsibilities

A description of the responsibilities of each organisation / role is tabled below:

For this project, Meath County Council Fire and Rescue Service (MCCFRS) has carried out a feasibility assessment and has determined that there is a need and justification for the Oldcastle Fire Station Upgrade project to proceed.

MCCFRS have engaged with the Department of Housing, Local Government and Heritage (DoHLGH) and the particular Approval Section namely the National Directorate for Fire and Emergency Management (NDFEM) who have provided approval to procure a Design Team for the project.

| Role | Responsibilities |
| --- | --- |
| Sponsoring Agency | Meath County Council as Local Authority (LA) represented by the Fire and Rescue Service as Delivery Agent, Client, Employer for Consultants and the Works Contractors |
| Sanctioning Authority | Department of Housing, Local Government and Heritage (DoHLGH) represented by the National Directorate for Fire and Emergency Management (NDFEM) |
| Project Coordinator | For MCC Fire and Rescue Service – Barry Quinn in the first instance supported by Paul Kelly |
| Project Manager | To be procured. Envisaged to be Architect as Lead Designer and lead of Design Team. Said Project Manager will act as Employer Representative |
| Project Supervisor Design Process (PSDP) | To be procured. Envisaged to be Architect as lead designer and lead of design team or a Specialist to be appointed by Architect as lead designer and lead of design Team |
| Project Supervisor Construction Stage (PSCS) | To be procured. Envisaged to be Main Works Contractor |
| Design Team – 4 Principal Services (to be Procured) |  |
| 1.A | Architect (including Design Team Lead), Project Manager, PSDP, Assigned Certifier, Employers Representative (ER) Note: Project Management (PM) Services are to be provided by the Architect as Lead Designer (i.e. Project Management is not a separate discipline). Note: Architect to act as Assigned Certifier under the Building Control (Amendment) Regulations 2014. |
| 2.CS | Civil / Structural Engineer |
| 3.ME | Mechanical & Electrical Engineer Note: Environmental Sustainability and BREEAM Analysis services to be provided by either the Mechanical & Electrical Engineer or by “A N Other” as a specialist |
| 4.QS | Quantity Surveyor and Whole Lifecycle Costs Manager |
| Specialist Consultants include (non-exhaustive list): |  |
| 1.A.1 | PSDP envisaged to be Architect as lead designer. Architect to include for a Specialist PSDP if expertise & experience is not available in house. |
| 1.A.2 | Architect to include for a Fire Safety Consultant Services if expertise & experience is not available in house. These services to be provided to the design team as a whole but as a specialist to the Architect as Lead. |
| 1.A.3 | Design Team to ensure Design and Construction comply with Best Practice and Applicable standard with respect to Universal Access and Design for Disabled Access (DAC). Architect to include for a Specialist Access Consultant if expertise & experience is not available in house. |
| 1.A.4 | All other related architectural services including Energy Efficiency, Acoustic design, Interior Design, Landscape design, Façade Design, 3D modelling / Presentation models, etc. if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
|  | Noted in Section 2.1.2.1 above that there is no particular requirement for Building Information Modelling (BIM) on this project and so there is no requirement for a BIM specialist if expertise & experience is not available in house |
| 2.CS.1 | All other related Civil / Structural engineering services appropriate for the project, including geotechnical and specialist structural design; temporary works design; etc if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the Civil & Structural Engineering Consultant and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| 3.ME.1 | As above, Mechanical & Electrical Engineer to include for an Environmental Sustainability and BREEAM Analysis Specialist if expertise & experience is not available in house. |
| 3.ME.2 | ICT related services: including Audio / Visual / Data / Security / BMS / etc. design if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the M&E Consultant and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| 3.ME.3 | All other related M&E services appropriate for the project, such as Vehicle exhaust design, Waste, HVAC, Acoustic engineering, lighting, wind / solar design etc. if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the M&E Consultant and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| 4.QS.1 | Including all such related services such as Whole Life / Life cycle costing; M & E Cost Surveying; specification advice / control / management; cost benchmarking etc. if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the Quantity Surveyor and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| Works Contractor | To be procured. |

Table 5 - Project Roles & Responsibilities

Building Control (Amendment) Regulations

The Architect (as Lead Designer) is to act as Assigned Certifier under the Building Control (Amendment) Regulations (BCAR 2014.

Project Contact List

The Project Contact List is tabled below and will be updated as Design Team as the Project progresses

| Organisation / Role | Name | Telephone & Mobile | email |
| --- | --- | --- | --- |
| Sponsoring Agency Chief Fire Officer | Meath County Council Sheila Broderick | TBC | SBroderick@meathcoco.ie |
| Sponsoring Agency Senior Assistant Chief Fire Officer | Meath County Council Barry Quinn | TBC | barry.quinn@meathcoco.ie |
| Sponsoring Agency Senior Executive Engineer | Meath County Council Paul Kelly | TBC | pkelly@meathcoco.ie |
| Sanctioning Authority | NDFEM at DoHLGH Karl Lawlor | TBC | Karl.Lawlor@housing.gov.ie |
| Sanctioning Authority Senior Assistant Chief Fire Officer - Advisor on secondment | NDFEM at DoHLGH Tom Burke | TBC | tburke@clarecoco.ie |

Table 6 - Project Contact List

Finance & Project Budget

Costs

Cost Limits & Basic Building Costs (BBC)

The NDFEM do not presently have specific guidance or requirements with respect to Basic Building Costs (BBC).

By way of reference, the Department of Education (DoES) current (as of 14th April 2025)  “Basic Building Cost Limit”  (BBC) is to a maximum of €2,420 per m2 of Floor Area.

For reference, Circular 0030/2025 is available at:

https://www.gov.ie/en/department-of-education/circulars/teorainneacha-costais-dfhoirgnimh-bhunscoile-agus-iar-bhunscoile/

This cost is intended to include:

- The building and substructures.

- The proportion of Preliminaries and Insurances allocated to the above.

- Value Added Tax.

There is an “External Works Allowance” (EWA) to a maximum of 12.5% of the BBC.

Abnormal costs deemed to be included unless otherwise agreed.

Project team understand that anecdotally, abnormal Costs in the amount of 25% + of the BBC, which covers the like of MVHR, Higher spec finish to façade, etc... so the cost of the building ends up being closer to €3,500/m2

Project team gave consideration to utilising a budget figure of €3,500 per m2. However sense is that a budget figure of €4,000 per m2 ex VAT and Prelims and Professional Fee’s is more appropriate for  utilisation on this project.

Dialogue to be held with NDFEM and appointed Quantity Surveyor to review same.

Site Costs

Land owned by Meath County Council with additional lands purchased. No additional costs envisaged.

Project Budget & Summary of Costs

Project Budget

At this juncture, Project Budget is summarised overleaf in Table 7 – Project Budget Overview

The budget utilises the Appendix C – Schedule of Accommodation and assigns the BBC of €4,000 per m2 ex VAT to the Internal areas.

A reduced BBC is included for external areas. These budget figures will need to be confirmed by Project Quantity Surveyor.

Table 7 – Project Budget Overview

Value Engineering (VE)

The Pareto Principle holds as a general rule that approximately 20% of the elements of a system will contain 80% of the total costs. Therefore there are normally only a small number of items that will contain the bulk of unnecessary costs, and it will be in this small number of items that the potential for achieving significant cost savings will be found.

Value Engineering (VE) is a creative, organised method for optimising cost and performance. The basic objective is to provide projects with the same or better performance at lower cost. The concept is that reliability, quality and maintainability cannot be lowered but cost can be lowered.

A feature of the engagement of the Design Consultants will be the requirement to carry out a VE exercise before the design is more than 30% complete and to carry out a second VE exercise at or before 70% design completion. It is at this 30% stage that the preliminary design will be presented to the Project Team including the NDFEM and at a later date at or before the 70% design completion.

Cost Management Procedures

Revised Cost Plans will be prepared as required at the various Stages.

Any changes to the Project will be managed by a change order procedure.

Design Team will be required to utilise a developed change order procedure so as to allow for management of costs.

This Change Order Management Procedure will be included in the Specification of Service /Design Brief which will be issued to the Design Team Consultants at Tender Stage.

At this juncture, MCCFRS envisage that the threshold which the ER can issue a change order without referring back to the MCCFRS for approval will be very low and may well be set at zero, i.e. ER will most likely need to obtain MCCFRS approval for processing and approving “change orders”.

Contract Strategy

Procurement of Consultants

Framework for Multidisciplinary and Integrated Design Team Services

Table 8  below includes an over-view of Capital Projects that Meath County Council Fire and Rescue Services with the support of the Sanctioning Authority; Department of Housing, Local Government and Heritage (DoHLGH) through the National Directorate for Fire and Emergency Management (NDFEM) propose for investment and delivery.

Table 8 – Capital Projects Summary Tracker Overview

Obviously all projects are subject to funding and approval.

There is confirmed support for Oldcastle Fire Station Upgrade Project.

MCCFRS are confident that there will be support for Capital Investment at Navan Fire Station and possibly one of the Fire Stations at Ashbourne or Dunshaughlin (at this juncture envisaged to be Ashbourne).

Given the above, the extension and upgrade of Oldcastle Fire Station is being used as part of the establishment of  a Multi-party Framework agreement for Architect Led Multidisciplinary and Integrated Design Team Services.

The Framework agreement is envisaged to provide services to allow for Upgrade and Capital Project works at 6 of the 7 Fire Stations in Country Meath.

Note: Nobber Fire Station was upgraded in recent years (2022/2023), and it is not included in Capital Works Summary Overview.

Oldcastle Fire Station Upgrade - Design Team Services

It is a basic principle of Government policy in relation to construction procurement that fixed price lump sum consultancy contracts are tendered on a competitive basis as the norm.

Table 5 above noted that 4 Principal Service Providers and a number of Specialist Consultants would be required for the Project. For ease of reference, they are summarised in Table 9 below:

| No. | Reference | Description |
| --- | --- | --- |
| Design Team – 4 Principal Services Providers |  |  |
| 1 | 1.A | Architect (including Design Team Lead), Project Manager, PSDP, Assigned Certifier, Employers Representative (ER) Note: Project Management (PM) Services are to be provided by the Architect as Lead Designer (i.e. Project Management is not a separate discipline). Note: Architect to act as Assigned Certifier under the Building Control (Amendment) Regulations 2014. |
| 2 | 2.CS | Civil / Structural Engineer |
| 3 | 3.ME | Mechanical & Electrical Engineer Note: Environmental Sustainability and BREEAM Analysis services to be provided by either the Mechanical & Electrical Engineer or by “A N Other” as a specialist |
| 4 | 4.QS | Quantity Surveyor and Whole Lifecycle Costs Manager |
|  | Specialist Consultants / Service Providers include (non-exhaustive list): |  |
| 1 | 1.A.1 | PSDP envisaged to be Architect as lead designer. Architect to include for a Specialist PSDP if expertise & experience is not available in house. |
| 2 | 1.A.2 | Architect to include for a Fire Safety Consultant Services if expertise & experience is not available in house. These services to be provided to the design team as a whole but as a specialist to the Architect as Lead. |
| 3 | 1.A.3 | Design Team to ensure Design and Construction comply with Best Practice and Applicable standard with respect to Universal Access and Design for Disabled Access (DAC). Architect to include for a Specialist Access Consultant if expertise & experience is not available in house. |
| 4 | 1.A.4 | All other related architectural services including Energy Efficiency, Acoustic design, Interior Design, Landscape design, Façade Design, 3D modelling / Presentation models, etc. if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
|  |  | Noted in Section 2.1.2.1 above that there is no particular requirement for Building Information Modelling (BIM) on this project and so there is no requirement for a BIM specialist if expertise & experience is not available in house |
| 5 | 2.CS.1 | All other related Civil / Structural engineering services appropriate for the project, including geotechnical and specialist structural design; temporary works design; etc if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the Civil & Structural Engineering Consultant and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| 6 | 3.ME.1 | As above, Mechanical & Electrical Engineer to include for an Environmental Sustainability and BREEAM Analysis Specialist if expertise & experience is not available in house. |
| 7 | 3.ME.2 | ICT related services: including Audio / Visual / Data / Security / BMS / etc. design if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the M&E Consultant and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| 8 | 3.ME.3 | All other related M&E services appropriate for the project, such as Vehicle exhaust design, Waste, HVAC, Acoustic engineering, lighting, wind / solar design etc. if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the M&E Consultant and so there is no requirement for identifying specific names for theses specialist service providers at this time. |
| 9 | 4.QS.1 | Including all such related services such as Whole Life / Life cycle costing; M & E Cost Surveying; specification advice / control / management; cost benchmarking etc. if expertise & experience is not available in house. Any of these particular specialist services required will be procured via the Architect as Design Team lead in conjunction with the Quantity Surveyor and so there is no requirement for identifying specific names for theses specialist service providers at this time. |

Table 9 – Service Providers (Principal and Specialist)

There are a number of options available in terms of the actual appointment of these Consultants / Service Providers and these include:

- Option “A” - Separate Appointments for each of the aforementioned 4 disciplines.

- Option “B” - Architecturally led Design Team (i.e. single appointment) encompassing the aforementioned disciplines.

- Option “C” – A mixture of an appointment for an Architectural Led Design Team (Service Providers 1 to 3) and a Separate appointment for Quantity Surveyor (to provide independent Quantity Surveyor and Cost Advice).

There are 2 types of procurement procedure1 available. These are:

- Type “1” - Restricted Procedure (Pass/Fail plus Qualitative)

- Type “2” - Open Procedure (Pass/Fail Only)

1Note, strictly speaking there are 4 types. However the use of the Negotiated (an exceptional procedure) and Competitive Dialogue are not appropriate for this project

MCCFRS propose to go with an Open Procedure (Type “2”), Option “B” namely a Single Appointment for an Architecturally Led Design Team for all 4 Principal Service Providers.

The rationale for adopting this approach is as follows:

- Consideration was given to appointing the Quantity Surveyor as a separate appointment to ensure independent cost advice.

- However, given that the QS must work as part of a team and given that all Service Providers will be needed to provide input in preparation of Outline Cost Plans and Preliminary Design proposals, recommendation perhaps best to have a single appointment.

- There will be a corresponding reduction in time in the administrative workload associated with the assessment and management of 2 separate procurements.

As outlined above, MCCFRS propose to procure the Design Team as part of a Multi-party Framework agreement for Architect Led Multidisciplinary and Integrated Design Team Services.

This will facilitate the procurement of Design Team for the other potential Capital Projects that are envisaged will be funded and delivered in County Meath.

Figure 6 overleaf includes an overview of the Project Organisation chart showing the interrelationship between client and service providers.

Figure 7 overleaf provides an overview of the Suitability Assessment Tasks for the Open Procedure.

Figure 8 overleaf provides an overview of Guidance Note 1.6 and its utilisation in providing guidance on Procurement Process for Consultancy Services (Technical).

Tenders will be evaluated against pre-set award criteria to determine which tenders are the “most economically advantageous”. i.e. MEAT.

Tenderers will be assessed on the basis of the extent and detail to which each of the criteria has been addressed within the submission. The criteria for Candidate Selection as part of the Suitability Assessment Questionnaire (SAQ) are detailed in the SAQ and Project Information Memorandum (PIM which accompany this PMP. Section 5.1.3 below notes same.

Those teams that Pass the Suitability Assessment Questionnaire and associated criteria will have their Tender Assessed.

The criteria for Contract Award are detailed in the Project Information Memorandum (PIM) which accompany this PMP.

Section 5.1.4 below notes same.

The Tenderer with the highest score assessed using the contact award criteria will be awarded the Contract for the Oldcastle Fire Station Upgrade. The top scoring 5 teams will be invited into the Framework for future contracts.

Details of the Framework have been developed and are included in Volume G – Framework Agreement.

Figure 6 – Project Organisation Chart

Figure 7 - Suitability assessment tasks for the open procedure

[Extract from GN-1.6.2-v1.2-17-1-12 ] available at https://constructionprocurement.gov.ie/wp-content/uploads/GN-1.6.2-v1.2-17-1-12.pdf

Figure 8 – Overview of Guidance Note 1.6 for Procurement of Consultants

Suitability Assessment Questionnaire (SAQ)

The reader is to refer to the Project Information Memorandum (PIM) and the Suitability Assessment Questionnaire (SAQ) for details.

Professional Indemnity Insurance

The reader is to refer to Section 4.4 of the Project Information Memorandum (PIM) which sets out the Professional Indemnity Insurance  (PII) requirements to be provided by the consultants. Level of PII is correlated to estimated construction cost and the details submitted by Consultants and Contractors are to be assessed by Irish Public Bodies (IPB) using their “Verification of Professional Indemnity Insurance Form” or similar.

Contract Award Criteria

The reader is to refer to the Project Information Memorandum (PIM) for details on Award Criteria for this Project.

Green Public Procurement

Meath County Council is committed to environmentally responsible purchasing and Green Public Procurement (GPP).  This requires that that all goods, products and services procured for and on behalf of the Meath County Council have the minimum harmful effect on our environment.

Award Criteria for Green Public Procurement included in the PIM for procurement of Consultants.

Procurement of Works Contractor

Similar to the engagement of consultants, the Works Contractor is to be procured either by an Open or Restricted Procedure. At this stage of the project the MCCFRS have an open mind if the procurement should be a single stage open procurement or a two stage restricted procedure.  Consultation with the appointed Architect led design team and an assessment of contracting market conditions at time of tender will determine the particular approach to be used.

Procurement Schedule

Table 9 above details a listing of the Service Providers (Principal & Service) envisaged to be included as part of the procurement of Consultant’s for the Project.

Table 10 below summarises the Procurement Requirements for the Project, the owner of the Procurement and a commentary with indicative dates for appointment / action as appropriate:

| Ref. | Description | Owner | Commentary on Requirements |
| --- | --- | --- | --- |
| DT | Design Team (DT) Consultants (Principal & Specialist Service providers) | MCCFRS | Propose to advertise early September 2025. Envisage 3 months for appointment |
| TS | Topographical Survey | DT | None envisaged given as noted that Apex Surveys have carried out a Survey. DT to review and action as necessary. |
| SI | Site Investigation | DT | DT to determine requirements and action as necessary. Envisage simple trial hole and CBR testing and compressive strength testing required. Verification of location of existing surface water drainage and all other services to be determined. |
| AA | Appropriate Assessment | DT | NIS Stage 1 AA Screening to be carried out. Stage 2 NIS is not envisaged. DT to action |
| Arch. | Archaeological Investigation | DT | None envisaged. DT to review. |
| ASB | Asbestos Survey | DT | No evidence of Asbestos. Best practice to carry out a survey and recommend that survey is carried out. |
| Inv. Weeds | Invasive Species, Giant Hogweed & Japanese Knotweed | DT | None envisaged given no evidence of same. DT to review. |
| COW | Clerk of Works | MCCFRS/DT | MCCFRS and DT to review appointment of COW to supervise Works Contractor and ensure Quality |
| WC | Works Contractor | GDA/DT | DT to determine Works Requirements, SAQ and preparation of Tender Documents for issue |

Table 10 – Procurement Schedule

Project Control and Administration

Overview

Project Governance and Management of Project Procedure Documents for the effective administration and Project implementation will be developed and provided as the project develops.

The MCCFRS Filing System Project Code Prefix for this Project is OLDFS – 22/01 and is to be included in all email project correspondence.

Contractors Documentation will be added as the Project progresses.

Change orders have been noted above. During the course of the project, issues relating to design, commissioning etc. may arise. Where an issue requires a change to be implemented, a change control procedure will first have to be followed.

Project Governance

MCCFRS will liaise with the NDFEM and DoHLGH at key Project Review stages and as the project progresses through the various stages. Reports, budgets and approvals will be requested as per NDFEM requirements.

Section 3 above outlines particular roles and responsibilities and sets out the particular external or management oversight roles.

Handover & Commissioning

The Health & Safety file which will contain the Operations & Maintenance (O&M) Manual for the Upgraded Fire Station will be handed over by the PSCS to the MCCFRS upon Substantial Completion of the Works.

MCCFRS will arrange in conjunction with the Lead Design Team and the Works Contractor arrange for demonstrations of all electrical & Mechanical plant within the school to representatives of the operations team who manage and operate the Fire Station.

Project Evaluation

Project Status Reports

Monthly Progress reports are required to be prepared by the Architect as Team lead during the Design Stage of the Project.

Architect will be engaged as the Employers Representative and will be required to prepare their own Monthly Progress report during Construction. This report to include for Quantity Surveyor Cost assessment.

Evaluation report

After Substantial Completion, the ER and his team are to chair an Evaluation Workshop with relevant project stakeholders to the project. The ER and his team are to complete an evaluation report on the project which will be circulated to all stakeholders.

The purpose of this report is to evaluate the successful delivery of the project with respect to the triple project constraints of Time, Cost and Quality /Specification and is to include an evaluation of:

- Significant Project Successes

- Project Shortcomings and Solutions.

Communication Plan

The Project Reporting Requirements are summarised in the table below and will be updated as the project progresses:

| Information Type | Provider | Frequency / Timing | Target |
| --- | --- | --- | --- |
| Feasibility Study /Preliminary Design Report | Project Architect to take lead on behalf of Team and issue | Single Issue with Preliminary Design | MCCFRS Project Coordinator |
| Design Status Report | Project Architect to prepare and issue (to include all Principal Service Providers) | Monthly (from Appointment to Commencement on site) | MCCFRS Project Coordinator |
| Project Status Report | Project Architect to prepare and issue (to include all Principal Service Providers) | Monthly (from Commencement on site to 2 months after Sub-completion) | MCCFRS Project Coordinator |
| Cost Monitoring Report | Quantity Surveyor | Feed into Project Reviews at each CWMF Stage (1-7) and Monthly input during Construction. | MCCFRS Project Coordinator |
| Construction Status Report | Contractor | Monthly | Employer’s Representative and MCCFRS Project Coordinator |
| Project Evaluation Report | Project Architect to prepare and issue | After Project Handover | MCCFRS Project Coordinator and NDFEM |

Table 11 – Reporting Requirements

The meeting schedule is tabulated below:

| Meeting | Chair | Purpose | Frequency / Timing | Output |
| --- | --- | --- | --- | --- |
| Project Steering Group (MCCFRS & NDFEM) | NDFEM /MCCFRS Project Coordinator | Forum for solving issues and setting high level direction. | Envisage 3 meetings at Briefing Stages | Agenda 3 days prior (by MCCFRS PC) and minutes 3 days post meeting (by MCCFRS PC) |
| Project Team i.e. Design Team and MCCFRS | Project Manager (PM) - | Manage Project Implementation, Monitor control and coordinate | Monthly | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| Design Team | Project Manager | Coordinate Design, discuss issues and resolve queries | Fortnightly | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| H&S Coordination | PSDP / PSCS | Review and ensure coordination with MCCFRS and operator of Fire Station to ensure continuity of service. | Provide for one meeting at handover to Contractor | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| Risk Register / Review Workshop | Design Team / MCCFRS | Review & Complete Register and Agree Actions | Allow 2 Meeting | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| Value Engineering Workshop | Design Team / MCCFRS | Review Design & Potential for Savings | Allow 2 Meetings | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| Construction Site Meetings | Contractors Representative / Employers Representative | Coordinate Construction & resolve any Construction issues | Monthly | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| Inspection / Snagging Prior to Substantial Completion | Design Team | Design Team to review Works Contractor Progress & Quality of Works | DT to determine appropriate No. | DT to issue listings of findings and actions reqd. |
| Post Substantial Completion | Design Team | - Review Snagging, completion & operational issues. - Review Status of Changes and Finance / Final Account | Allow 3 Meetings | Agenda 3 days prior (by PM) and minutes 3 days post meeting (by PM) |
| Post Project Review | Design Team / MCCFRS | Review End of Project Report | Project Closure | Agenda 3 days prior (by PM) and minutes 5 days post meeting (by PM) |

Table 12 – Meeting Schedule

Note: 	Design Team Project Manager (PM) is the Architect / Lead Designer i.e. Service Provider No. 1

Project Coordinator (PC) is MCCFRS Project Contact.

Quality Plan

It is envisaged that both the Design Consultant and Works Contractor will have some Quality Management Systems in operation. As client and sanctioning body for the project, MCCFRS will support both the design team and contractor in ensuring that they take all steps to safeguard and implement adequate quality control both at design and during construction and that they are operating a quality management system.

MCCFRS recommend that a Clerk of works is appointed for the supervision of the works on site. This will provide some degree of assurance that work will be constructed as per the specifications and work requirements.

Tabulated below are selections of the quality processes which will apply on this project:

| Quality Process | Description | Ownership |
| --- | --- | --- |
| Procurement Procedures | Adherence to the CWMF Procedures & documents | Project Coordinator & DT Lead |
| Documentation Procedures | Refer to Project Control & Administration Based on ISO 9001 type process control | Project Coordinator & DT Lead |
| Governance | Refer to Project Control & Administration, and documents referred to above | Project Coordinator & DT Lead |
| Insurances | GDA to review and ensure appropriate levels of insurance for design consultants and Work Contractors. | Project Coordinator & DT Lead |
| Technical Compliances | Design Team, Review of drawings &documents against parameters of brief and technical assessment of design quality. | Project Coordinator & DT Lead |
| Statutory Compliances | Planning, BCMS, Building Regulations Compliance. Fire Cert, Universal Access, BER Energy Report. | Design Team with MCCFRS input |
| Design Quality Audits | Best Practice, User satisfaction, buildability, compliance with overarching Masterplan principals; briefing documents. | Design Team with MCCFRS input |
| Environmental & Sustainability | Adherence to GDA process | Design Team with MCCFRS input |
| Value Management | Refer to Value Engineering in Budget | Design Team with MCCFRS input |
| Risk Register | Refer to Section on Risk Management | Design Team with MCCFRS input |
| Health & Safety | Design Risk Assessments. PSDP Statutory Compliance. Topic to be covered at all meetings. | Design Team with MCCFRS input |
| Ongoing quality review and feedback | Quality records, corrective actions, audits, non-conformance, CPD; Quality assurance and continuous improvements. Proper Quality Control mechanisms | Design Team with MCCFRS input |

Table 13 – Quality Process Summary

Health & Safety, Environmental Management

Health & Safety

As noted above the Project Supervisor Design Process (PSDP) is envisaged to be Architect as lead designer. Architect to include for a Specialist PSDP if expertise & experience is not available in house.

The works contractor will be appointed as Project Supervisor Construction Stage (PSCS).

Ensuring continuity of Operations of the Meath Fire and Rescue Service as an operational fire station is crucial. In particular Fire Station must continue to be able to receive alarms and alerts and be able to respond in a timely fashion.

The PSDP is required to assess if Construction works can be constructed with sufficient coordination and management such that the current fire station personnel do not need to decant to a temporary facility. If it is the case that operations can continue without decanting to a different location then the PSDP must outline in the Preliminary Health & Safety Plan how this is to be managed. Perhaps the Operations team can share the existing site in temporary facilities?

The PSDP must prepared a Preliminary Health & Safety Plan that sets out how continuity of operations is to be maintained and managed. The PSDP must ensure that the Project Supervisor Construction Stage (PSCS) takes the Preliminary Health & Safety Plan and develops this plan accordingly. The extent to which engagement with the Operator is to be determined by the PSDP and PSCS. At this juncture envisaged that a weekly coordination meeting will be required and that provision for same is included for in services provided by the PSDP and PSCS.

Service Providers should note that both the Preliminary Stage Health & Safety Plan prepared by the PSDP, and the Construction Stage Health & Safety Plan will need to be cognisant of above and ensure that the management of Health & Safety on the Fire Station site is managed in a SAFE way that ensures the safety of all.

Particular Risks

The Building Construction is envisaged to be over 2-4 storeys and there is likely to be some below ground construction.

Arising from the above the following Particular Risks [consistent with Schedule 1 of S.I. No. 504/2006 - Safety, Health And Welfare At Work (Construction) Regulations 2006 -2013] are likely to apply:

1.        Work which puts persons at work at risk of -

(a)        falling from a height,

(b)        burial under earth falls,

The Building Construction / Method of Construction may include the following in order to achieve Substantial Completion of the Works by 4th August 2017.

10.       Work involving the assembly or dismantling of heavy prefabricated components.

Asbestos Survey

MCCFRS not aware of Asbestos containing materials. Recommend that an Asbestos Survey is carried out.

MCC Safety Management System

Meath County Council (MCC) have a Safety Management System that conforms with all of the requirements of ISO 450001: 2018.

This certification is valid for the management of occupational safety and health for the following:

- Non-emergency activities

- Emergency response activities

- Fixed work locations: Navan Fire Station, Ashbourne Fire Station, Dunshaughlin Fire Station, Kells Fire Station, Nobber Fire Station, Trim Fire Station and Oldcastle Fire Station.

Upgrade works at Oldcastle will need to align with the Occupational Health and Safety Management System and updates necessary to the system will need to be identified by the Project team and actioned as required.

The Tendering Consultant and Works Contractors will need to demonstrate compliance with the Suitability Assessment Questionnaire (SAQ) prepared by the CWMF.

- MCC have developed a number of operating Systems, policies and procedures that support compliance with the Safety Management System.

- In order to comply with the requirement of this Safety Management System, MCC Safety Section require that all organisations who are to be appointed in the role of Project Supervisor Design Process (PSDP), Designer, Contractor, and Project Supervisor Construction Stage (PSCS)  are assessed for their competency before they are formally appointed in any of these roles. This is to ensure compliance with the Safety, Health and Welfare at Work Construction Regulations 2013.

- To support the assessment of competency, an External OSH Prequalification Questionnaire has been developed by MCC Safety Section.

- This questionnaire is titled “ SF046 External Duty Holder Prequalification Questionnaire”.

  - A copy of this questionnaire is included in Volume “I” of the Tender Documents.

- Tendering Service Providers are currently not required to complete this questionnaire as part of their Tender Return at this time.

- They are required to review the contents of the SF046 External Duty Holder Prequalification Questionnaire and satisfy themselves that they can comply with the requirements contained therein.

- Please note that the requirements contained in this Questionnaire broadly match the requirements contained in the Suitability Assessment Questionnaire (SAQ) which all tendering service providers are to demonstrate compliance with and PASS. Passing the SAQ does not negate the requirement to successfully complete and pass the competency assessment as outlined in SF046 External Duty Holder Prequalification Questionnaire.

- As noted in the Project Information Memorandum and in the Project Master Plan, the PSDP & Designer is envisaged to be Architect as lead designer.

Architect to include for a Specialist PSDP if expertise & experience is not available in house.

This LEAD is referred to as the “1.A - Architect (including Design Team Lead), Project Manager, PSDP, Assigned Certifier, Employers Representative (ER)”

- The Tenderer submitting the Most Economically Advantageous Tender (MEAT) will prior to their formal appointment to the initial Contract for the “Architect Led Multidisciplinary and Integrated Design Team Services for an extension and upgrade to Oldcastle Fire Station, Oldcastle, Co. Meath” be requested to provide the supporting information set out in the “SF046 External Duty Holder Prequalification Questionnaire.”

- Upon receipt of this information, MCC Fire and Rescue Service as Project Manager will forward this information to MCC Safety Section for their review.

- Provided they have been assessed by MCC Safety Section as having satisfactorily demonstrated their competency (by providing the aforementioned information set out in the “SF046 External Duty Holder Prequalification Questionnaire”), The 1.A - Architect (including Design Team Lead), Project Manager, PSDP, Assigned Certifier, Employers Representative (ER) will” be appointed as PSDP and Designer.

- This appointment will be for the Initial Contract.

- MCC Safety Section have developed a Template document with the Reference “SF050 - Notice of Appointment of Project Supervisor Design Process (PSDP) and Designer”

  - A copy of this DRAFT Notice of Appointment is included in Volume “I” of the Tender Documents.

- Upon successful completion of the assessment, The Appointed Architect will then have their details entered onto the live register of Health and Safety Appointments which is managed by Meath County Council Safety Section.

- Registered Appointments made by MCC are reviewed and updated. This normally means that those appointments have their competency assessed every 3 years. This means that the firm once appointed is available to other sections in Meath County Council as having been assessed as competent to fulfil the role for which they’ve been appointed for.

- Each of the 5 LEAD Framework Members who have been assessed as demonstrating compliance with the Suitability Assessment and Tender Award Criteria are required to provide the information contained in the SF046 External Duty Holder Prequalification Questionnaire.

- Provided the 5 LEAD Framework Members have been assessed by MCC Safety Section as having satisfactorily demonstrated their competency (by providing the aforementioned information set out in the “SF046 External Duty Holder Prequalification Questionnaire”), they will be included in the aforementioned Register.

- This will allow that for any follow-on contracts that arise under the Framework, the 1.A - Architect (including Design Team Lead), Project Manager, PSDP, Assigned Certifier, Employers Representative (ER) will have demonstrated their competency and can be appointed in the role of PSDP and Designer for any follow-on contracts.

Environmental Management

MCCFRS is committed to the protection and enhancement of the environment.  It takes a close and responsible interest in, and considers and respects, the physical, economic and social environments on all projects in which it is involved.

It aims to contribute towards environmental improvement and sustainable development by using best practice and innovation to minimise environmental impacts.  Environmental impacts are to be assessed at every stage of the business process in consultation with organisations working on behalf of the MCCFRS including, designers, contractors, local authorities and local stakeholders to develop agreed solutions that are sympathetic to the environment and community.  MCCFRS plays an active role in supporting and encouraging contractors in reducing their environmental impacts.

MCCFRS are currently exploring what is required to allow for the introduction of an ISO 14001 accreditation for an Environmental Management System (EMS). This will likely result in the development of an environmental action plan (produced on annual basis) seeking continual improvement and setting out specific objectives, targets and implementation steps, with the progress routinely monitored and reviewed.

Invasive Weeds

None envisaged.

Architect Led Design Team to assess if further Environmental assessment or surveys are needed.

Waste Management Plans

A significant amount of waste is falling out of the legitimate waste streams from construction projects. Construction and Demolition waste (which includes soil and stone) is now a national Enforcement priority. Whilst no significant earthworks or demolition is envisaged, the project team and in particular the Architect Led Design team must ensure compliance with current Waste Management and Disposal Legislation. They will need to prepare a Construction Environmental Management Plan (CEMP).

In addition to the CEMP a RWMP (Resource Waste Management Plan)  will be required for the project.

The EPA have published “Best Practice Guidelines for the preparation of resource &waste management plans for construction & demolition projects”. These guidelines are available at the following link and compliance with these guidelines is required..

https://www.epa.ie/publications/circular-economy/resources/CDWasteGuidelines.pdf

At this stage (Design) the Design Team will be required to identify all the waste streams that will be generated  (LOW Codes)  and quantify them. Any anticipated article 27 or 28 applications should also be identified.  At the Construction stage the contractor will identify the authorised waste collectors that are moving the waste and the Authorised Waste facilities where the waste will be deposited. This should be maintained as a live document and be available for inspection. A site register all dockets and chain of custody documents shall also be maintained. MCCFRS as the producer of the waste will have a cradle to grave responsibility for waste management.  When preparing construction contracts, the design team must include within the contract documentation (BOQ) that the items relating to waste disposal are only payable upon receipt of documentation from receiving authorised waste facilities.

Risk Management

Risk is defined as the “uncertainty of outcome” whether positive or negative. Risk management enables the project team to understand and manage potential risk, thereby minimising their impact.

Risk Register

A risk register is recommended as a good discipline. The risk register for the project lists all the identified risks and the results of their analysis and evaluation. Information on the status of the risk is also included. It is a live document that is updated as the project proceeds.

A risk workshop involving the key project stakeholders is an effective way of identifying and managing risk. It is envisaged that a risk workshop will be held for this project.

The first draft Risk Register for this project is included in Appendix “G”. The Risk Register will be updated and monitored throughout the course of the project.

Continuity of Operations

Section 9 above refers to the importance of ensuring continuity of Operations of the Meath Fire and Rescue Service as an operational fire station is crucial. In particular Fire Station must continue to be able to receive alarms and alerts and be able to respond in a timely fashion.

- If a Fire Service Station is unable to mobilise for whatever reason - resources/equipment availability/weather, there is a risk that a delay in roll out may harm lifesaving capabilities/property protection, and that the Fire Service may not meet there expected turnout times and that they may be criticised by the public, and other stakeholders such as National Oversight and Audit Commission (NOAC), media attention and possible accusations that a delay led to a serious injury or fatality, and there may be a consequent investigation, followed inevitably by bad press.

- Local logistics of fire crews responding may challenge the delivery/turnout time and that despite best efforts the fire service response time may be criticised, or the fire service may be the subject of negative NOAC findings, media attention and possible accusations that a delay led to a serious injury or fatality, and there may be a consequent investigation, followed inevitably by bad press.