## Background Information
Background information
Clúid is an Irish non-governmental organisation and Approved Housing Body with over 13,000 homes in management nationwide. Housing types include social housing, age friendly and cost rental homes across 26 counties. In Clúid as part of our Greening Strategy, we are targeting to have all of our properties brought to a minimum of B2 energy rating or better by 2030. We have begun this journey and in the past 4 years we have upgraded 1500 homes to B2 or better. Our Target is to complete out our remaining stock of approximately 2200 homes over the next 5 years. In order to achieve this, significant work is required in this short period of time. We are targeting a minimum number of 250 homes in year one, with this number increasing year on year, subject to budget. With this level of work, we are looking for a partner that will deliver on the Design, Project Management, Granting and of course the works on site to the highest possible standard.

## 1. Invitation & Summary
1. Invitation
Dear Contractor,
You are invited to quote for:
Better Energy Communities and National Home Retrofit Scheme Management Project Partner Etenders ref 7005162
1. Please review ITT and associated documents and familiarise yourself with the service requirements. 2. It is the intention to award a single party framework agreement for the scope of this competition and any related services required over a four year period. It is anticipated the recurring annual spend will be €7,000,000, the maximum value of the framework will be €35,000,000. (this spend estimate is based on value excluding benfit of grants / credits) 3. We request that you fully complete and return the documents listed in "Documents to be returned by Contractor" 4. Where page limits are defined, only information within those pages will be considered (external links will not be considered)
1.1 Competition Summary
Area | Particulars
Subject of competition | Better Energy Communities and National Home Retrofit Scheme Management Project Partner
Procedure | Open
Type of competition | Price & Quality
Price & Quality Ratio | 25% Price / 75% Quality
Location of service delivery | Dublin Ireland
Date of issue | 2025-11-21
Deadline for Queries and Clarifications | 2025-12-12
Contact for Queries and Clarifications | via etenders only
Deadline for Submission (5:00 PM GMT) | 2025-12-19
Submissions method | via etenders only
Form of Contract | Clúid Framework agreement
Term (length of contract) | Initial term of 2 years & with option to extend within the 4 year framework agreement scope
Value of the Framework | Max value €35 million over the entire framework term
Payment terms | 30 days of end of month invoice received
Minimum Public Liability cover (per incident) | 6500000
Minimum Employer’s liability cover (per incident) | 13000000
Minimum Professional indemnity cover (per incident) | 3000000
Anticipated go live date for the services | Feb / March 2026
Documents issued by Clúid | Issued (Yes/No)
ITT (separate word document) | YES
Background Information | YES
Tab 1. Competition Summary | YES
Tab 2. Eligibility Criteria | YES
Tab 3. Award Criteria | YES
Tab 4. Scope of Service separate doc (Cluid's Standard Energy Specification 25) | YES
Tab 5. Pricing Document | YES
Tab 5a. Cost proposed - option 1 | YES
Tab 5a. Cost proposed - option 2 | YES
Tab 6. Form of Tender | YES
Tab 7. Template Framework Contract (embedded file) | YES
Drawings of project to be costed | YES
Documents to be returned by Contractor | Returned (Yes/no)
Tab 2. Signed Eligibility Criteria response & Questionnaire | YES
Tab 3. Award Criteria Response | YES
Tab 5a. / 5b Pricing Documents | YES
Tab 6. Signed Form of Tender | YES

## 2. Eligibility Criteria
2. Eligibility Criteria Questionnaire
MINIMUM STANDARDS / ELIGIBILITY CRITIERIA - Pass /Fail
Bidder must confirm they can meet minimum requirments / standards set out in this section. Before a contract is issued, the preferred tenderer(s) must complete Clúid supplier on boarding process. This will verify that the preferred bidder meets the requirements detailed within this section. Note: no additional documentation / backup is required to be returned with the tender. All Fields shaded green must be responded to. Clúid will accept a completed European single procurement document (ESPD) in lieu of this form
COMPANY DETAILS
Company Name
Contact Name
Contact email
Company Address
Company Number
How Long has your company been trading?
SUB‐CONTRACTING |  | Select Below | If Yes, Provide Details:
Do you propose using any sub-contractors & What services will the sub-contractor carry out? Note, if you are relying on any sub-contractor to meet any minimum requirement of this section, each sub-contractor must complete a separate & complete response to this section. |  | YES / NO
Previous experience of other comparable clients/contracts
Applicants must provide details of three comparable projects successfully completed in the last three years. Appropriate contact details should be provided for each example referenced. This should include references similar in complexity with the needs of Clúid, specifically focusing on SEAI supported projects for: 1. Whole Building Residential Apartment retrofit experience (majorty of units and landlord area in scope) 2. Large scale residential home retrofit experience (multi home projects) with a central body (AHB, County council or similar) In the event that the evidence cannot be produced, or if Clúid is not satisfied that the minimum requirement is met, the tender will be eliminated. Clúid may contact any or all referees for verification / clarification of the reference without prior notice being given to the Tenderer. A 2 page per reference page limit applies to this section
Client | Summary of project & Comparability to this Contract | Project Value | Date & Duration | Your Role
MINIMUM RULE: Tenderers must demonstrate successful delivery of at least 3 contracts of a comparable nature and scale to Clúid’s tender requirements in the past, at least one related to whole apartment blocks and one related large scale home retrofit experience (multi unit projects) with a central body. Clúid Housing reserves the right to contact these referees directly on a confidential basis and without further reference to the Tenderer.
SEAI Certification & Experience
Applicants must meet the regulatory requirements to provide insurance related products and services in the Republic of Ireland, by being listed on the current SEAI approved providers list for the scope of services
Yes /No
Registered | Confirmation that the tenderer is Registered as SEAI "One Stop Shop" provider for the past 2 years
MINIMUM RULE: Applicants must be listed on the current SEAI "One Stop Shop" provider list provider for the past 2 years
Quality System
Applicants should provide information on the measures in place to demonstrate a commitment to quality assurance. Provide details of policies and processes in place in this regard. Specify whether these are externally certified or in-house operated. Note: alternatives equivalent to the referenced standard are acceptable, but detail of the alternative and process of testing should be made clear in your response.
MINIMUM RULE: Tenderers must demonstrate the have internal or external audited quality management process in place, to ISO 9002 or equivalent standard.
Financial and Economic Standing
Yes /No
Tax | Confirmation that the tenderer / all parties associated with the tenderer are fully tax compliant. Please refer to the tax rules contained in the Tender Response Document.
Turnover and Financial Standing | (a) Confirmation that the tendering party turnover exceeded €3,000,000 during each of the last three years. Pro rata may be accepted for more recently established firms.
(b) Confirmation of financial standing ensuring the tendering party has the financial capacity to pay its debts identified on the current statement of assets and liabilities as being the debts as they fall due.
(c) Confirmation that the tendering party has a credit score rating of 80% or higher with reputable assessment provider for each of the last 3 years.
Insurance | Confirmation of the following insurances being in place:
Insurance Type |  | Required Level
Employer’s Liability |  | €13 million any one occurrence
Public Liability |  | €6.5 million any one occurrence
Professional Indemnity |  | €3 million anyone occurrence
MINIMUM RULE: Pass /Fail (confirmation you will put insurance in place if successful is acceptable)
DECLARATION OF BONA FIDES
As per Article 57 of Public Sector Directive 2014/24/EU as implemented by SI 284 of May 2016.
Weighting: Pass/Fail
Economic Operators will be excluded from the procurement process if, A) there is evidence of a conviction relating to a specific criminal offence listed below (see 1.1) within the last five (5) years or B) if they have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security contributions (see 1.2) or C) answer Yes to situations within the last three (3) years set out in paragraphs 2.1.a to 2.1.i (except where this is disproportionate e.g. where only minor amounts are involved) or D) do not declare compliance with listed statutory obligations.
The preferred bidder may be required to provide evidence to confirm elements of this declaration prior to any contract award.
1. Has the Economic Operator or a member of their proposed consortium, (if applicable), Director, or Partner or any other person who has powers of representation, decision or control, been convicted of any of the following offences within the last five (5) years: |  | YES | NO
Please indicate your answer by marking ‘X’ in the relevant box
1.1.a | participation in a criminal organisation, as defined in Article 2 of Council Framework decision 2008/841/JHA;
1.1.b | corruption, as defined in Article 3 of the Convention on the fight against corruption involving officials of the European Communities or officials of Member States of the European Union and Article 2(1) of Council Framework Decision 2003/568/JHA as well as corruption as defined in Irish Law or the jurisdiction in which the Economic Operator is established;
1.1.c | fraud within the meaning of Article 1 of the Convention on the protection of the European Communities’ financial interests;
1.1.d | the subject of a conviction for terrorist offences or offences linked to terrorist activities or for inciting or aiding or abetting or attempting to commit an offence;
1.1.e | the subject of a conviction for money laundering or terrorist financing;
1.1.f | the subject of a conviction of child labour and other forms of trafficking in human beings;
Non-payment of taxes or social security obligations
1.2 Has it been established by a judicial or administrative decision having final and binding effect in accordance with Irish law or the legal provisions of the country in which the Economic Operator is established (if outside Ireland), that the Economic Operator is in breach of obligations related to the payment of tax and social security contributions? Note: If the response to 1.2 above is in the affirmative, please provide further information on the decision and the amounts involved.
2. An Economic Operator who answers ‘Yes’ in any of the situations set out in paragraphs 2.1.a to 2.1.j will be excluded, (except where this is disproportionate e.g. where only minor amounts are involved, or conflict a of interest can be remedied) please attach detailed explanation to any Yes response
Please indicate if any of the following situations have applied, within the past three (3) years, or currently apply, to your organisation. |  | YES | NO
Please indicate your answer by marking ‘X’ in the relevant box
2.1.a | has, in the performance of any public contract, failed to comply with applicable obligations in the field of environmental, social and labour law applying at the place where the works were carried out or the services provided, as established by EU law, national law, collective agreements or by international, environmental, social and labour law listed in Annex X of Directive 2014/24/EU;
2.1.b | is bankrupt or the subject of insolvency or winding-up proceedings, its assets are being administered by a liquidator or by the court, or has entered into an arrangement with creditors, suspended its business activities or is in any analogous situation arising from a similar procedure under national laws and regulations;
2.1.c | is guilty of grave professional misconduct which renders its integrity questionable;
2.1.d | has entered into agreements with other economic operators aimed at distorting competition;
2.1.e | has a conflict of interest within the meaning of Article 24 of 2014/24/EU
2.1.f | confirms that it has had prior involvement in the preparation of the procurement procedure which has resulted in a distortion of competition, as referred to in Article 41 of 2014/24/EU, that cannot be remedied by other, less intrusive, measures;
2.1.g | has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions.
2.1.h | is guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria;
OR | has withheld such information or is not able to submit supporting documents required under Article 59 of Directive 2014/24/EU; or
2.1.i | has undertaken to:
· unduly influence the decision-making process of the contracting entity, or
· obtain confidential information that may confer upon the Tenderer undue advantages in the procurement procedure; or negligently provide misleading information that may have a material influence on decisions concerning exclusion, selection or award.
2.1.j | Is excluded by circumstances listed in Article 29 of Council Directive 92/50/EEC (Coordinating Procedures for the Award of Public Service Contracts) or Article 20, Paragraph 1 of EU Council Directive 93/36/EEC of 14th June 1993
3 STATUTORY OBLIGATIONS
We confirm that we are fully compliant with the following legislation, or equivalent legislation in our country of establishment / operation: (in case of a No response provide a full explanation) |  | YES | NO
(i) | Employment Equality Acts 1998-2011
(ii) | Equal Status Acts 2000-2011
(iii) | National Minimum Wage Act 2000 as amended
(iv) | Organisation of Working Time Act 1997 as amended
(v) | Safety, Health and Welfare at Work Act 2005 and Safety, Health and Welfare at Work (General Application) Regulations 2007
(vi) | Disability Act 2005
(vii) | We have procedures in place to ensure that our subcontractors, if any are used for this contract, apply the same standards.
This Declaration is made for the benefit of Clúid Housing Association:
I certify that the information provided in this declaration (A6-1 to A6-3) is accurate and complete to the best of my knowledge and belief. I understand that the provision of inaccurate or misleading information in this Declaration will lead to my organisation being excluded from participation in this and future tenders and I am signing on behalf of:
Name of Economic Operator
Signature
Name
Rank / Position
NOTE: The term Economic Operator covers equally the concepts of Contractor, Supplier and Service Provider whether as Candidate, Tenderer or Participant under an award procedure in accordance with the relevant Public Procurement Directive.

## 3. Award Criteria
3. Award Criteria
The competition assessment will be awarded on the basis of the either Lowest Cost or a Price / Quality ratio (economically advantageous tender)defined in Appendix 1. The scoring methodology is defined in 3.2.1 of the ITT document. Where a Price / Quality ratio is defined the following will apply, should be responded to.
Criterion |  | Response Assessed per option | Page limit | Weighting | Marks | Minimum Section Pass
A | Test project quality assessment | Yes (min 1 max 2 options) | 2 | 25% | 250 | 40%
B | Project Management | No | 1 | 15% | 150 | 40%
C | Resident Experience | No | 1 | 15% | 150 | 40%
D | Sustainability | No | 1 | 10% | 100 | 40%
E | Warranty | Yes (min 1 max 2 options) | 1 | 5% | 50 | None
F | Adding value for Clúid | No | 1 | 5% | 50 | None
| Test project Cost Assessment | Yes (min 1 max 2 options) | N/A | 25% | 250 | None
TOTAL |  |  |  | 100% | 1000
Please note the following:
1. Where Criterion have a minimum pass score of marks for that section (A to F), failure to pass any section will render the entire submission to be excluded award consideration. Each sub section on cost must have a cost entered, a zero or blank sub-section in the Pricing Document may result in exclusion of the entire bid.
2. Clúid reserves the right to shortlist qualified bidders based on their written submission only, and only invite shortlisted bidders to present / interview
3. For Criterion A through F, final scores may be determined based on the combination of your written submission and fixed time presentation / interview, which will be recorded.
CRITERION A
Tenderers should submit detail on their proposed solutions to the Typical Project. Proposals should address each of the following:
Test project quality assessment Given an overview of your proposed upgrade solution and rationale for proposing it. (in keeping with guidance and specification issued). What do you see as the relative benefits of this solution to Clúid / the Residents of the properties. What consideration has been taken with regard to long term operation and effectiveness of the proposed solution? How can you ensure the value of credits / grants proposed will be attainable over the initial 2 year contract term? Answer this Criterion separately for each option proposed.
Responses to this criterion will be assessed on an per option proposed basis
CRITERION B
Tenderers should submit proposals on how the services will be delivered to meet the specification issued. Proposals should address each of the following:
Project Management. Please walk through your proposed project management cycle and method. Detail the key points and actions for Clúid throughout to include the process around Administration, documents (certs, letters, contacts), resident liaising, communication, complaint management, reports, etc
Responses to this criterion will be assessed on an overall basis
CRITERION C
Tenderers should submit proposals on how the services will be delivered to meet the specification issued. Proposals should address each of the following:
Resident Experience Please explain your procedures and approach to ensure resident satisfaction before, during and after each upgrade project. Detail the processes you have in place to guard tenant personal information.
Responses to this criterion will be assessed on an overall basis
CRITERION D
Tenderers should submit proposals on how the services will be delivered sustainably. Proposals should address each of the following:
What evidence would you proposed share with Clúid during the term of the contact, with regard to: 1) assessment of suitability of products in your supply chain and how that impacts product selection 2) recycling or re-use of all waste / excess associated with Clúid projects.
CRITERION E
Tenderers should submit proposals on how the services will be delivered to meet the specification issued. Proposals should address each of the following:
Warranty The following minimum warranty's are expected: 2 years parts and labour + further 3 years on parts for all products supplied, and 1 year on works defects. Please detail the proposed warranty period(s), manufacturer(s) and all conditions on the same for the products and works you propose(per option proposed) During the warranty period Clúid repairs operatives are often called on to look at minor issues with installations as part of our first time fix approach to repairs call outs. Please explain how you would support this approach while insuring warranty remains valid.
Responses to this criterion will be assessed on an per option proposed basis
CRITERION F
Tenderers should submit proposals on how the services will be delivered to meet the specification issued. Proposals should address each of the following:
Additional Value What additional value would your organization offer Clúid during the contract. For example: joint research, environmental improvements, specific support for larger project management, working to improve BER related data on the Clúid estate etc.
Responses to this criterion will be assessed on an overall basis

## 4. Scope of Services
4. Scope of Service / Requirements to be Provided
Please refer to separate Cluid's Standard Energy Specification 25 document

## 5. Price
5 Price
Your tender price will be established based on your proposed solution(s) to typical project. Your proposed solution will be assesed on both cost (sheet price sheets 5a & 5b) and quality. Your proposed solution(s) must meet the requirments detailed in this section and the Cluid's Standard Energy Specification 25. You may submit up to 2 Seperate proposed solutions for this question, each will be assessed seperatley.
Each proposed submission must include the following:
Smart Control energy saving heating systems that are compatible with the heating system being proposed for each apartment.
System to be easily accessible whether at home or on holidays.
Compatible with Smart metering.
All submissions should be future proofed, where existing internal units are compatible with next generation external units and vice versa, avoid reliance on cloud based software to be fully fuctional
Warranty duration for each component being proposed in each proposal.
A list of grants including amounts which will be applicable to each apartment.
Health & Safety for maintenance and future proofing should also be highlighted.
As part of the submission under Award Criterion A, detailed proposals for the heating in each apartment including the provision of hot water should be provided.
Typical Project Details
A set of plans are attached to this tender; the plans are of a block of apartments split into 4 separate blocks linked by common corridors spread over 4 floors. The apartments were built in 2003/4 traditional build with 2 lines of blockwork, 215mm internal leaf and 100mm external leaf with 100mm cavity that has 50mm areoboard insulation.
The concrete hollowcore flooring with structural screed between each level, and under the flat roof which has 100mm rigid polystyrene insulation under the Trocal uPVC roofing membrane carried ‘’up’’ the 900mm high parapet wall around the perimeter of the roofs and links capped with a precast concrete wall capping.
The concrete floor structure is not to be interfered with for any proposal.
As part of the tender process, we request each tender submission is submitted with an assessment and recommendation for the energy upgrade of all 57 apartments as each tendering contractor is an SEAI approved Contractor, it is assumed they will have the relevant experience to come up with a properly thought out highly recommended proposal that will not only provide value for money but also take into account future maintenance costs and realistic running costs with the ability to retrospectively provide evidence of those running costs built into the heating system using modern technologies with easy on site readings and means for off-site access all year round.
There are 45 No. 2 bedroom apartments and 12 No. 1 bedroom apartments, the existing heating is electric storage heating in the living areas, panel heaters in bedrooms and blow heaters in the bathrooms, the water is heated by 2 emersions in a copper cylinder which is fed from a common cold-water tank on the roof of each block.
There are service ducts with all services to each apartment that can be accessed from the common corridor all are visible on the attached plans, the cold-water feed from the roof, the mains water and the foul water pipe work run in the service ducts separate from the electrical ducts.
Each apartment has its own electric supply which supply power to the storage heating system any proposal should take into account the safe removal and making safe any electrical disturbance done by the tendering contractor, the tendering contractor will not be expected to carry out any painting, decoration however they are expected to leave all areas ready for painting by the tenant.
Health & Safety
The building is fully occupied so health and safety is very important as part of the assessment each contractor should compile a risk assessment and a method statement for installing the recommended heating system, windows and doors and air extraction ventilation system in their submission.
The risk assessment should be based on all 2-bedroom apartments and all 1-bedroom apartments with a combined average occupancy of 2.5 people, aged from 9 months to 90 years, the building is fully occupied.
Method statements should compliment the risk assessment to create a safe system of work while also considering the constant changing environment of each apartment and its occupants as some will have small children.
Clúid does not expect a full set of RAMS, we expect an overview from each tendering contractor on how it has managed similar multi storey projects in the past with examples of what went right and what went wrong, and the lessons learned and changes implemented based on those experiences.
Programming
A program of works should be including giving clear guidelines for example: Duration of the works, Phasing, critical points, access and egress, noise control, tenant information & management, working hours, Management Structure, etc. This program should be realistic and based on experience for the benefit of this tender, certain assumptions can be assumed, however they need to be highlighted and explained.
Warranties & Parts
The level and extent of warranties is important to Clúid as is the easy access to spare parts so any recommended proposal should be accompanied by manufacturer’s confirmation of warranty and supply of future parts, also confirmation that any future upgraded component is compatible with existing component parts, for example, split systems replacing the external unit without have the need to replace the internal unit and vice versa.
Annual V Bi-annual Service
With the high costs of service and the shortage of experienced service engineers Manufacturers who accept and maintain their warranties for bi-annual servicing should be highlighted in the tender.
While this may mean additional work this additional work should be highlighted.
Proposals/Recommendations
The contractor is expected to make a recommendation based on one of their proposed choices, explaining why they recommend this proposal with detailed reasoning for their choice, this recommendation should include manufacturer’s details, supply chains, warranties, maintenance cycles, etc.
Landlord/Common Areas
Landlord Area recommendation
For clarity, the common area proposal and the apartment proposal should be separate and stand-alone proposals with separate recommendations made for each.
Landlord areas
The landlord area comprises of all internal corridors, stair wells, public toilets, offices, lounge, recreation rooms, common kitchen, laundry, storerooms, service ducts, etc
The heating in these areas is costly and with the upgrade of all the apartments it’s important to maintain heating consistency in the corridor areas, with this in mind each tendering contractor should propose a heating system to replace the existing high-cost storage heaters.
The proposed heating system/s should have some level of energy saving controls and possible paybacks, example: PV panels, battery storage, smart metering systems, remote monitoring and environmental controls.
The indicated savings and payback periods for the landlord area should be realistic considering all future maintenance and parts should be taken into consideration.
Easy access for maintenance and future replacement should also be taken into consideration.
Additional costs for unforeseen items
Due the multiplication of costs for any specific item that may show up during a construction programme like this we have put in an unforeseen costly item.
The cold-water tanks on the roof are not sufficient to keep all the apartments supplied with water at peak times after a competitive quote process the plumbing contractor cost for this is €1,500, 00/per apartment €85,500
The Plumbing contractor has stated the tanks on the roof are sufficient to supply the 2 ground floors of each apartment block, so a decision must be made on the best solution so a recommendation on this and on how best to proceed is required from each tenderer bearing in mind future costs and weather conditions.
Please explain your decision and solution in Award Criterion A

## 5a Price Tender
5a Price Tender (Option 1)
Clúid has compiled this estimate net cost of the upgrade works for a typical project based on prior projects and level of investment Clúid would typically make. This value will be fixed for all bidders, you should propose solutions which will cost this much or less to supply (net cost of supply & works). Enter your markup on cost percentage to operate all projects to the Cluid's Standard Energy Specification 25, your energy credits and total grant funding for the project based on the solution you are proposing. All supplied and proposed cost to exclude VAT.
Values you must complete are highlighted green. Only edit other areas where noted.
The cost proposal is to split into Apartment and Landlord area sections, both must be fully completed, blanks or zeros in the total mark up column specifically will generally be considered unacceptable, unless fully explained and still meeting all the requirements of the tender.
The euro value for energy credits & grants you submit must be attainable based on this project completing at time of tender submission, similar (or better) value must also be attainable on projects over the initial 2 year term. Clúid may require detailed evidence as to how the value you have entered was established, and Cluid reserve the right the exclude portions of the total credit value which in Cluid's view are not attainable over the term of the contract. Where the energy credit value proposed is more that the simple open market value of a credit, you should fully explain the makeup of the value proposed in your response.
It is expected that winning bidder will operate the procurement of all upgrade works in line with SEAI guidance / requirements, and the Total Mark up on cost you tender will apply to all projects during initial contract term
| Apartments | [8 empty] | Grant breakdown based on your proposed solution (delete heading and apply new if required)
| NAME | Build Year | MPRN (Typical) | Block 4 | Floor | Type | Max Net install Cost Figure for recommended system | Total Mark up (Overheads Prelims & profit as a % of Cost) | Total Cost of Upgrades pre grants/credits | Heat Pump systems | Heat Pump Air To Air | Heating Controls | Rads | Windows | Doors | Cavity wall | Solar, PV | Project Management | Energy Assessment | Bonus B2 | Energy Credits (Euro value at time of time of tender) | Total Grant & Energy Credit | Tender Cost
| Apartment No. 1 | 2003/4. | 10301410001 | Block B | Ground | 1 Bed -Type 1 | 24000 | 0% | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
| Apartment No. 2 | 2003/4. | 10301410001 | Block B | Ground | 2 Bed -Type 2 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 3 | 2003/4. | 10301410001 | Block B | Ground | 2 Bed -Type 3 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 4 | 2003/4. | 10301410001 | Block B | Ground | 2 Bed - Type 4 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 5 | 2003/4. | 10301410001 | Block C | Ground | 1 Bed -Type 1 | 24000 | 0% | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
| Apartment No. 6 | 2003/4. | 10301410001 | Block C | Ground | 2 Bed - Type 4 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 7 | 2003/4. | 10301410001 | Block C | Ground | 2 Bed -Type 3 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 8 | 2003/4. | 10301410001 | Block C | Ground | 2 Bed -Type 2 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 9 | 2003/4. | 10301410001 | Block D | Ground | 1 Bed -Type 1 | 24000 | 0% | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
| Apartment No. 10 | 2003/4. | 10301410001 | Block D | Ground | 2 Bed -Type 2 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 11 | 2003/4. | 10301410001 | Block D | Ground | 2 Bed -Type 3 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 12 | 2003/4. | 10301410001 | Block D | Ground | 2 Bed - Type 4 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 13 | 2003/4. | 10301410001 | Block A | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 14 | 2003/4. | 10301410001 | Block A | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 15 | 2003/4. | 10301410001 | Block A | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 16 | 2003/4. | 10301410001 | Block B | 1st Floor | 1 Bed -Type 1 | 25000 | 0% | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
| Apartment No. 17 | 2003/4. | 10301410001 | Block B | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 18 | 2003/4. | 10301410001 | Block B | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 19 | 2003/4. | 10301410001 | Block B | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 20 | 2003/4. | 10301410001 | Block C | 1st Floor | 1 Bed -Type 1 | 25000 | 0% | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
| Apartment No. 21 | 2003/4. | 10301410001 | Block C | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 22 | 2003/4. | 10301410001 | Block C | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 23 | 2003/4. | 10301410001 | Block C | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 24 | 2003/4. | 10301410001 | Block D | 1st Floor | 1 Bed -Type 1 | 25000 | 0% | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
| Apartment No. 25 | 2003/4. | 10301410001 | Block D | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 26 | 2003/4. | 10301410001 | Block D | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 27 | 2003/4. | 10301410001 | Block D | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 28 | 2003/4. | 10301410001 | Block A | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 29 | 2003/4. | 10301410001 | Block A | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 30 | 2003/4. | 10301410001 | Block A | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 31 | 2003/4. | 10301410001 | Block B | 2nd Floor | 1 Bed -Type 1 | 26000 | 0% | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
| Apartment No. 32 | 2003/4. | 10301410001 | Block B | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 33 | 2003/4. | 10301410001 | Block B | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 34 | 2003/4. | 10301410001 | Block B | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 35 | 2003/4. | 10301410001 | Block C | 2nd Floor | 1 Bed -Type 1 | 26000 | 0% | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
| Apartment No. 36 | 2003/4. | 10301410001 | Block C | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 37 | 2003/4. | 10301410001 | Block C | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 38 | 2003/4. | 10301410001 | Block C | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 39 | 2003/4. | 10301410001 | Block D | 2nd Floor | 1 Bed -Type 1 | 26000 | 0% | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
| Apartment No. 40 | 2003/4. | 10301410001 | Block D | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 41 | 2003/4. | 10301410001 | Block D | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 42 | 2003/4. | 10301410001 | Block D | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 43 | 2003/4. | 10301410001 | Block A | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 44 | 2003/4. | 10301410001 | Block A | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 45 | 2003/4. | 10301410001 | Block A | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 46 | 2003/4. | 10301410001 | Block B | 3rd Floor | 1 Bed -Type 1 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 47 | 2003/4. | 10301410001 | Block B | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 48 | 2003/4. | 10301410001 | Block B | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 49 | 2003/4. | 10301410001 | Block B | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 50 | 2003/4. | 10301410001 | Block C | 3rd Floor | 1 Bed -Type 1 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 51 | 2003/4. | 10301410001 | Block C | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 52 | 2003/4. | 10301410001 | Block C | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 53 | 2003/4. | 10301410001 | Block C | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 54 | 2003/4. | 10301410001 | Block D | 3rd Floor | 1 Bed -Type 1 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 55 | 2003/4. | 10301410001 | Block D | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 56 | 2003/4. | 10301410001 | Block D | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 57 | 2003/4. | 10301410001 | Block D | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Sub Total | [5 empty] | 1653000 |  | 1653000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653000
Additional items
| 200-350L slimline cold water booster and tank set (requested by Clúid) | 2003/4 | All of above | 57 apartments @ €1500. | All | All | 85500 | 0% | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500
| Add breakdown if any additional (included in cost) items across all apartments (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add breakdown if any additional (included in cost) items across all apartments (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | [5 empty] | 85500 |  | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500
| Landlord Areas | [8 empty] | Grant breakdown based on your proposed solution (delete heading and apply new if required)
| NAME | Build Year | MPRN | Block | Floor | Type | Max Net install Cost Figure for recommended system | Total Mark up (Overheads Prelims & profit as a % of Cost) | Total Cost of Upgrades pre grants/credits | Heat Pump systems | Heat Pump Air To Air | Heating Controls | Rads | Windows | Doors | Cavity wall | Solar, PV | Project Management | Energy Assessment | Bonus B2 | Energy Credits (Euro value at time of time of tender) | Total Grant & Energy Credit | Tender Cost
| Landlord Areas | 2003/4. | Not Avaialbe | All | All | Common | 44000 | 0% | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000
| Add breakdown if any additional (included in cost) items across all landlord areas (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add breakdown if any additional (included in cost) items across all landlord areas (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | [5 empty] | 44000 |  | 44000 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 44000
[17 empty] | Tendered cost (option 1) |  |  |  |  | 1782500

## 5b Price Tender
5b Price Tender (Option 2)
Clúid has compiled this estimate net cost of the upgrade works for a typical project based on prior projects and level of investment Clúid would typically make. This value will be fixed for all bidders, you should propose solutions which will cost this much or less to supply (net cost of supply & works). Enter your markup on cost percentage to operate all projects to the Cluid's Standard Energy Specification 25, your energy credits and total grant funding for the project based on the solution you are proposing. All supplied and proposed cost to exclude VAT.
Values you must complete are highlighted green. Only edit other areas where noted.
The cost proposal is to split into Apartment and Landlord area sections, both must be fully completed, blanks or zeros in the total mark up column specifically will generally be considered unacceptable, unless fully explained and still meeting all the requirements of the tender.
The euro value for energy credits & grants you submit must be attainable based on this project completing at time of tender submission, similar (or better) value must also be attainable on projects over the initial 2 year term. Clúid may require detailed evidence as to how the value you have entered was established, and Cluid reserve the right the exclude portions of the total credit value which in Cluid's view are not attainable over the term of the contract. Where the energy credit value proposed is more that the simple open market value of a credit, you should fully explain the makeup of the value proposed in your response.
It is expected that winning bidder will operate the procurement of all upgrade works in line with SEAI guidance / requirements, and the Total Mark up on cost you tender will apply to all projects during initial contract term
| Apartments | [8 empty] | Grant breakdown based on your proposed solution (delete heading and apply new if required)
| NAME | Build Year | MPRN (Typical) | Block 4 | Floor | Type | Max Net install Cost Figure for recommended system | Total Mark up (Overheads Prelims & profit as a % of Cost) | Total Cost of Upgrades pre grants/credits | Heat Pump systems | Heat Pump Air To Air | Heating Controls | Rads | Windows | Doors | Cavity wall | Solar, PV | Project Management | Energy Assessment | Bonus B2 | Energy Credits (Euro value at time of time of tender) | Total Grant & Energy Credit | Tender Cost
| Apartment No. 1 | 2003/4. | 10301410001 | Block B | Ground | 1 Bed -Type 1 | 24000 | 0% | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
| Apartment No. 2 | 2003/4. | 10301410001 | Block B | Ground | 2 Bed -Type 2 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 3 | 2003/4. | 10301410001 | Block B | Ground | 2 Bed -Type 3 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 4 | 2003/4. | 10301410001 | Block B | Ground | 2 Bed - Type 4 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 5 | 2003/4. | 10301410001 | Block C | Ground | 1 Bed -Type 1 | 24000 | 0% | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
| Apartment No. 6 | 2003/4. | 10301410001 | Block C | Ground | 2 Bed - Type 4 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 7 | 2003/4. | 10301410001 | Block C | Ground | 2 Bed -Type 3 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 8 | 2003/4. | 10301410001 | Block C | Ground | 2 Bed -Type 2 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 9 | 2003/4. | 10301410001 | Block D | Ground | 1 Bed -Type 1 | 24000 | 0% | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000
| Apartment No. 10 | 2003/4. | 10301410001 | Block D | Ground | 2 Bed -Type 2 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 11 | 2003/4. | 10301410001 | Block D | Ground | 2 Bed -Type 3 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 12 | 2003/4. | 10301410001 | Block D | Ground | 2 Bed - Type 4 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 13 | 2003/4. | 10301410001 | Block A | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 14 | 2003/4. | 10301410001 | Block A | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 15 | 2003/4. | 10301410001 | Block A | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 16 | 2003/4. | 10301410001 | Block B | 1st Floor | 1 Bed -Type 1 | 25000 | 0% | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
| Apartment No. 17 | 2003/4. | 10301410001 | Block B | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 18 | 2003/4. | 10301410001 | Block B | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 19 | 2003/4. | 10301410001 | Block B | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 20 | 2003/4. | 10301410001 | Block C | 1st Floor | 1 Bed -Type 1 | 25000 | 0% | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
| Apartment No. 21 | 2003/4. | 10301410001 | Block C | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 22 | 2003/4. | 10301410001 | Block C | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 23 | 2003/4. | 10301410001 | Block C | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 24 | 2003/4. | 10301410001 | Block D | 1st Floor | 1 Bed -Type 1 | 25000 | 0% | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
| Apartment No. 25 | 2003/4. | 10301410001 | Block D | 1st Floor | 2 Bed -Type 2 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 26 | 2003/4. | 10301410001 | Block D | 1st Floor | 2 Bed -Type 3 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 27 | 2003/4. | 10301410001 | Block D | 1st Floor | 2 Bed - Type 4 | 29000 | 0% | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
| Apartment No. 28 | 2003/4. | 10301410001 | Block A | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 29 | 2003/4. | 10301410001 | Block A | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 30 | 2003/4. | 10301410001 | Block A | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 31 | 2003/4. | 10301410001 | Block B | 2nd Floor | 1 Bed -Type 1 | 26000 | 0% | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
| Apartment No. 32 | 2003/4. | 10301410001 | Block B | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 33 | 2003/4. | 10301410001 | Block B | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 34 | 2003/4. | 10301410001 | Block B | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 35 | 2003/4. | 10301410001 | Block C | 2nd Floor | 1 Bed -Type 1 | 26000 | 0% | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
| Apartment No. 36 | 2003/4. | 10301410001 | Block C | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 37 | 2003/4. | 10301410001 | Block C | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 38 | 2003/4. | 10301410001 | Block C | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 39 | 2003/4. | 10301410001 | Block D | 2nd Floor | 1 Bed -Type 1 | 26000 | 0% | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
| Apartment No. 40 | 2003/4. | 10301410001 | Block D | 2nd Floor | 2 Bed -Type 2 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 41 | 2003/4. | 10301410001 | Block D | 2nd Floor | 2 Bed -Type 3 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 42 | 2003/4. | 10301410001 | Block D | 2nd Floor | 2 Bed - Type 4 | 30000 | 0% | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
| Apartment No. 43 | 2003/4. | 10301410001 | Block A | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 44 | 2003/4. | 10301410001 | Block A | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 45 | 2003/4. | 10301410001 | Block A | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 46 | 2003/4. | 10301410001 | Block B | 3rd Floor | 1 Bed -Type 1 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 47 | 2003/4. | 10301410001 | Block B | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 48 | 2003/4. | 10301410001 | Block B | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 49 | 2003/4. | 10301410001 | Block B | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 50 | 2003/4. | 10301410001 | Block C | 3rd Floor | 1 Bed -Type 1 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 51 | 2003/4. | 10301410001 | Block C | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 52 | 2003/4. | 10301410001 | Block C | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 53 | 2003/4. | 10301410001 | Block C | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 54 | 2003/4. | 10301410001 | Block D | 3rd Floor | 1 Bed -Type 1 | 28000 | 0% | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
| Apartment No. 55 | 2003/4. | 10301410001 | Block D | 3rd Floor | 2 Bed -Type 2 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 56 | 2003/4. | 10301410001 | Block D | 3rd Floor | 2 Bed -Type 3 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Apartment No. 57 | 2003/4. | 10301410001 | Block D | 3rd Floor | 2 Bed - Type 4 | 32000 | 0% | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000
| Sub Total | [5 empty] | 1653000 |  | 1653000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653000
Additional items
| 200-350L slimline cold water booster and tank set (requested by Clúid) | 2003/4 | All of above | 57 apartments @ €1500. | All | All | 85500 | 0% | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500
| Add breakdown if any additional (included in cost) items across all apartments (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add breakdown if any additional (included in cost) items across all apartments (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | [5 empty] | 85500 |  | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500
| Landlord Areas | [8 empty] | Grant breakdown based on your proposed solution (delete heading and apply new if required)
| NAME | Build Year | MPRN | Block | Floor | Type | Max Net install Cost Figure for recommended system | Total Mark up (Overheads Prelims & profit as a % of Cost) | Total Cost of Upgrades pre grants/credits | Heat Pump systems | Heat Pump Air To Air | Heating Controls | Rads | Windows | Doors | Cavity wall | Solar, PV | Project Management | Energy Assessment | Bonus B2 | Energy Credits (Euro value at time of time of tender) | Total Grant & Energy Credit | Tender Cost
| Landlord Areas | 2003/4. | Not Avaialbe | All | All | Common | 44000 | 0% | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000
| Add breakdown if any additional (included in cost) items across all landlord areas (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add breakdown if any additional (included in cost) items across all landlord areas (overwrite this cell - not required if not applicable) | [5 empty] | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | [5 empty] | 44000 |  | 44000 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 44000
[17 empty] | Tendered cost (option 1) |  |  |  |  | 1782500

## 6. Form of Tender
6. Form of Tender
Better Energy Communities and National Home Retrofit Scheme Management Project Partner
Tender Return Date | 2025-12-19
Submission: | Via Etenders only
TO: THE CHIEF EXECUTIVE, Clúid Housing Association 159-161 Sheriff Street Upper Dublin 1
We are willing and hereby tender to execute and fully complete the whole of the services and obligations as described in the specification/schedule of works and in accordance with the contract referred to therein for the sum of:
(In Words) | * Insert total value of works Inclusive of Vat
With a commencement date of Q1 2025
Our tender will remain open for acceptance by you for a period of 12 weeks from the tender return date
SIGNED: | *_____________________________________
POSITION: | *_____________________________________
DATE: | *_____________________________________