DEFINITIVE PROJECT BRIEF

Housing Development, Lord Edward Street, Mountmellick, Co Laois County Council, for Laois County Council

DESCRIPTION OF SERVICES

Development of 9 No. housing units,

at Lord Edwad Street, Mountmellick, Co. Laois.

Consultancy Appointment of:

- Lead Consultant, Architectural

- Structural & Civil Engineering

- Building Services Engineering

- Quantity Surveying

- Project Supervisor Design Process

- Design & Assigned Certifiers

- Employer’s Representative Services.

| Item No. | Parameter | Description |
| --- | --- | --- |
| 1 | Objective | Provide social housing under the Housing for all housing plan |
| 2 | Purpose | Satisfy the housing need of an appropriate number of applicants on the Councils Housing Waiting List. |
|  | Scope | Laois County Council is seeking an Architect led design Team to provide the full architectural & engineering & quantity Surveying services required to deliver the Design, the Procurement of a Contractor and Contract Management of the project, including full and detailed Architectural and Engineering drawings, and a complete Bill of Quantities. In addition, Building Energy Rating certificates are to be provided for each individual unit upon substantial completion of the project. The Design Team will produce successive Preliminary Designs until a proposal that is acceptable to both the Department of Housing and Laois County Council is achieved. The Design Team will then take the scheme through the Part VIII Planning Approval Process, making whatever changes are required during the process. Tenders will be invited for the construction of the scheme. The Form of Contract shall be the Public Works Contract for Building Works designed by the Employer. The procurement of the contractor shall be in compliance with the Government’s Construction Procurement Reform programme and the Capital Works Management Framework. (CWMF) (constructionprocurement.gov.ie.) The design team shall undertake the tender assessment and submit a tender report and recommendation for the appointment of a contractor. The Design Team will manage and supervise the construction of the scheme and handover of the completed scheme to Laois County Council. The scope of the consultancy services required is as follows: Prepare a scheme layout for submission to the Department of Housing, Local Government and Heritage for approval. It should be noted that in order to achieve Departmental Approval, the scheme layout may require a number of revisions. The approved layout shall be submitted to Laois County Council for Part VIII Planning Approval and (if required) the design team shall modify the design and the drawings to achieve and to comply with the planning permission. The relevant stages under the CWMF are as follows: - Preliminary Report Stage. (ii) Design Stage (iii) Tender Action, evaluation, award stage (iv) Construction Stage (v) Handover of works stage. The Design Team shall provide the full set of services as set out for Architect, Civil/Structural Engineer, Building Services (M&E) Engineer, Quantity Surveyor, & Project Supervisor Design Process, in the Scope of Services -- Office of Government Procurement Framework -- Agreement for Full, Integrated Design Team. In addition, the Design Team shall also prepare Contract Documents to procure site investigation work, including a Site Investigation Report. This Report shall be issued as part of the tender documents for the main contract. The Design Team will produce detailed designs based on the Part 8 layout drawings for the scheme. The detailed drawings have to be agreed with the local authority and be acceptable to the Department of Housing, Local Government and Heritage. Tenders will be invited for the construction of the scheme. The Form of Contract shall be the Public Works Contract for Building Works designed by the Employer PW -CF 1. The procurement of the contractor shall be in compliance with the Government’s Construction Procurement Reform programme and the Capital Works Management Framework. (CWMF) (constructionprocurement.gov.ie.) The design team shall undertake the tender assessment and submit a tender report and recommendation for the appointment of a contractor. The design team will manage and supervise the construction of the scheme and handover of the completed scheme to Laois County Council. A sustainability report shall be provided by the building services consultant at detailed design stage outlining the various options (included estimated cost) with regard to the thermal and renewable properties of the building elements to achieve the required energy rating. BERS will also be provided to the Client at handover stage and the cost of providing these BERs should be allowed for in the % fee quoted/Tender Sum The design shall be in conformance with current Building Regulations and the Design Manual for Quality Housing and shall comply with the internal layout and space provision requirements in this document. The design team will be required to revise the design to incorporate any changes that arise out of the Laois County Council and/or the Department of Housing review of the design. The design team should allow for the cost of up to 4 revisions of the overall scheme layout design. In addition the successful design team will undertake the role of Project Supervisor Design Process in accordance with the Safety, Health and Welfare at Work (Construction Regs.) 2013 for the duration of the project. |
|  | Scope (continued) | An enabling works tender pack will be prepared by the design team to underground the overhead electricity cables and the undergrounding of the overhead electricity cables will be undertaken in advance of the main contractor’s appointment. The main building contractor will undertake the construction of the scheme in accordance with the drawings prepared by the design team and undertake the role of Project Supervisor Construction Stage in accordance with the Safety, Health and Welfare at Work Act (Construction) 2013 |
| 4 | Deliverables/desired outcomes | Deliver social housing on an urban site in Mountmellick County Laois with 9 no. social housing units: construction costs as per the Schedule of Accommodation required: Sites at - Social Housing for 9 no. units at lord Edward Street, Mountmellick, County Laois Demolition of existing structure and commercial units to the rear of the site, provide, develop new pedestrian and vehicular access, 9. Number new social housing units. The units must follow the Department of Housing Design Quality manual and submit a design based on incorporating universal design (UD) units as per draft prepared in works requirements. All subject to site surveys, as unforeseen circumstances may arise. Construction costs not to exceed unit ceiling costs published by DoHLGH and that the works to be undertaken in a safe manner in compliance with all relevant Health and Safety Legislation. Prepare planning documentation and bring to Part VIII the social housing scheme. |
| 5 | Performance | Housing units to comply with Part L – Conservation of Fuel and Energy of the building regulations. All design work shall comply with the Design Manual for Quality houses (including the requirement for floor area, room sizes etc.) published by the Department of the Environment, Heritage and Local Government 2007 and current Building Regulations. |
| 6 | Assumptions | - Existing structure on site to be demolished - Neighboring boundaries to be surveyed - Possibility of underpinning to neighboring properties - Private and public open space to be provided - Substantial parking to be provided as per the County Development Plan - Incorporated bin and bike storage to be provided |
| 7 | Governance and reporting | The Department of Housing, Local Government and Heritage is the relevant Government Department providing the funding for this project (the Sanctioning Authority under the Public Spending Code) Laois County Council (the Sponsoring Agency under the Public Spending Code) through its technical staff will be co-ordinating the project. The project is subject to approval from the DHPLG. before proceeding to tender, (Approval Stage 3) and before accepting a Tender (Approval Stage 4) and entering into a contract. The Design Team shall prepare a cost estimate (Single Stage Approval) and a tender report for review by Laois Co Co and for submission to DHPLG for Approval Stage to enable the main contractor to be appointed. The design team will report directly to the Senior Engineer (S.E.) in the Housing Department. The design team leader shall be made known as part of the tender submission. Laois County Council may, at its discretion appoint a Clerk of Works (CoW) to the project. This role will be limited to keeping some records of the project. The appointed lead architect shall undertake the role of Employers Representative and shall issue any Change Orders in accordance with the contract. Note: additional expenditure over 2.5% of the contract amount will require DHPLG prior approval. The design team will also undertake the role of PSDP for the project. |
| 8 | Preferred option | To ensure that this site provides a Sustainable and aesthetically pleasing development of social houses for the benefit of the Tenants and the towns of Laois, while designing within the parameters of the current Building Regulations, other regulatory requirements and current Dept of Environment Guidance Documents. |
| 9 | Known risks | Approval from the DHPLG is required at each stage, prior to proceeding to the next Stage. |
| 10 | Value management strategies | Change Orders will be issued when required by the Employer’s Representative. The Change Orders will be issued following a recommendation by the project quantity surveyor that the contractor’s submission is value for money and in line with the rates submitted at tender stage. If the cumulative value of Change Orders exceeds 2.5% it will be necessary to seek a revised budget from the DHPLG The Design Team shall submit a Monthly Financial Review of the Project. |
| 11 | Project execution plan | Timescale from the issue of the order number to the design team Week 1 – Issue order no. to design team Week 2 – Co-ordination meeting with design team Week 5 – Submit 2no. alternative layouts to Laois County Council for approval. Week 6 – Compile submission for Approval Stage 2 from DHPLG Week 7 – Submit layout to DHPLG for review and approval. Week 11 – Finalise layout following input from DHPCLG Architectural Advisor &LCC. Week 13 – Receive Approval, Stage 2 (approval to proceed to planning and tender documents). Week 14 – finalise enabling works tender pack for undergrounding overhead lines Week 16 – Submit Part VIII planning permission Week 18 – Issue tender documents for enabling works contract to underground overhead lines Week 34 – Complete Part VIII planning process Week 36 – Complete detailed design and submit to DHPLG for Approval, Stage 3 (Approval to proceed to tender) Week 38 – appoint enabling works contractor to lay ducting in order to reroute overhead electricity lines Week 40 – DHPLG to issue Approval, Stage 3 Week 96 – Complete tender report for submission to DHPLG for Approval, Stage 4 Week 100 – Achieve Approval, Stage 4 from DHPLG Week 104 – Award contract Week 108 – issue commencement notice Week 108 – Manage and Supervise Construction Week 182 – Substantial completion and handover Week 234 – Release contract retention |
| 12 | Expected functional life | 100 years |
| 13 | Design restrictions/requirements | The Design Team shall consider the indicative layout included as part of these suite of documents. The design team shall take due cognisance of the Design Manual for Quality Housing 2022 (DHLGH), and the Employers Requirements for Detail Design of Quality Housing 2020 guidelines published by DHLGH. |
| 14 | Location | Lord Edward Street, Mountmellick, County Laois |
| 15 | Budget | €3,300,000 euros ex VAT for the construction of the combined projects. |
| 16 | Constraints | Financial – work to the approved budget. |