SAINT GABRIEL’S CEMETERY PROJECT BRIEF

Landscape Masterplan, Feasibility Study, Part 8 Planning and Works Delivery Consultancy Services for Saint Gabriel’s Cemetery, Arklow, County Wicklow

June 2026

Table of Contents

1.0 Call For Tender Introduction:	3

2.0: Project Background:	5

3.0: Project Objectives:	6

4.0 Project Criteria	7

5.0: Scope of Consultancy Services:	8

Stage 1 – Inception, Site Analysis, Surveys, Mapping and Feasibility Assessment	8

Stage 2 – Landscape Masterplan, Options Appraisal, Part 8 Planning Documentation and Cost Estimates	10

Stage 3 – Tender Documentation, Tender Support, Evaluation Support and Award Recommendation	12

Stage 4 – Construction Stage Services, Inspections, Certification and Contract Administration Support	13

Stage 5 – Handover, Snagging, Defects Support and Close-Out Report	14

6.0: Fixed Price Requirement:	15

7.0: Governance And Approvals:	15

8.0 Submission Requirements	15

9.0: Contract Award Criteria:	16

# 1.0 Call For Tender Introduction:

Wicklow County Council, through its Climate, Environment, Recreation & Amenity Directorate, are seeking a fixed lump sum Tender for Landscape Architect-led Multidisciplinary Consultancy Services for Saint Gabriel’s Cemetery, Arklow, County Wicklow.

The purpose of this commission is to:

- undertake site analysis, mapping and feasibility assessment of Saint Gabriel’s Cemetery;

- assess opportunities to maximise remaining burial capacity within the existing cemetery;

- consider options for future cemetery provision, including possible extension or new burial ground requirements;

- assess existing drainage issues and develop practical drainage and Nature Based SuDS proposals;

- prepare a Landscape Masterplan incorporating heritage, biodiversity, accessibility, circulation, public realm and amenity considerations;

- develop proposals for the enhancement of the columbarium wall area, including potential memorial garden or other appropriate landscape treatment;

- prepare Part 8 planning documentation and support Wicklow County Council through the statutory planning process;

- prepare tender and contract documentation for the approved works;

- provide construction-stage services, where instructed, through to completion and defects close-out.

The commission will be undertaken under the Standard Conditions of Engagement for Consultancy Services (Technical) – COE1.

The appointed Consultant will act as Project Lead, coordinating all specialist inputs and delivering the services across defined stages, subject to Wicklow County Council approvals.

The project will require the provision of a Landscape Architect-led multidisciplinary team, including, as required:

- Landscape Architect / Lead Consultant;

- Cemeteries and Burial Grounds Expert;

- Civil / Drainage Engineer;

- Heritage Consultant;

- Ecologist;

- Arboricultural Consultant;

- Accessibility / DMURS Consultant;

- Quantity Surveyor / Cost Consultant;

- Project Supervisor for the Design Process;

- any other specialist input required to deliver the commission.

All related fees and charges associated with the Design Team Services shall be included in the lump sum tender price. The consultancy service must be an all-in package and shall incorporate all competent consultants required to ensure the successful completion of the project.

The Design Team services shall include all stages of the service requirement as set out in this brief, the Tender Schedule FTS 9 document and the associated tender documents.

The works will be carried out under the requirements of the Capital Works Management Framework.

# 2.0: Project Background:

Saint Gabriel’s Cemetery is located at Emoclew Road, Arklow, County Wicklow. The cemetery has been in continuous use since August 1870 and represents over 150 years of burial activity in Arklow.

The cemetery is an important active burial ground and historic civic place within the town. Available records indicate a significant number of recorded burials, and the cemetery contains a mix of historic and more recent plot arrangements. The site retains notable heritage features, including entrance structures, boundary treatments and a granite gate lodge associated with the historic development of the cemetery.

The cemetery is approaching capacity. Based on current burial rates and the limited number of remaining plots, it is anticipated that the existing cemetery may reach full capacity within a relatively short timeframe. Wicklow County Council therefore requires a coordinated study to assess remaining capacity, identify opportunities to maximise the existing site, and consider future cemetery provision.

There are also existing site constraints and opportunities which require assessment, including:

- limited remaining burial capacity;

- historic plot layout and cemetery character;

- existing drainage and ponding issues;

- vehicular and pedestrian access from Emoclew Road;

- internal circulation and operational requirements;

- potential for shared surfaces and reduced traffic areas;

- accessibility and visitor movement;

- parking and maintenance access;

- heritage features and cultural significance;

- biodiversity, ecology and tree constraints;

- potential enhancement of the columbarium wall area;

- potential for memorial garden, interpretation, signage and amenity improvements;

- long-term use and management of the cemetery, including when burials cease.

A detailed and coordinated multidisciplinary assessment is now required to inform decision-making and support the development of a practical, deliverable Landscape Masterplan and associated works package.

# 3.0: Project Objectives:

The objective of this commission is to:

- undertake a site analysis and mapping exercise for Saint Gabriel’s Cemetery;

- assess existing cemetery use, layout, capacity, access, circulation and constraints;

- identify options to increase or optimise burial capacity within the existing cemetery;

- prepare a feasibility assessment for future cemetery provision, including potential extension or new burial ground requirements;

- assess existing drainage and ponding issues;

- develop drainage proposals incorporating Nature Based SuDS where feasible;

- undertake ecological, arboricultural, cultural and built heritage assessments;

- assess accessibility, DMURS, internal circulation, parking and operational requirements;

- prepare a Landscape Masterplan for the cemetery;

- develop site regeneration and enhancement proposals;

- consider appropriate enhancement of the columbarium wall area, including a memorial garden or other suitable treatment;

- incorporate local heritage, biodiversity, amenity, accessibility and public realm considerations;

- prepare cost estimates, value engineering recommendations and phasing proposals;

- prepare Part 8 planning documentation and support Wicklow County Council through the statutory planning process;

- prepare tender and contract documentation for the approved works;

- support Wicklow County Council in procurement and delivery of the works;

- provide construction-stage services, snagging, certification and defects close-out support where instructed.

The overall objective is to provide Wicklow County Council with a clear, practical and deliverable plan for Saint Gabriel’s Cemetery that addresses immediate capacity, drainage and enhancement requirements while also supporting long-term cemetery management and future burial ground planning

# 4.0 Project Criteria

Project Team:

The Client for the project is the Climate, Environment, Recreation & Amenity Department, Wicklow County Council. The Project Team includes the following:

- Employer / Client: Wicklow County Council, Climate, Environment, Recreation & Amenity Department, County Buildings, Station Road, Wicklow Town.

- Consultant Stages: Design Team Consultancy Services.

- Employer’s Representative: Wicklow County Council nominated representative.

- Lead Consultant: Landscape Architect / Lead Consultant.

- Cemeteries and Burial Grounds Expert: Consultant appointed by Lead Consultant.

- Civil / Drainage Engineer: Consultant appointed by Lead Consultant.

- Heritage Consultant: Consultant appointed by Lead Consultant.

- Ecologist: Consultant appointed by Lead Consultant.

- Arboricultural Consultant: Consultant appointed by Lead Consultant.

- Accessibility / DMURS Consultant: Consultant appointed by Lead Consultant.

- Quantity Surveyor / Cost Consultant: Consultant appointed by Lead Consultant.

- Project Supervisor for the Design Process: Consultant appointed by Lead Consultant.

- A tenderer may include additional disciplines where required.

Consultant Requirements:

The Consultant shall:

- Act as Project Lead for the multidisciplinary team;

- Provide and coordinate all required specialist services;

- Deliver the commission in accordance with the Capital Works Management Framework (CWMF);

- provide all necessary reports, surveys, assessments, designs, drawings, specifications, cost estimates, Part 8 documentation and tender documentation;

- coordinate all disciplines to ensure a fully integrated output;

- support Wicklow County Council through the Part 8 statutory planning process;

- support Wicklow County Council during tendering and delivery of works, where instructed;

- ensure all outputs are suitable for Wicklow County Council’s approval, statutory planning, procurement, construction, maintenance and future cemetery management purposes.

Wicklow County Council reserves the right to engage other consultants for additional services for this project if required.

The selected Consultant will be required to maintain the levels of insurance stated in the Form of Tender and Schedule. The contract will be governed by the laws of Ireland.

The defects period for any works will be one year from Substantial Completion, unless otherwise stated in the works contract.

# 5.0: Scope of Consultancy Services:

The appointed Consultant shall deliver the commission across the following stages. Each stage shall be subject to written approval from Wicklow County Council before proceeding to the next stage.

## Stage 1 – Inception, Site Analysis, Surveys, Mapping and Feasibility Assessment

The Consultant shall undertake all surveys, inspections, reviews and assessments necessary to establish the existing condition, capacity, constraints and opportunities at Saint Gabriel’s Cemetery.

This stage shall include:

  - inception meeting with Wicklow County Council;

  - review of existing information, cemetery records, maps, drawings, reports and available historic information;

  - review of current burial capacity and recent burial trends;

  - site familiarisation and detailed site analysis;

  - mapping of existing cemetery layout, circulation, access, boundaries, entrances, landscape features, trees, drainage features, heritage features and operational constraints;

  - assessment of existing burial capacity and opportunities to maximise remaining use within the existing cemetery;

  - review of internal circulation, access, maintenance routes, parking and visitor movement;

  - assessment of existing drainage and ponding issues;

  - identification of survey requirements, including topographical, levels, drainage, ground investigation or infiltration testing as required;

  - ecological survey and identification of biodiversity constraints and opportunities;

  - arboricultural survey and identification of tree constraints, tree protection requirements and potential tree works;

  - cultural and built heritage assessment, including review of historic cemetery character, entrance structures, boundary treatments, gate lodge context and graveyard features;

  - accessibility / DMURS review, including pedestrian access, shared surfaces, reduced width routes and universal access considerations;

  - cemeteries and burial grounds expert review of operational, capacity, layout, maintenance and management issues;

  - initial stakeholder and elected member engagement requirements, to be agreed with Wicklow County Council;

- preparation of a coordinated stage 1 report.

The Stage 1 Report shall include:

  - summary of existing site conditions;

  - site analysis and mapping;

  - photographic record;

  - existing capacity assessment;

  - constraints and opportunities plan;

  - drainage issues and initial recommendations;

  - heritage, ecological and arboricultural constraints;

  - accessibility and circulation findings;

  - cemetery management and operational considerations;

  - initial options for capacity optimisation;

  - survey gaps and assumptions;

  - risk items and recommended next steps.

## Stage 2 – Landscape Masterplan, Options Appraisal, Part 8 Planning Documentation and Cost Estimates

Following approval of the Stage 1 Report, the Consultant shall prepare options and a preferred Landscape Masterplan for Saint Gabriel’s Cemetery. The Consultant shall also prepare the required Part 8 planning documentation for the preferred option.

This stage shall include:

- development of options to maximise remaining burial capacity within the existing cemetery;

- consideration of future cemetery provision, including potential extension or new burial ground requirements;

- development of options for improved internal circulation, reduced traffic areas, shared surfaces, pedestrian routes, maintenance access and parking arrangements;

- development of proposals for the columbarium wall area, including potential memorial garden, seating, planting, access, signage or other appropriate treatment;

- development of cemetery enhancement proposals having regard to heritage, biodiversity, amenity and long-term use;

- development of drainage options to address ponding and surface water issues;

- incorporation of Nature Based SuDS, including raingardens, swales, bioretention areas, attenuation features, planting and ponds where feasible;

- integration of ecological, arboricultural and heritage recommendations into the Landscape Masterplan;

- development of signage, interpretation and wayfinding proposals where required;

- preparation of landscape plans, sections, elevations, sketches, schedules and photomontages as necessary to present proposals;

- preparation of cost estimates for options and preferred proposals;

- value engineering and phasing recommendations;

- Preparation of Part 8 planning drawings and supporting documentation;

- preparation of site location maps, site layout plans, existing and proposed drawings, sections, details and visual material as required;

- preparation and coordination of drainage, ecology, arboriculture, heritage, accessibility and other specialist inputs required for the Part 8 package;

- preparation of public consultation drawings and display material as required;

- attendance at meetings, workshops or elected member briefings as required;

- support to Wicklow County Council during the Part 8 process, including review of submissions and preparation of technical responses where required;

- input to the Chief Executive’s Report for the Part 8 process, where required;

- preparation of a Stage 2 Options, Landscape Masterplan and Part 8 Report.

The Stage 2 Design Report shall include:

- summary of options considered;

- assessment of advantages, disadvantages, constraints and risks;

- preferred Landscape Masterplan;

- burial capacity recommendations;

- drainage and SuDS strategy;

- heritage, ecology and arboriculture integration;

- accessibility, circulation and parking recommendations;

- columbarium / memorial garden enhancement proposals;

- Part 8 planning package;

- cost estimates;

- value engineering recommendations;

- phasing and implementation strategy;

- recommendations for tendering the works.

Wicklow County Council shall remain responsible for the statutory Part 8 process, publication of notices, formal consultation requirements, elected member procedures and final planning decision.

## Stage 3 – Tender Documentation, Tender Support, Evaluation Support and Award Recommendation

Following completion of the Part 8 process and approval to proceed, the Consultant shall prepare the technical documentation required to allow Wicklow County Council to tender the works.

This stage shall include:

- preparation of detailed design drawings, specifications, schedules of works, performance requirements and relevant appendices;

- preparation of landscape, civil, drainage, SuDS, accessibility, heritage, ecological, arboricultural and public realm details as required;

- preparation of pre-construction information and health and safety information for inclusion in the tender documents;

- preparation of pricing documents and cost plan updates;

- advice on suitable works contract form, pricing structure and tender return requirements;

- support to Wicklow County Council during the tender process;

- preparation of responses to technical queries raised by tenderers;

- attendance at clarification meetings, if required;

- review of contractor submissions from a technical perspective;

- assessment of proposed methodology, programme, compliance with specification and technical quality;

- preparation of technical evaluation comments and clarification questions, where required;

- support to Wicklow County Council in preparing an award recommendation;

- preparation of a Tender Evaluation / Award Recommendation Report, as required.

Wicklow County Council shall remain responsible for the formal tender process, procurement decisions and contract award.

## Stage 4 – Construction Stage Services, Inspections, Certification and Contract Administration Support

Following appointment of the works contractor, the Consultant shall provide construction stage services to support delivery of the approved works.

This stage shall include:

- Attendance at pre-start meeting and site meetings as required.

- review of contractor programme, method statements, technical submissions, material proposals and shop drawings where relevant;

- site inspections at agreed intervals to monitor progress, quality and compliance with the design and specification;

- Lead Consultant inspections of landscape, public realm, cemetery enhancement and general works;

- Civil / Drainage Engineer inspections of drainage, levels, SuDS and civil works where required;

- Heritage Consultant input where works interface with heritage features;

- Ecologist input where ecological mitigation or biodiversity enhancement measures are being implemented;

- Arboricultural Consultant input where tree protection, tree works or planting works are being undertaken;

- Accessibility / DMURS Consultant input where access, shared surfaces or universal design measures are being implemented;

- Quantity Surveyor input in relation to cost control, variations, payment recommendations and final account support where required;

- PSDP input in relation to design changes and design risk matters;

- responses to contractor requests for information and design queries;

- review and agreement of design clarifications, proposed substitutions or variations, subject to Wicklow County Council approval;

- progress reporting to Wicklow County Council;

- advice on interim payment claims, where required;

- identification and reporting of defects, non-compliance, delays, risks or cost issues;

Support for contract administration, including records, instructions, minutes and certification as required under the relevant works contract

## Stage 5 – Handover, Snagging, Defects Support and Close-Out Report

At completion of the works, and where instructed by Wicklow County Council, the Consultant shall support Wicklow County Council in closing out the project and confirming that the works have been completed in accordance with the design intent and contract requirements.

This stage shall include:

- Practical completion inspection.

- Preparation of snagging list and coordination of close-out of snag items.

- Final inspections by relevant disciplines.

- Review of contractor completion documentation.

- Review of as-built drawings, operation and maintenance manuals, warranties, certificates, test records and safety file information.

- confirmation that landscape, drainage, SuDS, accessibility, heritage, biodiversity, arboricultural and civil works have been completed in accordance with the agreed design, insofar as applicable to each discipline.

- Final certification and professional statements as required.

- Review of final account information, where required.

- Preparation of a final Close-Out Report including:

  - Summary of works completed;

  - Outstanding issues, if any;

  - Certifications received;

  - Maintenance recommendations;

  - Future inspection or renewal requirements;

  - Lessons learned and recommendations for future phases or cemetery development.

# 6.0: Fixed Price Requirement:

The consultancy services shall be tendered as a fixed lump sum price, broken down by stage.

The Contract will be: COE1 – Standard Conditions of Engagement for Consultancy Services (Technical). The works contract (future stage) will be procured separately by Wicklow County Council. No additional fees shall be payable unless expressly approved in writing by Wicklow County Council.

# 7.0: Governance And Approvals:

At each key project stage, the Design and Construction Team must secure formal approval from Wicklow County Council by email before proceeding.

The key stages include the following:

- completion of Stage 1 Site Analysis, Mapping and Feasibility Report;

- approval of preferred Landscape Masterplan option;

- approval of Part 8 planning documentation;

- completion of Part 8 process;

- approval of detailed design and cost estimates;

- approval to proceed to works tender;

- approval at construction completion stage;

- approval of final close-out documentation

Failure to obtain such approval may invalidate subsequent work or expenditure.

# 8.0 Submission Requirements

Interested parties should submit:

- Completed Form of Tender & Schedule;

- Completed Suitability Assessment Questionnaire, where required

- Quality submission (as per criteria);

- Completed Fixed Price Proposal covering all stages of the project;

- Indicative delivery programme with key milestones;

- Details of Proposed Design Team, including lead consultant, key personnel, and previous relevant experience;

- example of a relevant cemetery, burial ground, heritage landscape, public realm, parkland or similar landscape master planning commission;

- proposed approach to drainage, Nature Based SuDS, biodiversity and climate resilience;

- Confirmation of tax clearance, professional indemnity, and public liability insurance.

- any other documentation required under the Instruction to Tenderers and Tender Schedule

All tender submissions must be submitted online.

# 9.0: Contract Award Criteria:

Wicklow County Council does not bind itself to accept the lowest or any tender, and no person making a submission will be remunerated for any costs incurred in the preparation of a tender submission.

The Contracting Authority reserves the right to:

- Seek clarification of any submission;

- Verify information provided;

- Reject abnormally low tenders;

- Cancel or suspend the procurement process at any stage.

The consultancy services shall be delivered under the Standard Conditions of Engagement for Consultancy Services (Technical) – COE1. The procurement and delivery of any subsequent works arising from this commission will be undertaken separately by Wicklow County Council, in accordance with the Capital Works Management Framework (CWMF) and applicable Office of Government Procurement (OGP) guidance. For more details refer to the Instruction to Tenderers and other contract documents.

Assessment Process:

The procurement process will be conducted under the Open Procedure and will comprise:

(a) Suitability Assessment Questionnaire (SAQ)

Tenderers will be required to demonstrate their:

- Financial and economic standing;

- Technical and professional capability;

- Relevant experience and competence to deliver the services.

- Tax clearance certificate,

- E.L. insurances (€13,000,000)

- P.L. insurance (€6,500,000)

- P.I. Insurance (€1,000,000

Only Tenderers who meet the minimum suitability requirements will proceed to full tender evaluation.

(b) Award Criteria – Most Economically Advantageous Tender (MEAT)

The contract will be awarded on the basis of the Most Economically Advantageous Tender (MEAT), assessed on the basis of a Quality Price Ratio of 70:30.

The Quality Criteria (700 marks) includes the following:

Quality Criteria A Project Delivery & Capability:

Sub Criteria A1 Proposed Team and Relevant Experience (120 marks)

Sub Criteria A2 Understanding of the Service Brief and Project Context (140 marks)

Sub Criteria A3 Methodology and Approach to Service Delivery (160 marks)

Sub Criteria A4 Resources, Programme and Project Management (80 marks)

Quality Criteria B Technical & Sustainability:

Sub Criteria B1 Relevant Project Example (100 marks)

Sub Criteria B2 Drainage, Nature Based SuDS, Biodiversity and Climate Resilience Approach (100 marks)

Minimum Quality Threshold

Tenderers must achieve a minimum score of 350 marks out of 700 under the quality assessment. Tenders scoring below this threshold may be excluded from further consideration and may not proceed to the price evaluation stage.

Note on Pre-Tender Site Inspection

Tenderers may request a site inspection through the tender query process. However, it is acknowledged that not all Tenderers may undertake a pre-tender site inspection. Tenderers will not be disadvantaged where a site inspection has not been undertaken.

Quality assessment will focus on the Tenderer’s professional understanding of the brief, relevant experience, proposed methodology, assumptions, risk management approach and ability to validate existing site conditions during the initial survey, mapping and feasibility stages of the commission.

Suggested Anticipated Contract Period

The anticipated contract period is approximately 12 months from appointment, including site analysis, feasibility assessment, Landscape Masterplan preparation, Part 8 planning support, tender documentation and construction-stage services, subject to project approval and instruction.

Suggested Discipline / Time Input Schedule

| Discipline / Role | Indicative Hours |
| --- | --- |
| Project Landscape Architect / Lead Consultant, including stakeholder consultation, Part 8 coordination, tender documentation and tender support | 165 |
| Cemeteries and Burial Grounds Expert | 40 |
| Project Civil / Drainage Engineer, including drainage assessment and topographical / measured survey coordination | 80 |
| Heritage Consultant | 35 |
| Ecologist | 30 |
| Arboricultural Consultant | 25 |
| Quantity Surveyor / Cost Consultant | 30 |
| Accessibility / DMURS Consultant | 25 |
| Project Supervisor for the Design Process | 25 |
| Total Indicative Input | 455 |

Note: Tenderers shall provide a breakdown of the proposed time input for each discipline and key team member. The above indicative discipline breakdown is provided for tender assessment purposes only. Tenderers may propose alternative allocations where they consider this appropriate, provided the overall approach demonstrates sufficient resources to deliver the full scope of services.

Note: For the purposes of the above indicative allocation, stakeholder consultation, workshop preparation, Part 8 planning coordination, reporting, contract documentation and tender support are deemed to be included within the Project Landscape Architect / Lead Consultant allocation. Topographical / measured survey coordination is deemed to be included within the Project Civil / Drainage Engineer allocation. Construction-stage and defects support shall be distributed across the relevant disciplines as required, having regard to the nature of the works progressed.