Single-Party Framework Agreement

For

The Provision of Interpretive Design Consultancy Services to Trinity College Dublin

SCHOOL OF COMPUTER SCIENCE AND STATISTICS - TRINITY COLLEGE DUBLIN

Ref: TCD-26-C2400

Pricing Schedules

Contents

A1. Scope for this Tender	3

A4. Roles and day rates (variations only)	4

A5. What is included in the ﬁxed fees	5

A6. Visualisation requirements (included)	5

A7. Minimum charges and disbursements	5

A8. Acceptance and KPIs	5

A9. Change control	6

1. Scope and outputs	7

2. Programme	7

3. Price and payment	7

4. Dependencies and exclusions	8

5. Acceptance, KPIs, contacts	8

## A1. Scope for this Tender

Supplier to provide interpretive design, graphic design, content research, scriptwriting and supervision to deliver a tender-ready production package; and then supervise the production and fabrication. Production and fabrication are excluded and will be procured separately by SCSS. Pricing should be the budget range €60,000.

A2. Evaluated Tender Price (ETP) Calculation

ETP = [0.80 × Stage-fee basket] + [0.20 × Day-rate basket].

Stage-fee basket = (Small × 10%) + (Medium × 60%) + (Large × 30%). See A3 below.

Day-rate basket = Blended day rate × 40 days. See A4 below. [Using the example numbers given in sections A3 and A4 below: ETP = 36,000 + 5,600 = €41,600]

The lowest ETP will receive the full price score. Other tenders will be scored proportionally:

Price score = (Lowest ETP ÷ Tenderer’s ETP) × [3,000 price points].

A3. Design stages and ﬁxed fees

##### Package size definitions

Interpretive & graphic design, content research and scriptwriting for:

- Small: A single room (equivalent to 6 print panels, 1 conservation-grade case inc. 3 case labels, one AV screen layout and one interactive screen layout)

- Medium: One floor (equivalent to narrative framework and content, 24 print panels, 3 conservation-grade cases inc. 9 case labels, and 3 interactive screen layouts, matching web content – see Appendix 1’s scope of work for more details)

- Large: Atrium or multi-zone package above Medium

- Stage fees for sample packages

(example below; bidder to replace blue with own amounts):

| Package size | Concept Design | Detail Design | Technical Design | Tender & Supervision | All-stages total | Package Weighting | Weighted subtotal |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Small | €2,500 | €3,500 | €4,000 | €2,000 | €12,000 | 10% | €1,200 |
| Medium | €7,500 | €10,000 | €12,000 | €6,000 | €35,500 | 60% | €21,300 |
| Large | €15,000 | €20,000 | €24,000 | €16,000 | €75,000 | 30% | €22,500 |
| Stage fee basket total |  |  |  |  |  |  | €45,000 |
| Weighting |  |  |  |  |  |  | 80% |
| Weighted stage fee basket total |  |  |  |  |  |  | €36,000 |

Notes

- Tender & Supervision covers up to 6 site visits (Small), 10 (Medium), 14 (Large). Extra visits use day rates.

- Still visualisations included per A6.

## A4. Roles and day rates (variations only)

The below rates will be used only for instructed extras outside the fixed scopes. Each call-off sets maximum hours per role as a hard cap.

Indexation: annual uplift of 3% or the Harmonised Index of Consumer Prices inflation rate, whichever is lower.

Example below; bidder to replace blue text with own Euro amounts.

| Role | Day rate (€, 8h day, ex VAT) | Weighting | Weighted Pricing |
| --- | --- | --- | --- |
| Design Director/Interpretive Master planner | €900 | 25% | 225 |
| Lead Exhibit/3D Designer | €700 | 25% | 175 |
| Graphic / Information Designer | €600 | 20% | 120 |
| Scriptwriter | €600 | 10% | 60 |
| Visualisation Artist | €650 | 10% | 60 |
| Project Manager | €650 | 10% | 60 |
| Blended Day Rate (sum of weighted pricings) |  |  | €700 |
| Number of Days* |  |  | 40 |
| Day-rate basket Total |  |  | €28,000 |
| Weighting |  |  | 20% |
| Weighted day-rate basket total |  |  | €5,600 |

* the number of days allowance is not a commitment; it is only for evaluation.

## A5. What is included in the ﬁxed fees

Workshops and reviews, content outline and copy edits, all drawings/elevations/case specs, graphics to pre-press artwork (alternatively – graphic style guide with template examples for print and digital; final art working to be done by production & fitout contractor), tender documents for production (scope, schedules, finishes, mounting, lighting notes, BoQ), supervision (submittal checks, sample approvals, site meetings, snag list, sign-off), coordination with SCSS/Estates/fabricator, brand alignment, accessibility notes (Web Content Accessibility Guidelines–AA) for digital files.

## A6. Visualisation requirements (included)

- Small: Concept Design – 2 mood boards + 1 annotated plan;

Detail Design – 2 annotated elevations; Technical Design – 2 final visuals.

- Medium: Concept Design – 3 mood boards + 1 annotated plan;

Detail Design – 2 plans + 3 elevations; Technical Design – 4 final visuals.

- Large: Concept Design – 4 mood boards + 1 plan;

Detail Design – 2 plans + 4 elevations; Technical Design – 6 final visuals.

- Extra visuals: €400 per additional still, or via day rate.

## A7. Minimum charges and disbursements

Minimum call-off value €5,000.

Except where expressly pre-approved in writing by the Client, the Supplier’s fees are fully inclusive of routine disbursements e.g. local meetings, standard prints/PDFs, routine deliveries, usual software, phone, etc. Approved disbursements (limited to third-party image licences, colour-accurate press proofs) will be reimbursed at actual receipted cost with no administrative surcharge or mark-up.

## A8. Acceptance and KPIs

Milestone dates per Call-Off are binding. Variances require prior written approval.

Technical Design shall be tender-ready with zero critical non-conformances as defined: items that would prevent tendering, ordering, fabrication, installation, or safe operation.

During Tender & Supervision, the Supplier shall respond to RFIs, submittals and sample requests within 3 business days

## A9. Change control

Changes must be instructed in writing.

No retrospective billing. Before the Supplier starts extra work, the cost will be agreed in advance either:

- using the published day rates with a cap on hours, or

- as a small, fixed fee for that specific add-on.

No change to unit rates during the framework term. The Supplier’s rates submitted at the start – stage fees and day rates, subject only to the stated indexation rule – cannot be renegotiated in the middle of the framework. A change may add quantity or scope, but the price per unit stays the same.

Call-OI Order Sample

Framework: SCSS Chronology Project Interpretive Design Framework

##### Call-Off no.: 01

Title: Phase 1 – Interactive Timeline + Corridor Panels

Supplier: [Insert]

Date: [Insert]

## 1. Scope and outputs

Zones: ORI atrium wall; ORI corridor.

Elements: Narrative framework and content; 24 corridor panels; 3 object cases and label sets; ~6 x interactive timeline screens; web content

Stages required:

IRJConcept Design IRJDetail Design IRJTechnical Design IRJTender & Supervision Package size: oSmall IRJMedium o Large

Stage outputs:

Concept Design: narrative, mood boards, concept layouts, 1 plan, outline schedule. Detail Design: scaled plans/elevations, key details, outline specs, draft copy deck. Technical Design: full technical set, graphics to pre-press, tender scope & BoQ. Tender & Supervision: tender clarifications, submittal review, 10 site visits, snag-clear, handover.

Visualisations included per A6. Extra visuals: 2 additional stills at [€	] each.

## 2. Programme

Start: 1st September 4th 2026

Concept Design approval: 10th October 2026

Detail Design approval: 19th December 2026

Technical Design issued for tender: January / February 2027

Install & Supervision complete and handover: 1st November 2027

Design reviews: fortnightly; content reviews at Detail Design and Technical Design.

## 3. Price and payment

Fixed stage fees (Medium package):

Concept Design [€	] + Detail Design [€	] + Technical Design [€	] + TS [€	] =

[€	]

Extras: 2 x additional visuals @ [€	] = [€	]

##### Subtotal (ex VAT): [€	]

Minimum call-off: not applicable (exceeds €5,000).

Variations cap by role (only if instructed):

Design Director [€	] x max 6 h; Lead Exhibit/3D [€	] x max 24 h; PM [€	] x max 12 h.

These are caps, not pre-authorised hours.

Payment Milestones

M1 Concept approved: [€	] (25%) M2 DD approved: [€	] (30%)

M3 TD issued for tender: [€	] (30%)

M4 TS complete and handover: [€	] (15%)

## 4. Dependencies and exclusions

Client to provide brand assets, floor plans, conservation policy and image permissions by 28 Oct 2025.

Production procurement, AV hardware and case fabrication are excluded.

## 5. Acceptance, KPIs, contacts

Acceptance on delivery of stage outputs and closed issue log. KPI response times for supervision RFIs ≤ 3 business days.

Client PM: [Name, email]. Supplier PM: [Name, email].

Signed for Client: 	 Date:

Signed for Supplier: 	 Date: