Contract Data (part one)

The Client’s Contract Data

The Client is

| Name | Loughs Agency |
| --- | --- |
| Address for communications | 22 Victoria Road Derry~Londonderry BT47 2AB |

| Address for electronic communications | tricia@evolveproc.co.uk |
| --- | --- |

| The works are | Culdaff Fisheries Improvement Project (CfT2026/109) |
| --- | --- |

| The site is | Culdaff River - 55°14'49.2"N 7°09'49.9"W to 55°15'08.5"N 7°10'26.3"W |
| --- | --- |

| The starting date is | No earlier than Monday, 3rd August 2026 |
| --- | --- |

| The completion date is | Instream Works to be completed by 30th September 2026 Riparian Works to be completed by 30th November 2026. |
| --- | --- |

| The delay damages are | £100 | per day |
| --- | --- | --- |

| The period for reply is | one | weeks |
| --- | --- | --- |

| The defects date is | 52 Weeks | weeks after Completion |
| --- | --- | --- |

| The defect correction period is | Four | weeks |
| --- | --- | --- |

| The assessment day is the | n/a – lump sum payment on certification of satisfactory completion of each phase of the works | of each month |
| --- | --- | --- |

| The retention is | n/a – as above | % |
| --- | --- | --- |

The Construction Contracts (Northern Ireland) Ordef does/does not apply?

(delete as applicable)

The Adjudicator is

| Name | To be nominated by the CIArb |
| --- | --- |

| Address for communications | To be advised to the Consultant should the nomination of an adjudicator be required. |
| --- | --- |

| Address for electronic communications | As above |
| --- | --- |

Contract Data

The Client’s Contract Data

| The interest rate on late payment is | 0.25% | % per complete week of delay. |
| --- | --- | --- |

Insert a rate only if a rate less than 0.5% per week of delay has been agreed.

| For any one event, the liability |  |
| --- | --- |
| of the Contractor to the Client |  |
| for loss of or damage to the |  |
| Client’s property is limited to | - the level of Public Liability insurance required under this contract |

| The Client provides this insurance | No insurance will be provided by the client |
| --- | --- |

Only enter details here if the Client is to provide insurance.

| The minimum amount of | Refer to clause Z1 for insurance cover to be provided by the Contractor |
| --- | --- |
| cover for the third insurance |  |
| stated in the Insurance Table is, |  |
| for any one event |  |

| The minimum amount of |  |
| --- | --- |
| cover for the fourth insurance |  |
| stated in the Insurance Table |  |
| is, for any one event |  |

| The Adjudicator nominating |  |
| --- | --- |
| body is | CIArb |

| The tribunal is | Courts of Ireland |
| --- | --- |

| If the tribunal is arbitration, the |  |
| --- | --- |
| arbitration procedure is |  |

The conditions of contract are the NEC4 Engineering and Construction Short Contract June 2017 (as amended) and the following additional conditions

Only enter details here if additional conditions are required.

Z1: Insurance Requirements The insurances which the Contractor is required to provide under clause 83 shall have the following minimum amounts of cover for any one event: Employer’s Liability Insurance - £10 million (€13 million) per incident Public Liability Insurance - £5 million (€6.5 million) per incident and unlimited in any one period of insurance Contractor’s All Risks (CAR) Insurance – full reinstatement value of the works, plant and materials. Z2: Archaeological / Ecological Discoveries Archaeological remains or protected ecological features are discovered during the Works, the Contractor shall immediately notify the Project Manager and cease all work in the affected area until instructed to proceed. Z3: Extended Defects Correction Period Notwithstanding the Defects Correction Period stated in the Contract Data, if a Defect relates to in-river works, bank reinstatement or any element of the works subject to environmental or statutory restrictions (including but not limited to ecological timing constraints, flood risk or license conditions), the Project Manager may, at their discretion, extend the period for correction of that Defect. Any such extension shall take into account: - The need to comply with relevant environmental legislation or licenses (e.g. in-stream working restrictions); - Availability of safe and lawful access to the affected location; and - Any consultation required with statutory bodies. The Contractor shall propose a revised date for correction of the Defect and a method statement if requested by the Project Manager. Z4: Two Stage Payment Two payments will be made to the Contractor as follows: - following certification of completion of all Instream Works by 30 September 2026 - following certification of completion of all Riparian Works by 30 November 2026. No interim payments will be made.

Contract Data (part two)

The Contractor’s Contract Data

The Contractor is

| Name |  |
| --- | --- |
| Address for communications |  |

| Address for electronic communications |  |
| --- | --- |

| The fee percentage is |  | % |
| --- | --- | --- |

The people rates are

| category of person | unit | rate |
| --- | --- | --- |

| The published list of Equipment is |  |
| --- | --- |

| The percentage for adjustment for Equipment is |  | % (state plus |
| --- | --- | --- |
|  |  | or minus) |

The Contractor’s Offer and Client’s Acceptance

The Contractor offers to Provide the Works in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.

| The offered total of the Prices is |  |
| --- | --- |

Enter the total of the Prices from the Price List.

Signed on behalf of the Contractor

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

The Client accepts the Contractor’s Offer to Provide the Works

Signed on behalf of the Client

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

Price List

Entries in the first four columns in this Price List are made either by the Client or the tenderer. If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank. If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

| ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | PRICE |
| --- | --- | --- | --- | --- | --- |

| The total of the Prices |  |
| --- | --- |

The method and rules used to compile the Price List are

Scope

The Scope should be a complete and precise statement of the Client’s requirements. If it is incomplete or imprecise there is a risk that the Contractor will interpret it differently from the Client’s intention. Information provided by the Contractor should be listed in the Scope only if the Client is satisfied that it is required, is part of a complete statement of the Client’s requirements and is consistent with the other parts of the Scope.

1 Description of the works

Give a detailed description of what the Contractor is required to do and of any work the Contractor is to design.

See ‘CfT2026-109 Fisheries Improvement Project Culdaff_001 – Scope of Works’

2 Drawings

List the drawings that apply to the contract.

| DRAWING NUMBER | REVISION | TITLE |
| --- | --- | --- |
| n/a |  |  |

Scope

3 Specifications

List the specifications which apply to the contract.

| TITLE | DATE OR REVISION | TICK IF PUBLICLY AVAILABLE |
| --- | --- | --- |
| Refer to See ‘CfT2026-109 Fisheries Improvement Project Culdaff_001 – Scope of Works’ |  |  |

4 Constraints on how the Contractor Provides the Works

State any constraints on the sequence and timing of work and on the methods and conduct of work including the requirements for any work by the Client.

Specific Requirements for Contract Delivery - All Instream Works must be completed by 30 September 2026 (it is the appointed contractor's responsibility to ensure that its work schedule can accommodate this deadline). - All Riparian Works must be completed by 30 November 2026 (it is the appointed contractor's responsibility to ensure that its work schedule can accommodate this deadline). - Pre- and post-works, the appointed contractor will attend site walkovers and meetings with Loughs Agency staff and landowners. - Only tracked machines must be used within work area to avoid unnecessary disturbance to farmland. - Machinery mats must be used in areas particularly likely to be affected by transit of plant machinery. - If plant machinery must enter river to carry out work, then this MUST be done at a period of low flow. - Plant machinery and personnel must use single track close to fence line to protect integrity of farmland. - All access points and routes used for machinery will be agreed with relevant landowner and member of the Loughs Agency before commencing work on that section. - A dedicated refuelling area for machinery, with appropriate sumps and bunding to contain any spills, must be set up and located at least 50m away from the watercourse. - A wash area for machinery and personnel – using Virkon disinfectant, or equivalent - must be set up to avoid transmission of invasive species. Environmental Requirements The Contractor shall comply with all environmental requirements described in the Scope, including site-specific restrictions arising from the Natura Impact Statement and fisheries protections. Access to Private Land he Contractor shall not access private lands outside the designated working areas without prior written approval from the Client and the relevant landowners.

Scope

5 Requirements for the programme

State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated. State what the use of the works is intended to be at their Completion as defined in clause 11.2(1).

The Contractor shall carry out the Works in accordance with the programme submitted with its tender, as updated from time to time to reflect progress and any changes to the Works. The Contractor shall submit a revised programme to the Project Manager whenever reasonably requested. Any revised programme shall demonstrate completion of all Instream Works by 30 September 2026 and all Riparian Works by 30 November 2026.

6 Services and other things provided by the Client

Describe what the Client will provide, such as services (including water and electricity) and ‘‘free issue’’ Plant and Materials and equipment.

| ITEM | DATE BY WHICH IT WILL BE PROVIDED |
| --- | --- |
| Solar Powered Pumps (10 no.) | Prior to installation |
| Drinking Water Troughs (10 no.) | Prior to installation. |

Site Information

Give information about the site such as the ground conditions and any other information which is likely to affect the Contractor’s work such as the position of adjacent structures.