MONAGHAN COUNTY COUNCIL

COMHAIRLE CONTAE MHUINEACHAN

Briefing Document

for

Consultancy Services

For

The Provision of

The L14105 (Old Cross Square) to N2 (Annahagh Roundabout) to N12 (Knockaconny)

Link Road

Design, Environmental Evaluation and Statutory Processes.

June 2026

Preface

The information provided in this Tender Brief, in addition to the associated Appendices, is offered in good faith for the guidance of parties interested in tendering (hereafter referred to as the “Design Team”), but no warranty or representation is given as to the accuracy or completeness. Monaghan County Council (hereafter referred to as the “Contracting Authority”) and its advisers, servants and/or agents shall be under no liability for any error, misstatement or omission.

All costs incurred by the Design Team submitting a tender must be borne by the Design Team. The Contracting Authority accepts no liability for these costs, irrespective of the outcome of the procurement process or if the procurement process is postponed or cancelled.

None of the information in this document shall, pending formal execution of a contract, constitute a contract or part of a contract between the Contracting Authority and any Design Team. The Client shall not be obliged to enter into a contract with any Design Team. No legal relationship or other obligation shall arise between any Design Team and the Contracting Authority unless and until a contract has been formally executed in writing by the Contracting Authority and the final successful party and any conditions precedent to the effectiveness of contract documents have been fulfilled.

The Contracting Authority reserves the right to amend this Tender Briefing Document, its requirements and any information contained herein at any time by notice, in writing, to the Applicants. Nothing in this Tender Brief is, nor shall be relied upon as, a promise or representation as to the Contracting Authority’s ultimate decision in relation to the pre-qualification of Applicants. However, the Contracting Authority reserves the right to take such steps as it considers appropriate, including (but not limited to):

- changing the basis of, or the procedures (including the timetable) relating to, the pre-qualification process;

- rejecting any or all of the applications;

- not inviting an Applicant to proceed further; or

- abandoning the pre-qualification process.

Applicants must treat this Tender Briefing Document, their submissions, and their participation in this pre-qualification process as confidential. Applicants must not disclose any information about this pre-qualification process to anyone other than those who have a legitimate need to know or whom they need to consult for the purpose of making a submission, and then only on a confidential basis or as required by law. Applicants shall promptly return this Tender Brief to the Contracting Authority upon request.

The Contracting Authority is entitled to disclose to any person any information about this pre-qualification process, including the identity of the Applicants and details of their respective members, the Services, at any time. If an Applicant considers that information it supplies is commercially sensitive or confidential, this should be clearly stated, and clear and substantive reasons should be given. Representations regarding confidentiality or commercial sensitivity should give a time after which the information may be disclosed; this would not normally exceed 5 years. The Contracting Authority will have regard to such a statement in considering a request for access to the information under the Freedom of Information Act 2014 but is not bound by the Applicant’s view.

It will be a condition of the contract award that the Tenderer must comply with all applicable terms of the Department of Finance Circular 43/20061: Tax Clearance Procedures: Public Sector Contracts or any replacement. Applicants may obtain information regarding their obligations concerning taxation from the Revenue Commissioners (www.revenue.ie).

Regarding General Data Protection Regulation(s), Applicants should note that the standard Conditions of Engagement that will be used have a data protection clause.

References to this Tender Brief include all information contained in this Tender Briefing Document, accompanying documentation, and any information and/or opinions made available during the pre-qualification process by or on behalf of the Contracting Authority, its advisers, consultants, contractors, servants and/or agents in connection with this Tender Brief or the Services including, without limitation, information made available in response to any queries. Irish law applies to this Tender Briefing Document. The Irish courts shall have exclusive jurisdiction in relation to any disputes arising from this Tender Briefing Document. Each Applicant’s acceptance of delivery of this Tender Brief constitutes its agreement to and acceptance of the terms set forth in the Preface.

The Contracting Authority reserves the right to increase or decrease the scope of the works depending upon the funding made available for the project.

Contents

1.	Introduction	1

2.	Scope of Service	1

2.1	Design, Environmental Evaluation and Statutory Processes requirements	2

3.	Indicative Consultant  Procurement Timetable	5

4.	Design, Environmental Evaluation and Statutory Processes Delivery Programme	5

5.	Pricing	6

6.	Tender Assessment Criteria	6

6.1 Stage 1 - Suitability Assessment	6

6.2 Stage 2 – Award Criteria	6

6.2.1 Price	6

6.2.2 Quality	6

7.	Award of Contract	8

8.	Documents Accompanying this Project Brief	9

9.	General Instructions to Applicants	9

9.1 Submission via eTenders (www.eTenders.gov.ie)	9

9.2 Submission Format, Contents and Details	9

9.3 Non-Compliant Submissions	10

9.3 Required Tender Submissions	10

9.4 Insurance Requirements	10

9.5 Tax Clearance	10

# Introduction

Monaghan County Council, the “Contracting Authority”, completed a Feasibility study and options report, to explore the construction of a link road between the L14105 (Old Cross Square) and the N2 (Annahagh Roundabout) and a SAR Report to explore a link road between N2 (Annahagh Roundabout) and the N12 (Knockaconny).

Link Road from Old Cross Square roundabout in Monaghan Town to the Annahagh Roundabout on the N2 Road circa 1.3km and to the N12 at Knockaconny, circa 1.2km.

The Contracting Authority now wishes to develop the design based on both technical and environmental inputs, to a stage where sufficient levels of detail exist to establish land take requirements and to progress the Project through the statutory processes for the complete project, from Old Cross Square to the N12 at Knockaconny (2.5km), Figure 1.1 below.

The Feasibility Study report and Options report and the SAR Report are included in the Information Pack of the tender documents. These stages must be undertaken in the format as outlined in the TII Publications Project Management Guidelines PE-PMG-02041 May 2025.

Figure 1.1 - Project Extents, Old Cross Square to Knockaconny (N12)

# Scope of Service

Monaghan County Council is seeking suitably qualified and experienced multidisciplinary engineering consultants to carry out the Design, Environmental Evaluation and Statutory Processes on a possible link road between the Old Cross Square roundabout in Monaghan Town via the Annahagh Roundabout on the N2 Road to the N12 at Knockaconny, circa 2.5km.

The link road must include provision for:

- Completion of a high-quality design vehicle carriageway between Old Cross Sq. and N12,

- Active Travel infrastructure,

- Provision of services including water, foul drainage, stormwater, ESB and telecommunications along the entire route,

- Incorporating the planned developments, as shown in Figure 2.1 and Map MDP1 in Appendix A, and access to all other lands for development along the route.

- Linkage to the existing Ulster Canal Greenway,

- A planned Transport Hub to include park and ride facilities, bus set down areas, cycle parking facilities and any other facility that will improve the user experience of the transport hub.

- Other details as per the Feasibility Study and Options Selection Report and SAR Report.

Figure 2.1 – Feasibility study and options report area extent

## Design, Environmental Evaluation and Statutory Processes Requirements

The Option Selection, Design, Environmental Evaluation and Statutory Processes will follow the format of the TII Publications Project Management Guidelines PE-PMG-02041 May 2025.

- Phase 2 Options Selection (N2 to N12 Section only)

- Phase 3 Design and Environmental Evaluation

- Phase 4 Statutory Processes

The required services will include the following:

- Review of Existing relevant planning policy and other policy considerations relating to the proposal.

The process is expected to review the following existing documents at a minimum:

- The Old Cross Square to Annahagh Roundabout Link Road, Feasibility Study and Options Report.

- Transport Access to the North-East of Monaghan Town (TANEMT), Strategic Assessment Report, June 2023.

- Monaghan Land Use and Transportation Study

- Monaghan County Development Plan 2025-2031.

- Monaghan Town Local Transport Plan – September 2025

- National Climate Action Plan

- Smarter Travel

- National Cycling Policy Framework

- Monaghan County Council Walking and Cycling Strategy 2021 – 2026

- Transport Appraisal Framework (TAF).

- Department of Transport Appraisal Guidelines

The delivery of services under this commission shall also ensure full compliance with the Infrastructure Guidelines (IG) and the Transport Appraisal Framework (TAF). Therefore, the delivery of services will align with the Department of Transport Appraisal Guidelines

The Consultants Team will be expected to have an existing in-depth knowledge and understanding of the Infrastructure Guidelines, Public Spending Code, National Planning Framework, the National Development Plan, Project Ireland 2040 and Planning and Development Guidelines.

- Consultations

The consultant is expected to liaise with, at a minimum, the following organisations:

- Monaghan County Council's internal departments

- Department of Transport (DOT),

- Transport Infrastructure Ireland (TII)

- National Parks and Wildlife Service (NPWS),

- Office of Public Works (OPW),

- Inland Fisheries,

- Waterways Ireland,

- Irish Water,

- Landowners

- All relevant utility providers

- Site Visits

The Consultants Team will be expected to carry out sufficient site visits to view and assess the area and its surroundings to complete the full stages requirements for the route option identified in the Feasibility Study and Options Report.

- Project Phase Summary Requirements

The Consultants Team will be expected to:

Phase 2 Option Selection (N2 to N12 Section)

Examination of alternative options to determine a Preferred Option.

Processes

- Option Selection Process

- Road Safety Impact Assessment - PE-PMG 02001 (if required)

- Option Selection Report

- Road Safety Impact Assessment - PE-PMG 02001 (if required)

- PSDP Duties

- Road Safety Audit Stage F, Parts 1 and 2 (if required)

- Option Selection Peer Review (if required)

- Public Consultations

- Cost Management

- PAG Requirements

- Evaluation of Environmental Constraints

Deliverables

- Option Selection Report

- Road Safety Impact Assessment - PE-PMG 02001 (if required)

- Cost Management Deliverables

- Project Appraisal Deliverables (Refer to PAG)

- Road Safety Audit Stage F (Parts 1 and 2) (if required)

Phase 3 Design and Environmental Evaluation

Develop the Project design, following the selection of a Preferred Option, based on both technical and environmental inputs, to a stage where sufficient levels of detail exist to establish land take requirements and to progress the Project through the statutory processes.

Processes

- Update to Project Execution Plan (PEP).

- Consultation with land and property owners.

- Statutory processes and required environmental reporting requirements.

- Preparation of Design Project.

- Commissioning of surveys.

- Determine requirements for licences, consents, and permits.

- Cost, Risk, and Value Management.

- Road Safety Risk Report.

- Environmental Evaluation documentation.

- Design Report.

- Schedule of Environmental Commitments.

- Preparation of Construction Environmental Management Plan.

- Determination of Land Acquisition requirements.

- Preparation of Land Acquisition documentation.

- Engagement of Property Valuation Advisors and Legal Advisors.

- Preparation of Project Appraisal documentation.

Deliverables

- Updated Project Execution Plan.

- Design Report.

- Signed Design Report Peer Review Report.

- Cost Management Manual deliverables.

- Project Appraisal Report/Preliminary Business Case.

- Environmental Deliverables.

- Land Acquisition Documentation.

- Statutory process documentation as applicable.

Phase 4 Statutory Processes

Compile documentation and participate in oral hearing(s) as required by the statutory processes to ensure that the proposed Project is developed in accordance with planning and environmental legislation.

Processes

- Update to Project Execution Plan (PEP).

- Preparation Briefs of Evidence for Oral Hearing, (if required).

- Project Oral Hearing. Requests for Further Information, Amendments and Further Public Presentation (if required).

- Schedule of Environmental Commitments.

- Cost, Risk and Value Management.

- Project Appraisal documentation.

- Lessons Learned workshop.

Deliverables

- Updated Project Execution Plan (PEP).

- Cost Management Manual Deliverables, including reviewed Minor Project Estimate (Target Cost 1).

- Updated Project Appraisal Report.

Notes:

Lidar point cloud topo data will be provided by Monaghan CC of the study area.

The consultant must allow in their tendered lump sum for process the lidar raw data to generate an existing ground model so that it can be used in the modelling of the preferred route.

OSI vector mapping will be provided by Monaghan County Council.

- Meetings/Workshops

The Consultants Team will be expected to meet regularly with the Client to review progress. At a minimum, this will include:

- Initial project brief meeting

- By-weekly updates

- Interim meeting

- Final project meeting

The meetings are to be chaired by the consultant’s team leader, minuted by the consultant's team, and forwarded to the client for approval within two days of the meeting. An agenda is to be forwarded with the approved previous meeting minutes two days before the scheduled meeting.  The consultant shall also allow for three workshop meetings to review the Design Report to facilitate recommendations/alterations by the Client or stakeholders.

The Consultants Team shall make the Client aware as soon as possible of any delays or risks to the project programme.

- Reports

The Client shall be presented with a Draft Design for review and approval. The Final Design in accordance with the TII Publications Project Management Guidelines PE-PMG-02041 May 2025 shall be provided once the draft review is completed and approved by the Client. Two hard copies and a soft copy are required.

- Health and Safety

The consultant will be responsible for the Health and Safety of all its personnel and will have to undertake all necessary Risk Assessments and implement any required mitigation measures prior to undertaking the service requirement.

- Required Project Outputs

The consultant must include for the following project output in their fixed tendered lump sum price:

- Provision of a complete Design, Environmental Evaluation and Statutory Processes in accordance with the TII Publications Project Management Guidelines PE-PMG-02041 May 2025 and Project Manager’s Manual for National Road Projects PE-PMG-02042 May 2025.

The purpose of Phase 4 is to compile documentation and participate in the planning process, including oral hearing(s) as required by the statutory processes to ensure that the proposed Project is developed in accordance with planning, environmental and other relevant legislation.

- Delivery Milestones

The consultant team are to allow for achieving the following milestones in their tendered fixed price lump sum:

Phase 2 Option Selection

Phase 3 Design and Environmental Evaluation

Phase 4 Statutory Process

- Initial week after appointment:

The Consultants Team shall hold a briefing meeting to discuss the project, introduce staff, and outline their programme and the delivery of the service.

- 4 weeks after the appointment:

Consultants Team to have completed reviews of existing documents and necessary consultations, including completion of the first workshop. Hold Interim progress Meeting.

- 28 weeks after the appointment:

Completion of the Option Selection Report for N2 to N12 Section.

- 60 weeks after the appointment:

Draft Issue of Design, Environmental Deliverables and completion of the second workshop.

- 64 weeks after the appointment:

Land Acquisition Documentation.

- 80 weeks after appointment:

Final Issue of the Final Design and Statutory process documentation.

- 90 weeks Complete Statutory Process and Project close meeting.

# Indicative Consultant Procurement Timetable

The table below outlines the indicative procurement timetable. The timelines may change due to the process itself or for any other reason as determined by the Contracting Authority.

| Item | Activity | Proposed Dates |
| --- | --- | --- |
| 1 | Latest date for queries | 7 days prior to the closing date |
| 2 | Closing date for submissions | As per e-tenders |
| 3 | Notification of Successful/Unsuccessful | Q3 2026 |

# Final Design and Statutory Process Documentation Delivery Programme

The Design Report and Statutory Process documentation must be delivered to Monaghan CC no later than the timeline as outlined above. The Design documents and Statutory Process documents should be in accordance with the TII Publications Project Management Guidelines PE-PMG-02041 May 2025.

# Pricing

All prices quoted must be expressed in Euro only and Exclusive of VAT.

The Consultants Team Price shall include for all meetings, workshops and project correspondence as well as site visits and associated travel.

Consultants Teams must confirm that all prices quoted in the tender will remain valid for six months (180 days).

# Tender Assessment Criteria

All submitted tenders will be assessed in a two-stage process.

## 6.1 Stage 1 - Suitability Assessment

For any consultant team to be considered for this competition, they must first pass the Suitability Assessment. Please refer to the instructions for tenders (ITT) in folder 002 for further details. The Suitability Assessment Questionnaire that will be used to assess the eligibility of the consultant team is found in folder 004 of the tender documents.

The questionnaire is a pass/fail document, and should any submission fail on any of the Suitability Assessment criteria, that consultant team submission will not be considered further.

Tenderers will be assessed to determine which is the most economically advantageous tender in accordance with the Award Criteria set out in the ITT and the FTS.

## 6.2 Stage 2 – Award Criteria

Only the submitted tenders that pass the Stage 1 suitability assessment will be assessed at Stage 2.

The award criteria is the most economically advantageous tender based on Quality (40%) and Price (60%). A maximum of 1000 marks is available (Quality 400 marks: Price 600 marks).

Please refer to the ITT for further information on the award criteria and assessment methodology.

### 6.2.1 Price

600 Marks Available from a maximum of 1000.

Marks will be awarded as follows:

Please refer to the ITT for further information on the award criteria and assessment methodology.

### 6.2.2 Quality

400 Marks Available from a maximum of 1000.

The consultant is required to submit their Quality Submission addressing the following Criteria.

Please refer to the ITT for further information on the award criteria and assessment methodology.

| Criterion | Description | Marks Available |
| --- | --- | --- |
| A | Project Resources Committed With regard to the level of services required to deliver this commission, tenderers should provide an Organogram outlining the full design team proposed to be committed to the project. With reference to the proposed organogram, tenderers should provide a written submission of no more than two pages explaining the advantage to the Contracting Authority of the Tenderer’s Proposed Team and Resourcing Plan. Tenderers should include a brief synopsis of each key staff member’s experience, qualifications and any specific experience with particular reference to the delivery projects of a similar scale and nature. CVs (2 pages maximum) must be included for each design team member, which provides evidence of the experience outlined in the brief synopsis. Maximum submission, 4 A4 pages (excluding CV’s) | 100 |
| B | Project Programme Tenderers are to provide a Project Programme (in the form of a Gantt Chart or equivalent) for the delivery of the full scope of required services and work for each stage/phase of the project. The Project Programme should include key tasks, key project milestones, dependent tasks and the critical path for ensuring the successful delivery of the required services within the required project timeframes. | 50 |
| C | Responsibility Assignment Matrix. Tenderers are to provide a Responsibility Assignment Matrix (RAM) for the project. The RAM shall indicate the amount of each team member’s time (in person-hours) that shall be allocated to the project per task (as outlined in the Project Programme (Criterion B) and the total number of hours on the project. Tenderers are advised that a sufficient breadth of expertise and an appropriate time allocation (person-hours) must be proposed for each category/grade of staff and relevant service tasks, taking into account the scope, nature and complexity of each service task required that demonstrates the Tenderers understanding of the Project Brief and the Service Requirements for the project. Maximum submission, 2 A4 pages | 150 |

RULE: - In the event that more than the maximum requested pages of a written statement are submitted for each criterion (excluding cover page and attached references), only the maximum requested pages, as detailed in the criterion description above, of the statement, will be read and scored accordingly. The remaining pages will be disregarded.

The methodology for assessing each of the quality criteria is as follows:

| Score | Meaning | Interpretation |
| --- | --- | --- |
| 80 – 100% | Excellent | An excellent response that clearly demonstrates a thorough understanding of the brief, with detailed supporting evidence of how the tenderer will meet the Authorities requirements |
| 60 – 79% | Good | A good response that demonstrates a real understanding of the brief and provides evidence as to how the Tenderer will satisfy the Authorities requirements |
| 40 – 59% | Acceptable | A response which demonstrates a reasonable understanding of the brief and reasonably well demonstrates how the Tenderer will satisfy the Authorities requirements but lacks sufficient detail to award a higher mark |
| 20 – 39% | Mediocre | The response demonstrates limited understanding with insufficient or no detail and a risk of non-delivery. |
| 1 – 19% | Poor | The response demonstrates a very limited understanding of the requirements, has fundamental flaws and lacks credibility with a significant risk of non-delivery. |
| 0% | No response | Response completely fails to address the criterion under consideration. This is unacceptable and classified as inadmissible. |

# Award of Contract

The Consultants Team is advised that the award of the contract will be on the basis of the Government Standard Conditions of Engagement for Consultancy Services (Copy available at http://www.constructionprocurement.gov.ie/).

The Design Team should note that the Conditions of Engagement provide for a fixed price lump sum for a defined scope of work.

Tenders will be assessed to determine which is the most economically advantageous tender based in accordance with the award criteria set out below.

| Category | Weighting | Max Marks Available |
| --- | --- | --- |
| Tendered Price | 60% | 600 |
| Quality Submission | 40% | 400 |
| Total Marks Awarded |  | 1000 |

The tender receiving the highest combined score (quality and price) will be awarded the contract.

# Documents Accompanying this Project Brief

1.0 – ITT

2.0 – Form of Tender

3.0 – Project Brief

4.0 – Suitability Assessment

5.0 – Model Forms

6.0 – Contract

7.0 – Information Pack

# General Instructions to Applicants

The Contracting Authority reserves the right to terminate this Tender process at any stage and will not be liable for costs incurred by Applicants in participating in this process.

Applicants shall not collude with any other Applicant in relation to this Tender process. Applicants shall not attempt to influence the assessment process. Any breach of confidentiality or  form of collusion shall entitle the Contracting Authority to disqualify an Applicant from the pre-qualification process without notice.

## 9.1 Submission via eTenders (www.eTenders.gov.ie)

Monaghan County Council is using the Tender Post box facility, and tenders must be submitted electronically via the e-Tenders post box facility on www.etenders.gov.ie only. Only Tenders submitted to the electronic post box will be accepted. Tenders submitted by any other means (including but not limited to by email, fax, post or hand delivery) will not be accepted.

Tenderers must ensure that they give themselves sufficient time to upload and submit all required tender documentation before the Tender Deadline. Tenderers should consider the fact      that upload speeds vary.

To submit a document to the electronic post box, please note that you must click “Submit Response”. After submitting, you can still modify and re-send your response up until the response deadline. Tenderers should be aware that the ‘Submit Response’ button will be disabled automatically upon the expiration of the response deadline.

Tenderers not familiar with uploading on e-Tenders should ensure they familiarise themselves.

Submissions and supporting documents must be written in English. Queries and other communications must be in the same language. Any original document in another language must include an accurate translation into English.

## 9.2 Submission Format, Contents and Details

Tender submissions shall be in the format outlined in the relevant section of the ITT.

After the closing date, Applicants may be asked to clarify aspects of evidence supplied, by written submission, by interview or by both for any of the suitability assessment criteria specified as required or submitted in support of any declaration. If such clarification is requested, any additional material supplied must be strictly to supplement material already provided in the original submission.

## 9.3 Non-Compliant Submissions

If an applicant fails to comply in any way with this Tender Brief document, the Contracting Authority may (but is not obliged to) disqualify the Applicant concerned and reject any Tender submission concerned as non-compliant, and, without prejudice to this right, the Contracting Authority may (but is not obliged to) seek clarification or further information (that does not materially alter a submission) from the Applicant in respect of the relevant submission or take any other step permitted by law, including the principles of equal treatment, non-discrimination, transparency and proportionality.

## 9.3 Required Tender Submissions

1. Tender And Schedule

2. Quality Submission responses

3. SAQ

## 9.4 Insurance Requirements

The successful tenderer shall be required to hold for the term services contract the following insurances:

• Employers Liability - €13,000,000

• Public Liability - €6,500,000

• Professional Indemnity - €2,000,000

Tenders must confirm that if awarded a contract under this public procurement competition, they will, from the effective date of the services contract, obtain and hold the types and levels of insurance as specified above. A formal confirmation from the tenderer’s insurance company or broker to this effect will be requested from the successful tenderer prior to the award (And shall be a condition) of any contract.

## 9.5 Tax Clearance

It will be a condition of any contract that the successful tenderer shall comply with all EU and domestic taxation law requirements for the term of any such contract.

The tenderer will be required to produce a tax registration number, as they appear on the Tax Clearance Certificate, to facilitate online verification of their tax status by the Contracting Authority.

## 10.0 Phase 2 Option Selection – (N2 to N12 Section Only) The completion of the Options Selection Process will propose an option which considers risk, cost and meeting of the strategic objectives, ultimately the presentation of the preferred options should also establish that case exist to consider the project in more detail. The Consultant shall carry out all services described below (non-exhaustive), and all relevant items contained in ' 5.0 General Requirements' - Deliverables as per TII – Project Management Guidelines / DoT Transport Appraisal Framework - Updated Project Execution Plan (PEP) - Option Comparison Estimates / Options Report - Road Safety Audit Stage F - Public and Stakeholder Engagement Prior to the commencement of the Options Selection Process, the Consultant shall engage with stakeholders to ensure that they are made aware of the proposal to develop and assess option(s) leading to the selection of a preferred option. This may include the preparation of publicity information (e.g. media advertisements, postal drops, web-based services etc.) to raise awareness of the Project. The Consultant will provide briefings as necessary to public representatives. - Survey Requirements Surveys may be required to develop the preliminary options and to inform the options selection process. The Consultant shall assess the need for additional surveys and make recommendations where necessary. The most common surveys required for a road project of this scale are as follow. - Environmental surveys; - Topographical and Utility surveys; - Multi-modal Transport surveys; - Archaeology-geophysical surveys; and - Ground investigations Where recommendations are accepted by the Client, the Consultant shall prepare tender documents, manage tender process and prepare a tender assessment report. The Consultant shall manage and administer the contract and provide expert site supervision (including associated expenses) and prepare factual and interpretative reports. Cost of actual surveys to be borne by the Client.

- Development of Options + Options Report Options shall be developed in accordance with the TII PMG, TII Project Manager’s Manual for National Road Projects (PE-PMG-02042) and TII Project Appraisal Guidelines. The Consultant shall develop options to a sufficient level of design detail and environmental assessment to comprehensively inform the Option Selection process. The Consultant shall prepare land ownership mosaic mapping to assist in the Option Selection phase. The Consultant shall include for procurement of landownership information from the PRAI. The Option Selection Process shall be a 3-stage process as outlined below and is to be comply with Section 2.1.5 of the TII Publication PE-PMG-02042. - Stage 1: The Consultant shall develop a number of feasible options (maximum of 5 no. including Do-Nothing and Do-Minimum) in accordance with design standards (identifying horizontal and vertical alignments, indicative drainage outfalls, preliminary junction strategy, establishing the proposed road type etc.) including ‘Do-Nothing’ and ‘Do-Minimum’ alternatives. The Consultant shall carry out a Preliminary Options Assessment using the assessment criteria of Engineering, Environment and Economy. This shall result in a number of options being refined to a minimum of 3. - Stage 2: The Consultant shall evaluate the options advancing from Stage 1 by carrying out a Multi Criteria Analysis of the quantifiable and non-quantifiable impacts of the options using the following appraisal criteria of Economy, Safety, Environment, Accessibility & Social Inclusion, Integration and Physical Activity. This MCA shall be used in the selection of the Preferred Option. - Stage 3: The Consultant shall select a Preferred Option for the Scheme and then shall prepare a Project Appraisal Balance Sheet in accordance with the Transport Assessment Framework. Following selection of the Preferred Option the Consultant shall undertake a Walkover Survey to ensure that all significant features have been identified and properly assessed in the Option Selection Process. The Client’s Project Archaeologist shall accompany. The Consultant shall produce an Option Selection Report with the Monaghan County Council, Senior Engineer signing off on its completion.

  - Cost, Risk and Value Management

The Consultant shall complete the following processes in Phase 2, in accordance with TII Cost Management Manual:

- Project Cost Management, including preparation of the Option Comparison Estimates (OCEs), Estimate Assumption Sheet and Estimate Tracking Sheet;

- Project Risk Management, including Project Risk Register (PRR), Quarterly Risk Status Summary Reporting, and Risk Assessment Report(s).

- Project Value Management, including the assessment of project development against key value performance indicators and the preparation of a Quarterly Value Management Summary Report

  - Road Safety Audit (RSA)

The Consultant shall complete Road Safety Audit Feasibility Stage in accordance with TII GE-STY-01024 Road Safety Audit.

  - Ground Investigations

The Consultant is to provide the following Geotechnical deliverables for Phase 2, produced in accordance with TII Document DN-ERW-03083 (Managing Geotechnical Risk),

- Statement of Intent

- Preliminary Sources Study Report

  - Public Consultation

Reference should be made to the general requirements for Public Consultation events in Section 5.7 of this document. The Consultant shall organise, prepare for, and attend the following Public Consultation events for this Phase of the scheme;

- Event 2 (Phase 2) - Stakeholder and Public Consultation – Options Selection (to display Options progressed from Phase 1)

- Event 3 (Phase 2) - Stakeholder and Public Consultation – to display Preferred Option

The Consultant must allow for the attendance of the following key project staff at each public display;

- Project Manager

- Senior Engineer

- Project Administrator

The Public Consultation events (Public Event 2 and Public Event 3) shall be held on separate dates. In addition to the Public Consultation events for this Phase, the Consultant shall prepare for and deliver one presentation to each of the following, in advance of each Public Consultation event required for this Phase;

- Elected Representatives of Monaghan County Council

- Elected Representatives of the Monaghan Municipal District

Consultant shall include for all costs and expenses associated with preparing for and attending these Meetings in person, in the respective office locations.

  - Preparation of Landowner Mapping and Schedules

The Consultant shall prepare Landowner Drawings for the Emerging Preferred Option, for all lands required both temporarily and permanently for the complete provision of the scheme, including all schedules, maps, individual maps and schedules, land searches, extinguishment of rights of way, road closures, etc. The Consultant shall conduct all land ownership and rights-of-way searches to include for Land Registry searches and consultations with landowners on land ownership, rights-of-way and any third-party rights or claims. Legal services, postage and advertising costs shall be borne by the Client.

## 11.0 Phase 3 Design & Environmental Evaluation The Consultant shall carry out all services described below (non-exhaustive), and all relevant items contained in '5.0 General Requirements'. The purpose of Stage 3 is to develop the project design, following selection of the preferred option based on both the technical and environmental input, to a stage where sufficient levels of detail exist to establish land take requirements, to identify and mitigate projects risks and facilitate the progress of the project through statutory process in Stage 4. - Deliverables as per TII – Project Management Guidelines / DoT Transport Appraisal Framework - Updated Project Execution Plan (PEP) - Design Report - Environmental Deliverables - Updated Cost Estimate - Land Acquisition Documentation - Preliminary Business Case - Risk Register - Consultants with Land and Property Owners Land and property owners shall be alerted by Consultant that access to their property may be required at various stages during Phase 3. They should also be advised that Monaghan County Council will provide written notice for access in the case of intrusive works and that compensation may be payable for such works. Individual Stakeholder maps shall be prepared showing the Project’s potential impacts upon the stakeholder’s property when requested. Consultant shall assume 10 no. such requests during Phase 3.

- Environmental Considerations The Consultant shall ensure that all environmentally and other statutorily required documentation is appropriately prepared, having regard to legal and other requirements. The Consultant shall have regard to RE-ENV-07008 Environmental Planning of National Road and Greenway Projects. The Consultant will advise and make recommendations to Monaghan County Council in relation to any Environmental Assessment required to progress the infrastructure development. It shall be necessary during the design stage to review the impact of the Preferred Layout for the Scheme on environmental considerations including the following: - Human Beings - Flora & Fauna - Soils & Waste - Noise & Vibration - Air Quality - Geology, Hydrology & Hydrogeology - Landscape & Visual - Material Assets - Agriculture The design shall proceed where possible and practical in tandem with some of the environmental work outlined below. In some cases, it shall be necessary to adjust/alter the design due to impacts identified. - Screening for Environmental Impact Assessment The Consultant shall carry out screening for EIA/EIAR in accordance with the EIA Directive 2011/92/EU (as amended by Directive 2014/52/EU) and the results shall be documented in a Screening Report. The Consultant shall allow for screening as part of the Fee. A preliminary EIA Screening Report has been commissioned and is included in the Information Pack for reference. Should an EIA/EIAR be required the Consultant shall provide on request a fee proposal using the rates provided on page 4 of the Form of Tender and Schedule (FTS) and make available the resources for an EIA/EIAR to be prepared. Provision of all sub-Consultants/environmental expertise and surveys required to complete the EIA/EIAR shall be included in the Fee proposal. The Consultant shall prepare all necessary documentation and shall carry out the procurement and supervision of site works associated with the above and the costs of same, including associated expenses, to be included in the Fee proposal.

- Screening for Appropriate Assessment (AA) The Consultant shall prepare a Screening for Appropriate Assessment (AA) in accordance with Article 6(3) of the Habitats Directive (Council Directive 92/43/EEC). The findings shall be documented in an Appropriate Assessment Screening Report. A preliminary AA Screening Report has been commissioned and is included in the Information Pack for reference. Provision of all sub-Consultants/environmental expertise and surveys required to complete the above, as indicated in the Environmental Schedule below, shall be included in the Fee. The Consultant shall prepare all necessary documentation and shall carry out the procurement and supervision of site works associated with the above and the costs of same, including associated expenses, to be included in the Fee. The Consultant shall allow for screening as part of the Fee. Environmental Schedule: - AA Screening - EAIR Screening - Ecological Impact Assessment - Tree Survey - Bat Survey - Habitat Survey - Terrestrial Mammals Survey - Invasive Species Survey Should any additional sub-consultants/environmental expertise and surveys be required the Consultant shall provide on request a fee proposal using the rates provided on page 4 of the Form of Tender & Schedule (FTS) and make available the resources for the additional sub-consultants/environmental expertise and surveys to be provided.

- Ecological Impact Assessment The Consultant shall prepare an Ecological Impact Assessment Report (EcIA) for both projects. The Ecological Impact Assessment shall include the following: - Baseline Ecological Assessment - All habitats within the site and its zone of influence shall be surveyed by suitably qualified ecologists at the appropriate time(s) of year. Habitats shall be classified and mapped in accordance with Fossitt (2000) A Guide to Habitats in Ireland or any updated or superseding national guidance. Survey methodologies shall accord with current best practice and professional standards - Assessment should include the likely impacts on the ecology of the whole site and its zone of influence, including any sites designated for nature conservation, such as Special Areas of Conservation (SACs), Special Protection Areas (SPAs), Natural Heritage Areas (NHAs) and other relevant ecological constraints. The presence of protected habitats and species, species of conservation concern, Flora (Protection) Order species, and invasive non-native species shall be considered. The assessment shall identify impacts on key ecological receptors and propose appropriate mitigation measures in accordance with current statutory guidance and best practice. - Proposals should seek to integrate the protection and enhancement of existing biodiversity/ecological and landscape features, where possible, by minimising adverse impacts on existing habitats (whether designated or not) and by including mitigation and/or compensation measures, as appropriate and provide links to wider countryside (pursuant to article 10 of the Habitats Directive). - Fauna - using established best practice survey methods an assessment of: - Breeding birds - Site surveyed for presence of mammals (e.g., badgers and otters) and an assessment of likely impact and proposed mitigation - Bat survey Provision of all sub-Consultants/environmental/ecological expertise and surveys required to complete the above, as indicated in the Environmental Schedule below, shall be included in the Fee. The Consultant shall prepare all necessary documentation and shall carry out the procurement and supervision of site works associated with the above and the costs of same, including associated expenses, to be included in the Fee. Environmental Schedule: - AA Screening - EAIR Screening - Ecological Impact Assessment - Tree Survey - Bat Survey

- Habitat Survey - Terrestrial Mammals Survey - Invasive Species Survey Should any additional sub-consultants/environmental expertise and surveys be required the Consultant shall provide on request a fee proposal using the rates provided on page 4 of the Form of Tender & Schedule and make available the resources for the additional sub-consultants/environmental expertise and surveys to be provided.

- Archaeological Assessment The Consultant shall scope and procure all Archaeological Assessments, Monitoring and Licences that are deemed necessary to advance the scheme to the detailed design of the Infrastructure Project. Some or all of the following specialist surveys shall be required; geophysical, topographic, Lidar, metal detection, ploughed topsoil and machine &/or hand dug trenches/pits (including sieving for finds). In addition, and further to the ground surveys/investigations, the specialist shall carry out desk-based research and validation & recording of the location, date, nature and extent of any discovered archaeological or modern sites or features. This shall include scoping the extent of surveys, (including but not confined to archaeogeophysical surveys) invitation of Tenders, evaluation of Tenders, supervision and administration of the Contract, certification of work done and payment thereof, advising on claims and settlement thereof, and attendance at conciliation / arbitration hearings if necessary. Any licensing requirements should be obtained during phase 3 Design and Environmental and included in the environmental evaluation reporting. The Consultant shall manage and administer the contracts, provide expert full-time site supervision (including associated expenses) and prepare assessment reports. The cost of actual specialists’ survey contract works to be borne by the Client.

  - Land Acquisition Boundary Requirements

The Consultant shall determine Project land take requirements and determine the total number of land holdings affected and, as far as reasonably practicable, the total number of persons with an interest in the affected lands. The current and proposed land use of the lands impacted by the Project should be identified (e.g. agricultural, residential, commercial, other zoned lands). The number, if any, of residential and other buildings required to facilitate construction of the Project should be determined. All boundaries should be determined on the basis of surveys, folios and land registry.

The Consultant shall ensure that sufficient lands are included within the land acquisition boundary to facilitate the construction and operation/ maintenance of the Project. These should include drainage outfalls and attenuation ponds, earthworks, working spaces, service diversions, signs and associated foundations, severed holdings, traffic management, and accommodation works. The Consultant shall ensure that these lands are necessary for or incidental to the construction or maintenance of the Project. The Consultant shall also ensure that the design of any temporary drainage works does not cause flooding in, or otherwise adversely affect, areas outside the lands made available.

  - Detailed Ground Investigations

The GI works will include for the delivery of the entire infrastructure including the delivery of services to the site, road works, structures and any flood mitigation measures proposed in the development. The Consultant should complete a review of available geotechnical information and request information which is supplementary to same. The Consultant shall arrange for the GI contractor in accordance with Department of Transport Grants Memorandum, relevant the year of survey to have access to landowner’s land to facilitate the geotechnical survey. The consultant shall prepare a Ground Investigation Report and Geotechnical Design Report in accordance with the TII Publication DN-ERW-03083 (Managing Geotechnical Risk)

The Consultant shall arrange for and procure all Geotechnical Site Investigations that are deemed necessary to advance the scheme to the Detailed Design of the Infrastructure Project. This shall include scoping the extent of surveys, invitation to Tenders, evaluation of Tenders, supervision and administration of the Contract, certification of work done and payment thereof, advising on claims and settlement thereof, and attendance at conciliation /arbitration hearings if necessary. The Consultant shall satisfy themselves that the scope of the Geotechnical Ground Investigation being undertaken is sufficiently detailed. Specifically for the Geotechnical Site Investigation Works, the Consultant must provide full time site supervisory staff for the duration of the site works associated with the Site Investigation Contract. The cost of this site supervisory staff is to be included in the tender proposal. The consultant should assume a timeframe of 2 months for the completion of site investigation works.

- Detailed Ground Investigations The GI works will include for the delivery of the entire infrastructure including the delivery of services to the site, road works, structures and any flood mitigation measures proposed in the development. The Consultant should complete a review of available geotechnical information and request information which is supplementary to same. The Consultant shall arrange for the GI contractor in accordance with Department of Transport Grants Memorandum, relevant the year of survey to have access to landowner’s land to facilitate the geotechnical survey. The consultant shall prepare a Ground Investigation Report and Geotechnical Design Report in accordance with the TII Publication DN-ERW-03083 (Managing Geotechnical Risk) The Consultant shall arrange for and procure all Geotechnical Site Investigations that are deemed necessary to advance the scheme to the Detailed Design of the Infrastructure Project. This shall include scoping the extent of surveys, invitation to Tenders, evaluation of Tenders, supervision and administration of the Contract, certification of work done and payment thereof, advising on claims and settlement thereof, and attendance at conciliation /arbitration hearings if necessary. The Consultant shall satisfy themselves that the scope of the Geotechnical Ground Investigation being undertaken is sufficiently detailed. Specifically for the Geotechnical Site Investigation Works, the Consultant must provide full time site supervisory staff for the duration of the site works associated with the Site Investigation Contract. The cost of this site supervisory staff is to be included in the tender proposal. The consultant should assume a timeframe of 2 months for the completion of site investigation works. - Topographical and Utility Surveys The Consultant shall procure and manage topographical and/or Utility surveys. The extents, defined by the Consultant, will allow for development of the infrastructure project. The boundary and specification of the said topographic survey will be defined by the Consultants, based on preliminary review of the infrastructure project requirements and the requirements of the infrastructure project as a whole. The cost of the surveys will be borne by the Client while the Consultant will supervise and manage the surveys. - Multi-model Transport Surveys The Consultant will identify data collection requirements for transport modelling. Transport studies that are carried out should be multi-modal assessments, as required. Any such requirements are outlined within Project Appraisal Guidelines Unit: 5.2 – Data Collection.

- Detailed Design + Design Report The detailed design of the Scheme shall be undertaken in accordance with the TII Publications (Standards), Design Manual for Urban Roads and Streets (DMURS), Traffic Signs Manual (TSM), Cycle Design Manual and NTA Bus Infrastructure Design Guidance. The Consultant shall develop the design of the preferred option to an appropriate level of detail to establish land take requirements and to evaluate potential environmental impact. The entire design process should be outlined in a Design Report. The Consultant will develop the design of the scheme by preparing papers/drawings of the scheme which shall include, but are not limited to: - Traffic Counts and Modelling report - Surveys – Environmental, Topographical and Ground Investigation - Licencing Requirements - Design Standards - Road Type, Road Edge Design, Finishes, Foundation; Pavement Design - Traffic Signs / Road Markings / Lighting - Road Geometry (Horizontal and Vertical) & Junction Strategy - Site Clearance and Earthworks - Road Safety Audit Stage F/1/2 (As appropriate) - Boundary Fencing Requirements - Public Transport Facilities / Infrastructure - Cycling, Pedestrian, Vulnerable Road Users Facilities / Infrastructure - Drainage, Flood Attenuation - Ground Investigation, Soil Classification - Existing Services / Proposed Services

9.13.1 Geometric Design The Consultant shall carry out geometric design of the preferred layout including horizontal and vertical alignments, junction design. The Consultant shall ensure that all Design Relaxations / Departures proposed for the Scheme are recorded and submitted to the Client for review.

9.13.2 Earthworks Design The Consultant shall prepare the Detailed Geotechnical Interpretative Report and Design Recommendations. The issues covered in the Detailed Geotechnical Interpretive Report & Design Recommendations shall include the following. - acceptability / re‐use potential or otherwise of materials encountered - determination of quantities of acceptable/unacceptable material in cuts/fills/existing roads, including earthworks balance, etc. - details of any areas of soft/difficult ground conditions and feasible geotechnical design solutions - excavation methods available for any rock encountered and its potential for re‐use - geotechnical design solutions where the proposed alignment coincides with the existing road - costings for geotechnical solutions - advice in the preparation of earthworks cost estimates - advice in relation to levels of risk associated with geotechnical issues - any other issues that the Consultant considers appropriate

9.13.3 Drainage Design / Water Treatment Design The Consultant shall carry out preliminary drainage design and preliminary water quality and pollution control design, in accordance with all current and relevant design standards, including all TII drainage standards, such as - TII Drainage Systems for Roads - TII Design of Earthworks Drainage, Network Drainage, Attenuation and Pollution Control - TII Roads Drainage and Water Environment The Consultant shall prepare a draft erosion and sediment control plan to consider construction work activities and phases, including earthworks, drainage, environmental mitigation, measures for watercourses, site compound(s), avoidance and control measures, emergency procedures, etc. The Consultant shall develop drainage drawings and a Drainage Analysis Report for mainline, junctions and side roads, including the identification and assessment of outfalls. The drainage design shall be progressed to a detailed stage. Drainage environmental issues as highlighted in the ecological assessment of the road project must be considered.

9.13.4 Flood Assessment / Risk Management The Consultant shall liaise with the Office for Public Works (OPW) and prepare all applications for OPW Consents, including, but not limited to, Section 9 & Section 50 consents. The Consultant shall carry out flood risk assessments in accordance with The Planning System and Flood Risk Management Guidelines for Planning Authorities (OPW & Department of Housing, Local Government and Heritage, 2009, as updated) and shall ensure compliance with all current flood risk and drainage design standards in relation to flooding issues, including all TII Drainage Standards where applicable. The Consultant is required to prepare a Flood Risk Assessment Report for submission as part of the Planning Application.

9.15.6 Services/Utilities The project has potential to interact with significant existing services including, inter alia, 110kv ESB Network services, Uisce Éireann trunk watermains, main drains, telecommunications cables (including fibre optic), etc. The Consultant shall assemble all records of current utilities within the study area and shall liaise with all service providers/statutory undertakers with respect to locating of their existing services and relocation as necessary. The Consultant shall prepare a utilities report outlining the presence of all current utilities and proposals for the relocation of certain services to allow the scheme to be progressed. The Consultant shall prepare costs for these proposals and agree with the relevant service provider all conditions that apply in connection with the relocation of same. The proposed access roads will require supporting utility infrastructure provided to facilitate the activation of lands for development along the route. This will require design / accommodation of the following services along the entire route at locations / junctions ready for connection. - Usice Éireann Trunk Watermains with connection to Existing Network - Usice Éireann Foul Sewerage Network with connection to Existing Network & Treatment. - Surface Water Drainage Capacity / Sustainable Urban Drainage Systems for Road Scheme & accommodation made for adjoining lands surface drainage requirements - ESB Network Ducting Provision with Connection to Existing Network - Telecommunications Ducting with connection to Existing Network

9.13.7 Landscape Design The consultant shall undertake a preliminary landscape design for the scheme (planting, trees, flowers, grass, seating, specialised paved area, sculptures, etc.) as necessary. The design may also include landscaping on private property 9.13.8 Accommodation Works The Consultant shall indicate the extent of accommodation works and associated preliminary cost estimate of same. The Client shall be responsible for agreeing accommodation works with landowners and issuing the requirements to the Consultant for development. 9.13.9 Design Report The Consultant shall prepare a Design Report for the Scheme which shall outlines the design process and should follow the template outlined in Appendix A3.5 of the TII Publication, Project Manager’s Manual for the National Road Projects (PE-PMG-02042). It should also take account of any changes to the scope because of the Value Management Process, Peer Review Process, Road Safety Audit and Health and Safety Design Risk Assessment.

- Design Peer Review The Consultant shall prepare for, attend and present their designs at a Design Peer Review. The Design Peer Review shall take place online via MS Teams. - Road Safety Audit (RSA) + Quality Audit The Consultant shall complete the Stage 1 & Stage 2 Road Safety Audits (RSA) in accordance with TII GE-STY-01024 Road Safety Audit and the Quality Audit for the scheme as per Section 5.12. The Consultant shall give full consideration to findings of the audits and respond to the audit team in the prescribed manner. The Consultant shall make any necessary alternations to the design or provide reasoning where the consultant feels that alteration is not appropriate.

- Procurement of Property Valuation Advisors On approval from Monaghan County Council the Consultant shall procure a suitably qualified specialist firm to undertake land and property valuation. The Consultant shall apply Monaghan County Council’s procurement procedure during the process and recommend a preferred valuer. An outline brief for Property Valuation Advisors is included in the TII Publication PE‐PMG‐02042 Appendix A3.8. The appointment of said Consultant and payment of same will be processed through Monaghan County Council and the cost borne by the client. - Land Acquisition Documentation The Consultant shall identify all lands required, both temporarily and permanently for the complete provision of the project and prepare land acquisition mapping. All lands required temporarily are to be reported separately for activities such as temporary diversions, service diversions, accommodation works, short term construction operations, enabling works, borrow pits, disposal of waste material. The Consultant shall prepare Compulsory Purchase Order (CPO) for the scheme, including all schedules, notices, deposit maps, server maps, individual CPO maps and schedules, land searches, extinguishment of rights of way, road closures, etc. The Consultant shall include for consultation with landowners. Legal services, postage and advertising costs shall be borne by the Client. Accommodation Works Schedule: - The Consultant shall attend meetings with landowners, assessing impacts, compiling accommodation works required and prepare costing of such works. - The Consultant shall include for the preparation of and attendance at Scheduled Landowner Meetings during Sub-Stage (ii b). Assume there will be one set of meetings scheduled over 2 working days in total (9:00am to 6:00pm). - The Consultant will provide a key member of the Design Team to attend these meetings at a suitable location in Monaghan. - The Consultant shall attend all and any additional meetings with Landowners required as necessary and as directed by the Client. - The Consultant shall prepare all documentation, publications, letters and notifications as required and/or other duties directed by the Client for the completion of land negotiations and Compulsory Purchase Order (CPO) purposes.

- Health and Safety Design Risk Assessment The Consultant shall examine the Scheme design, as described in the Design Report, to ensure that it can be constructed, operated and maintained in a safe manner in accordance with the requirements of the Safety, Health and Welfare at Work Act 2005 and the Safety, Health and Welfare at Work (Construction) Regulations, 2013 as amended. The assessment shall examine the feasibility of implementing a suitable traffic management plan and shall take account of the Principles of Prevention to mitigate identified risks during construction. All Road Safety Audits shall highlight any safety problems of the end user during the operation of the scheme. The assessment shall also examine how the scheme is to be maintained (e.g., grass cutting on side slopes, maintenance of culverts etc.)

- Cost, Risk and Value Management The following processes will be required for this project at Phase 3 - Updated Cost Estimate – Consultant shall prepare a draft Total Scheme Budget which will comprise of the Preliminary Scheme Cost, inflation provision and provision of Employer Risks. This cost estimate should be prepared in accordance with the requirements of the TII Cost Management Manual (PE-PMG-020044) and the Project Appraisal Guidelines Unit 6.2 - Preparation of Scheme Costs (PE-PAG-02021) - Risk Management update including mitigation plans, Key Risks Schedule; Qualitative Risk Assessment; Quantitative Risk Assessment; and Risk Management Meetings - Regarding Value Engineering, the consultant shall consider Value Engineering Proposals and produce a Value Proposals Register. Consultant to include and discuss Value Management as part of progress meetings with Client All Cost, Risk, and Value management processes and deliverables should be updated as Phase 3 progresses and applied to Project development. Cost, Risk, and Value meetings should be held during Phase 3 as appropriate. The recommendations from risk and value management shall be presented and discussed at Project Progress meetings. It is necessary to ensure that cost, value, and risk items are appropriately managed by the relevant stakeholders.

- Preliminary Business Case (PBC) The Preliminary Business Case sets out the context, rationale, and objectives for a project or programme. It considers scheme options and ultimately identifies a preferred option. The PBC, in its assessment of the most suitable options, must review the likely costs, benefits, impacts, and the overall feasibility of the options intended to deliver a project or programme. This will provide local authorities with an in-depth breakdown of the costs & benefits of the different options, the overall affordability and required budget for schemes as well as the risks and sensitivities associated with potential scheme options. It will also allow the Approving Authority to make an informed decision on whether or not to allow the project or programme to proceed to the next phase of the project lifecycle. The required content of the PBC is available in Module 4 of the Transport Assessment Framework. The PBC must clearly document how the proposed scheme aligns with public policy, including the following - National Development Plan - National Planning Framework - National Climate Action Policy and the current Climate Action Plan - National Investment Framework for Transport in Ireland (NIFTI) - Monaghan County Development Plan 2025-2031 - Monaghan County Council Climate Action Plan 2024-2029 The Preliminary Business Case is the key Transport Appraisal Framework (TAF) deliverable for Gate 1.

- Phase 4 Statutory Processes The Consultant shall carry out all services described (non-exhaustive), and all relevant items contained above. The purpose of Phase 4 is to compile documentation, participate in oral hearing(s) and to advance the Project through the Statutory Processes. It is essential that the Consultant directly considers the relevant legislation when progressing the Project through the statutory processes and ensures it is developed in accordance with planning, environmental and other relevant legislation. - Deliverables as per TII – Project Management Guidelines / DoT Transport Appraisal Framework - Updated Project Execution Plan (PEP) - Updated Design Report - Updated Cost Estimate - Detailed Project Brief & Procurement Strategy - Part VIII Process The Consultant shall undertake a statutory public consultation process in relation to the Preferred Option for both Sections, which is expected to be the Part VIII Planning Process. The Consultant shall prepare the Part VIII documentation for the Scheme to comply with the requirements of the Planning and Development Regulations 2001 as amended. The Part VIII application shall include to produce detailed drawings, which shall fully describe the extent of the proposed works. The Consultants tasks in developing the Part VIII application shall include for but not be limited to the following: - Consultation with Planning Section before preparation of Part VIII documentation to ensure compliance with the Development Plan - Preparation of site notice, location plan, site layout, general arrangement drawings, Part VIII application report, statutory advertisement notices, public consultation material and public consultation report, - Preparation of the following supplementary documents; Traffic Impact Assessment, SUDS Calculations for Road Drainage, Visual Impact Statement, Photomontages, 3D Models, Flood Risk Assessments, Ecological Impact Assessments and Screening Reports (EIAR and AA) - Attendance to attend two in-person meetings with Monaghan County Council’s Planning Department and two in-person meeting with multi-disciplinary teams from within Monaghan County Council and presentation of the Part VIII application before submission. The first such meeting will initiate a 2-week period where each relevant section will provide a preliminary written report indicating any issues arising for consideration. - Alteration / update to Part VIII documentation to accommodate issues arising out of the pre-submission consultation. The Consultant shall prepare copies (3 no. hard copies and Electronic Copy) of the Part VIII Documents and Drawings for the scheme for submission to Monaghan County Council Planning Department. The Consultant shall be responsible for all printing, copying, binding, etc. and delivery to the Client, and all costs associated with same. This Part VIII Public Consultation shall take the form of: - Drawings made available for public viewing in two locations. - Individual meetings, as requested, with persons directly affected by the Project and/or their representatives i.e., Landowners and Businesses. - The Consultant shall attend one Municipal District meeting and attend one Monaghan County Council Meeting to present the Part VIII submission. At the end of the statutory consultation, the Consultant shall prepare a report summarising the submissions received and consider all submissions and make recommendations with regard to any submissions made.

- EIAR/NIS Should an EIAR/NIS be required the Consultant shall provide on request a fee proposal using the rates provided on page 3/4 of the Form of Tender and Schedule (FTS) and make available the resources for an EIAR/NIS to be prepared. Provision of all sub-Consultants/environmental expertise and surveys required to complete the EIAR/NIS shall be included in the Fee proposal. The Consultant shall prepare all necessary documentation and shall carry out the procurement and supervision of site works associated with the above and the costs of same, including associated expenses, to be included in the Fee proposal. The services required should an EIAR/NIS be necessary are detailed below and will form the basis of a future fee request from Monaghan County Council to the consultant to carry out this work. The Consultant shall prepare a Natura Impact Statement. Where it is confirmed that Appropriate Assessment is required, a Natura Impact Statement shall be prepared having regard to the TII’s Environmental Assessment and Construction Guidelines and all relevant National and European guidance, all relevant legislation, including Regulation 30/33 of the Natural Habitats Regulations and Articles 6(3) and 6(4) of the Habitats Directive and all relevant case law. For Archaeological Assessment, services shall include Screening for Appropriate Assessment and preparation of Method Statements and Natura Impact Statement if required. Where an EIAR/NIS is deemed necessary the Consultant shall provide reports, drawings and documentation to An Coimisiún Pleanála. and to Monaghan County Council. The Consultant shall liaise with the Client and arrange for advertisements to be placed in the nominated press (at the expense of the client) on behalf of the Client in advance of the public display. The Consultant shall notify An Coimisiún Pleanála and consult with the prescribed statutory bodies by sending them copies of all reports and associated documents. Upon approval, the Consultant shall submit three hard copies and one electronic copy of the EIAR documentation and associated documents to the board for approval. Any changes required by the Client or any approving authority e.g. An Board Pleanála, must be included in the tender price and incorporated into the Environmental Documents. The Consultant should prepare a comprehensive Construction Environmental Management Plan (CEMP) in accordance with best practice. The CEMP should ensure that environmental impacts identified during the preparation of the EIS and the NIS will be properly managed and that all activities comply with applicable rules and regulations. The intent of the (CEMP) is as follows; - Provide effective, site‐specific, and implementable procedures and mitigation measures to ensure environmental impacts are minimized, monitored and controlled throughout the construction phase of the project. - Ensure the construction activities do not adversely impact amenity, traffic, or the environment in the surrounding area. Specifically, the CEMP ensures that the environmental impacts identified during the preparation of the Environment Impact Statement and the Appropriate Assessment will be properly managed and that activities will comply with all applicable environmental rules and regulations. The main goals of the CEMP are to specify the roles and responsibilities of personnel involved with all aspects of the construction activities; identify potential environmental impacts and the mitigation measures that will be used to address them; establish procedures for audits, monitoring, and inspections; and specify training, recordkeeping, and documentation requirements. The CEMP is intended for use by all personnel involved with construction activities, therefore, the use of technical terms and graphics should be clear and understandable to non‐specialists.

- Publication of CPO Mapping, Order, Schedule and Notices The Consultant shall prepare an Engineers report certifying that the lands contained within the CPO are necessary and sufficient for the purpose of constructing the scheme and recommending to the Chief Executive of Monaghan County Council that the CPO be published. Monaghan County Council will require 8 No copies of all CPO Maps and Documentation, (3No for An Coimisiún Pleanála, 3No for Display and 2 No for Monaghan County Council Departments) for submission to the board. Any EIAR/NIS required to be submitted should be coordinated with the submission to An Coimisiún Pleanála. The Consultant will liaise with the Client’s land and property valuation advisers to provide all engineering assistance required, including costing of engineering solutions, and developing accommodation works as required. The Consultant is to prepare responses/replies to submissions and observations to the CPO. A register of all submissions is to be maintained by the Consultant. - Presentation of the Project to an Coimisiún Pleanála The Consultant will lead the presentation of the scheme at the An Coimisiún Pleanála public Oral Hearing into the scheme. The Consultant’s Project Manager shall ensure and be responsible for making sure that all of the Consultant’s Team, all Project Witnesses, and Local Authority Project Staff have adequately prepared for the Oral Hearing. Each key member of the design team including environmental, agronomy and other specialists shall prepare a précis of evidence to include, assessment report on each objection to the scheme made prior to and during the Oral Hearing. The Consultant shall prepare all display drawings, as agreed with the Client during the Oral Hearing process/preparations and all drawings and documentation for submission at Oral Hearing, including a range of photographs of significant locations within the preferred option, i.e. sensitive environmental areas, buildings, etc. The Consultant shall prepare a spreadsheet stating clearly the justification for each land plot required. This shall be updated on an ongoing basis and as required by the Client. - Attendance at the Pre-Oral Hearing Meetings The Consultant will attend pre‐Oral Hearing meetings with Client’s legal team and advisors (assume initiation workshops/meetings and mock oral hearing workshop), attendance at the Oral Hearing; The preparation of all display drawings for OH and all drawings and documentation for submission at the OH; including range of photographs of the site. The preparation of the Schedule of Commitments for submission during the OH. The Consultant shall prepare a booklet of objections, which shall include but not be restricted to the following (per individual landowner/objectors): - Landowner CPO map and schedule - Individual landowner objection; - Monaghan County Council response to objection; - Accommodation works drawings and schedule; - Drawing of following combination: CPO drawings and overall land holding; - Drawing of following combination: CPO drawings, overall land holding and proposed scheme; Drainage and Water Treatment proposals in vicinity of objector; - Landscape proposals in vicinity of objector; - Environmental mitigation in vicinity of objector; - Photographs of existing landholding. The Consultant shall prepare the Schedule of Commitments for submission during Oral Hearing. The Consultant shall allow for all necessary preparations, including the preparation of briefs of evidence and incorporating review by Senior Counsel and the Client. The Consultant shall prepare an Errata, if required. The Consultant shall prepare Closeout Report on environmental aspects of the Statutory Process and the changes/amendments/agreements made during the process. Attendance at debriefing meeting post hearing and preparation of closeout report on the statutory process and implement changes/amendments/agreements made during the process or as recommended by An Coimisiún Pleanála - Preparation of all Oral Hearing Witness Statements The Consultant will include in their Tender submission for all costs related to the preparation of all Oral Hearing witness statements and associated Oral Hearing documentation, reports, drawings, etc as detailed above. The Consultant will also include in their Tender submission for attendance at all pre‐Oral Hearing meetings/workshops and a post Oral Heating meeting. The Consultant as part of the CPO process shall be required to prepare a book of evidence and attend any Oral Hearing that may arise as the Project Manager for the project and provide any specialist evidence in relation to the project on matters such as environmental considerations, hydrological considerations, option selection process and design considerations both structural and geometrical. The Consultant shall allow 5 days for the Oral Hearing. - Attendance at Oral Hearing by the Consultant Witnesses and Specialist Witnesses Attendance at the Oral Hearing by the Consultants Witnesses and all Specialist Witnesses will be based on and calculated using the tendered hourly rates as submitted in the Consultant’s Tender and included in the Contract. Judicial Review: Where there is an Application or Applications for Leave to Judicially Review the decision of An Coimisiún Pleanála, the Consultant shall be available to provide advice to the Client. - 3D Digital Model / Animation / Visualisation / Photomontages of the Scheme. The Consultant shall provide a 3D computer generated animation and visualisation of the proposed project, incorporating a computer-generated animation illustrating the traffic model/movements/flow and upload this in a widely accessible video format to the project website and other open-source websites (e.g.) YouTube. The Consultant shall provide 12 No. photomontages of aspects of scheme for use by the Client in both the Statutory Process and with landowners. - LAND AGREEMENTS AND ENVIRONMENTAL COMMITMENTS Following Project approval, the Consultant shall collate details of all agreements with affected landowners. The Consultant shall make the updated land agreements, the updated Schedule of Environmental Commitments, and a schedule of any development approval conditions available to the Approving Authority. The Consultant shall inform the Approving Authority of the implications, if any, which these updated requirements may have on the Project scope (programme, budget and quality). - Detailed Business Case & Procurement Strategy The Detailed Business Case and Procurement Strategy refine the preferred option, design and scope initially outlined in the Preliminary Business Case. The Detailed Business Case should provide a clear understanding of what the final output of the project will be once implemented and what is required to progress the scheme so that it delivers the intended benefits over its intended lifespan. It is the benchmark for measuring the development of the scheme and later becomes the basis for the construction contract. The Detailed Business Case is the key Transport Appraisal Framework (TAF) deliverable for Gate 2 (Pretender Approval). The required content of the Detailed Business Case is available in Module 5 of the Transport Assessment Framework, and shall include but not limited to the following; - The project context and updated assessment of the rationale for the project. This will include a description and updated assessment of the strategic relevance of the project. - The consultant shall collate all agreements with affected landowners and include them in the Detailed Business Case for review by the Approving Authority. - Updated Total Project Cost and Stage 4 Total Project Budget to account for any changes arising from modifications to the project, amendments to the environmental mitigation strategy, landowner agreements and any other changes to the design arising from Stage 4. - Procurement Strategy which outlines the proposed approach to procurement required to implement and operate the proposed scheme as described in the Detailed Business Case

- Handover The Consultant shall handover all Project information to the Client, including Design Documentation (prelim & detailed), Cost Estimates, Landowner & Residents File, Safety File, Correspondence, drawings (in the various formats Autocad and Pdf) etc. Electronic copies of drawings to be submitted in suitable, fully referenced, containers. The Consultant shall be mindful of the requirements on Monaghan County Council by the Freedom of Information Act 2014. The information will be handed over in a format that will allow for the data to be easily retrievable at a later stage. The relevant format is to be agreed with Monaghan County Council prior to finalisation. - Termination The Consultant will be required to deliver the consultancy services in accordance with PE‐PMG‐02041 -TII Project Management Guidelines Phase 1 to Phase 4 inclusive. A number of time constraints as yet unknown and outside of the control of Monaghan County Council may arise in the course of this project, for which the Council will not be liable. Monaghan County Council also reserves the right to abandon the project, or parts of the project, if on balance, continuation would not represent value for money or if for any reason funding is not available. The Council may, at will, terminate the Consultants Contract in accordance with Clause 14 of the Standard Conditions of Engagement for Consultancy Services (Technical) – COE1‐v2i March 2023, at any time (during any stage or between stages, even if the project is continuing, if it chooses).

#### Appendix A

Feasibility Study Area Map