# Weaving Worlds Together Phase 2 – Application Responses

Q1 Name of lead applicant

Kerry County Council, Arts Office/Creative Ireland Kerry

Q2 Contact details of lead applicant

Kate Kennelly, Council Buildings, Rathass, Tralee. kkennell@kerrycoco.ie

Q3 Applying strand A or B

If b move to Q #8 Strand B

Q8 List all partners in NI and ROI

Kerry County Council Arts Office /Creative Ireland Kerry

Healthy Ireland Kerry

Family Resource Centre National Forum, Regional Office Cork/Kerry

Ballyheigue/Tralee Family Resource Centre

Kenmare Family Resource Centre

Killarney Family Resource Centre

Listowel Family Resource Centre

Healthy Living Centres Alliance Regional Office (all NI)

- Maureen Sheehan Centre, Belfast

- Cullyhanna & Bessbrook Healthy Living Centre

- Kilkeel Healthy Living Centre

- Omagh Healthy Living Centre

HSE South West – Advisory Partner – see letter of support attached.

Q9 List names and email addresses of all partners.

Kate Kennelly kkennell@kerrycoco.ie

Emma Carmody emma.carmody@kerrycoco.ie

Rita Bevan ritabevan@familyresource.ie

Tony Doherty Tony@hlcalliance.org

Mary Ellen Browne maryellen.browne@listowelfrc.ie

Mary Hunter mary.hunter@heartprojectbelfast.com

Paula McElligott paula@kenmarefrc.ie

Marion Godley mariongodleysp@gmail.com

Sophie Annett kda.nautilus@gmail.com

Alaine Ward health@omaghforum.org

Teresa Nugent teresanugent@rhpsa.org

Deirdre Nagle Deirdre.Nagle@torccfrc.ie

Sheelagh Broderick Advisory Partner Sheelagh.Broderick@hse.ie

Healthy Kerry – Role vacant, however previous HK Co-ordinator in October 25, confirmed alignment with 2026 framework and had begun to explore resources. KCC has advised that new appointee will be engaged on Steering Committee.

## Q10 – Project Title

Weaving Worlds Together Phase 2: Embedding a Scalable All-Island Creative Health Model for Social Prescriber Services (WWT P2)

## Q11 – Target Groups & Key Actions 100 words

WWTP2 combines social prescribing and traditional craft as a non-clinical route to better health, confidence and community. WWTP2 scales the evidence-based hyper-local model. Target groups are adults (80 in 2026; 160 in 2027), experiencing isolation, trauma, and vulnerability – specifically men, older women (settled and Traveller communities), young mothers. WWTP2 actions include expanded reach through peripatetic workshops in remote rural villages, towns, and urban settings; all-island meetups (3) to continue fostering connection and mutual understanding. WWTP2 builds facilitator capacity through all-island workforce engagement, embeds digital data capture and evaluation; fosters health, education, craft partnerships to establish a sustainable, replicable framework.

Q12 Select the area which is the main focus: Can select more than 1

- Core determinants of health YES

- Playing a critical role in health promotion and improvement YES

- Supporting positive mental health in particular for harder to reach groups e.g. older men.  YES

- Promoting positive ageing YES

- Building an inclusive society where every disability is understood and supported YES

- Prevention and management of chronic disease YES

- Supporting end of life bereavement care for patients and their families N/A directly

13 Please state how your project will deliver on the objectives set out in the relevant Local Authorities' Culture and Creativity Strategies and/or the Strategic Action Plan for Creative Arts and Health 2025 (200 words max)

WWTP2 delivers on the objectives of the Strategic Action Plan for Creative Arts and Health 2025 by embedding creative participation within community-based health pathways - specifically social prescribing. Building on a proven all-island 2025 model, WWTP2 positions traditional craft as a non-clinical intervention that enhances wellbeing, strengthens social connection, expands equitable access to high-quality creative practice. The project aligns with Local Authority Culture and Creativity strategies by increasing participation, supporting creative practitioners through professional facilitation opportunities, fostering collaborative cultural networks. WWTP2 moves beyond proof of concept toward a structured, scalable framework that enables local authorities, health partners, and new stakeholders e.g. All Island Social Prescriber Network - to integrate creative engagement into long-term service provision. Intentionally designed, WWTP2 will generate replicable, transferable learning for local authorities, health partners, and community organisations seeking to embed creativity within preventative health approaches. Formalised governance, strengthened cross-sector and agency ownership, enhanced workforce capacity, and robust digital evaluation will produce actionable insights to inform future policy and investment. By combining hyperlocal delivery with all-island engagement, the project strengthens cultural infrastructure while advancing all island ambitions to embed creativity in public life and positions partners at the forefront of creative health innovation and cross-border collaboration.

14. Please state how your project supports the objectives of:

- Healthy Ireland Strategic Framework

- Mental Health Promotion Plan Stronger Together

- The HSE Mental Health Promotion Plan 2022 - 27

- National Traveller Health Action Plan 2022 - 27

- The National Human Rights Strategy for Disabled People Or any other recent (last 5 years)

- Health policy or strategy in Ireland or Northern Ireland

(350 words)

WWTP2 supports key national and regional health policy objectives by embedding an established model of creative participation within preventative, community-based health pathways, provided through structured inclusive programme design that reduces practical barriers such as transport, childcare, and cost, while fostering respect and cultural exchange.

Healthy Ireland Strategic Framework: The primary objective of Healthy Ireland is to improve population health and wellbeing by addressing social determinants of health and supporting people to live healthier lives. WWTP2 directly advances this objective by reducing isolation and loneliness through accessible, non-clinical creative activity delivered via social prescribing, strengthening individual agency, social connection, and community participation.

Mental Health Promotion Plan – Stronger Together prioritises connection, inclusion, and early intervention to promote positive mental health across the lifespan. WWTP2 responds by creating safe, relational spaces where participants build peer support, confidence, and belonging through shared creative practice, particularly for men, young mothers, and older women experiencing vulnerability.

HSE Mental Health Promotion Plan 2022–2027 emphasises prevention, community-based supports, and evidence-informed approaches. WWTP2 aligns through structured, time-bound interventions delivered in non-stigmatising settings, with robust digital evaluation capturing wellbeing outcomes to inform future service planning and resource allocation.

National Traveller Health Action Plan 2022–2027: A core objective of this plan is to reduce health inequalities and improve access to culturally appropriate supports for Traveller communities. WWTP2 supports this through targeted outreach, delivery in trusted local venues.

National Human Rights Strategy for Disabled People (2021–2026): This strategy prioritises equality of access, participation in cultural life, and community inclusion. WWTP2 aligns by offering adaptable, community-based workshops that support participation regardless of ability, promoting dignity, autonomy, meaningful engagement rather than clinical intervention.

Broader health policy in Ireland and Northern Ireland: Across both jurisdictions, health strategies emphasise prevention, social prescribing, and cross-sector collaboration. WWTP2 exemplifies this by integrating arts, health, and community sectors within an all-island model that strengthens local infrastructure while generating transferable learning. By positioning traditional craft as a preventative health support, WWTP2 contributes to a holistic, rights-based model of care that complements statutory services, reduces inequalities, and supports long-term mental wellbeing through community connection and cultural participation.

15. Provide details of 'who does what' in terms of your Creative Ireland and Health Ireland teams are working in partnership with other relevant networks or partner organisations to deliver this project (200 words max)

WWTP2 builds on a proven all-island foundation to deliver a collaborative, embedded, scalable cross-sector craft and health model. Kerry County Council Arts Office/Creative Ireland leads the consortium in partnership. A strengthened governance structure underpins delivery. An expanded steering committee provides strategic oversight.  The local centre partners across the island lead on local service provision, participant engagement for local workshops and the meetup.  Traditional craft facilitators will be procured to deliver the 4-week peripatetic workshops programme and the meetup event workshops. The specifics of the workshops will be designed in collaboration with the SPLOs based on participant needs. The facilitators are required to provide sustainable craft materials and contribute feedback for evaluation purposes. Kerry County Council will procure an external professional project management (PM) team to take responsibility for project and programme activity implementation, general administration, monitoring, data capture, evaluation, reporting, fiduciary remit and governance, communications, future stakeholder engagement, procurement of craft facilitators and other creative industry and technical service providers. The PM team will facilitate remote and in-person knowledge-sharing fora,  report monthly to the steering committee and to KCC. For cost efficiency and sustainability, the PM team will be required to facilitate remote engagement once relationships established with various teams.

16 Set out the plan for engagement with partners and participants, delivery schedule and expected milestones (200 words max)

WWTP2 structured delivery model has been agreed with partners. It combines hyperlocal engagement with sustained all-island collaboration. Engagement begins with partner alignment and governance, facilitators procurement, ensuring operational readiness ahead of programme delivery.

2026: June to November, eight partner centres will each deliver a four-week peripatetic traditional craft workshop series in trusted community settings.

June: WWT presentation at the All-Island Social Prescriber Network strengthening referral pathways and sector visibility.

October: All-island  meet-up in Northern Ireland will bring participants together for shared workshops designed to deepen connection and mutual understanding.

2027: January to November, eight partner centres will deliver two four-week workshop series, significantly expanding participation and geographic reach.

October: An all-island gathering in 2027 will convene partners, craft facilitators, and strategic stakeholders to support knowledge exchange, workforce development, and future scaling.

2026-2027:Partner centres will lead participant engagement through established social prescribing pathways, prioritising target cohorts. Monthly all-island forums for Social Prescriber Link Officers, facilitators, and the Steering Committee will support coordination and oversight. Key milestones include workshops rollout, all island meet-ups (2),implementation of digitalised evidence and evaluation checkpoints, structured existing stakeholder and prospective resource entity engagement, communications. This phased approach strengthens sustainability while establishing firm foundations for long-term growth.

17 What is the creative approach? Tell us more about the creative medium(s) being used and why, and how you will promote a high quality of creative practice in this project

The creative approach aligns with increasing evidence (WHO, historicengland, publichealth.ie, socialprescribingademy.uk) of the positive impact of creative engagement on health, wellbeing, connection and shared cultural experience. The disciplines - ceramics, textiles, and willow weaving - provide accessible, hands-on forms of creative expression that encourage participation regardless of prior experience.

Workshops are delivered by professional facilitators. To ensure a high standard of creative practice, facilitators are procured through public calls and selected based on rigorous criteria, for both artistic excellence, community facilitation expertise and compliance (e.g. vetting). The programme prioritises participant-led exploration within structured environments that balance skills development with social interaction. As 2025 evidenced, the provision of a hyper-local peripatetic service is key to engagement success. The all-island dimension deepens the creative experience by enabling participants to encounter shared traditions through new perspectives, reinforcing creativity as a bridge between local, regional and all island communities. Building on WWT2025 identified opportunities in the craft facilitator services ecosystem, and also challenges identified in the global craft industry, WWTP2 extends engagement with the all-island workforce and guilds. By investing in practitioners, participants, and SP service resources, WWTP2 contributes to building a resilient creative ecosystem capable of delivering lasting health, cultural, and social benefits.

18 What is/are the intended outcome(s) of your project? Please outline your intended wellbeing, social and/or creative outcomes (200 words max)

WWTP2 is designed to deliver measurable participant, community, and sectoral outcomes while operating as a replicable all-island model for sustainable creative health provision. Participants (80 2026, 160 2027) will experience increased social connection, improved confidence, reduced isolation, and a stronger sense of belonging through structured engagement in high-quality craft activity.  Communities comprising participants, partners, and stakeholders will benefit from deeper relationships and strengthened collaboration through shared cultural participation, enhancing social infrastructure, resilience, and inclusion. At a systems level WWTP2 advances a transferable operating framework that embeds creative practice within social prescribing pathways. This includes digitalised administrative processes and a digitally supported evaluation model to generate robust evidence to help inform policy.  Sectoral outcomes include progression toward shared governance across health and community partners, stabilisation and development of the facilitator workforce, a scalable model capable of guiding future investment from prospective cross-sectoral stakeholders in 2026-2027 e.g. ETB/EDU, LEOs/LEAs, Skillnets, Craft Guilds, University researchers.

Intended Impacts

- Timebound goal-oriented sustainable 5 -year business plan

- Use of existing established SP assessment models for ongoing evidence

- Hyperlocal Peripatetic Craft Programme Model embedded & expanded through a multi-agency resource pathway

- Continuation of annual shared island craft activity meetups

- Stabilisation and scaling of professional facilitator community capacity

19. How do you propose to evaluate the final project? (200 words max)

Monitoring and evaluation are embedded in the WWT model. This will continue in 2026/27across all stages of Phase 2 to ensure robust evidence generation and continuous learning.  Enhancing evaluation processes and the 2025 toolkit, a newly implemented digital data collection system will support capture of consistent anonymised participant, partner, and facilitator insights, establishing a reliable baseline for longitudinal analysis. Specific metrics will be finalized with the partners on activation. Mixed-method evaluation will combine quantitative indicators — including participation rates, retention, and engagement levels — with qualitative feedback from partners and participants capturing, wellbeing, confidence, and social connection outcomes.  Case studies will be developed in WWT P2. The WWT monitoring and evaluation is grounded in established social prescriber service monitoring and evaluation methodologies. Regular partner and craft service provider review sessions contribute to reflective practice and adaptive programme management. Findings will inform ongoing WWT model refinement while supporting structured knowledge-sharing with health sector partners, the traditional craft sector, prospective education, training partners and policy stakeholders. This evidence-led approach strengthens the case for sustained investment and supports replication in additional settings. In WWTP2, engagement with appropriate and relevant tertiary education research entities is a key action to facilitate robust and sustained evidence build.

20 If applying under Strand B, please identify how the project has a clear North/South and/or East/West basis, and relates to the Shared Island Initiatives (200 words max)

WWTP2 is inherently structured as a shared island initiative, building on established  North/South partnerships that integrate local authorities, FRCs, HLCs (NI), health partners, social prescribing networks, traditional craft networks and communities across the island.

A central element of WWTP2 is an in-person residential meet-up in the North bringing together participants, professional craft facilitators , Social Prescriber Link Officers, and the Steering Committee from the north and south.  Maintaining momentum on the successful 2025  meet-up, this reciprocal gathering deepens interpersonal connection, supports shared creative experience, and strengthens the relational infrastructure required for sustained cooperation.

WWTP2 embeds ongoing North/South collaboration through monthly all-island forums for Social Prescriber Link Officers, for the craft facilitators, enabling structured knowledge exchange, peer learning, and the development of aligned practices across jurisdictions. The all-island Steering Committee will meet regularly to provide strategic oversight, reinforce governance, and guide long-term model development.

Engagement with the All-Ireland Social Prescribing Network conference further extends professional connectivity while positioning the project within a broader ecosystem.

WWTP2 moves beyond episodic collaboration towards an integrated operational all island model. This approach strengthens mutual understanding, supports professional mobility, and establishes a sustainable framework capable of generating lasting social, cultural, and health benefits across the island.

21 Please state the proposed completion date of the project:

December 2027.

22 What is the potential for your project to be embedded into a healthcare context i.e. into ongoing work of the HSE locally?

Weaving Worlds Together Phase 2 is intentionally designed to support the long-term embedding of creative participation (specifically traditional craft) within community health infrastructure. While the Local Authority has provided critical leadership in establishing the model, Phase 2 represents a planned progression toward shared governance across health, community, and cultural partners.

By strengthening integration with social prescribing services and deepening collaboration with organisations such as the HSE SW, Healthy Living Kerry, Family Resource Centres, and the Healthy Living Centres Alliance, the project advances toward a distributed delivery framework capable of sustaining creative health provision beyond the lifecycle of individual funding streams.

This evolution reflects the growing recognition of creativity as a preventative, non-clinical support that complements existing healthcare pathways while addressing social determinants of health including isolation and reduced community participation.

Enhanced digital evaluation will support health-sector decision-making and future resource allocation. As operational ownership expands across partner organisations, the model becomes increasingly positioned for adoption within routine community health practice. Through this structured progression, Weaving Worlds Together Phase 2 moves beyond project delivery toward systemic integration, establishing the conditions for creativity to function as an embedded component of holistic health support across the island.

23. Statement of Strand Applied For (strand b – auto)

24 Total funding requested over 2026 and 2027 and 2028: €270k

25. Please complete the following table of anticipated income and expenditure for the budget. Please note that funding in 2027 is subject to budgetary availability

(a) 2026 Income - list sources of income here showing Creative Ireland funding sought and any other potential sources of funding:

CI funding sought: €90k inclusive of statutory tax (VAT)

Partner Contributions – In-kind - €24,772

Family Resource Centre National Forum Cork-Kerry Regional Office:  In-kind contribution calculated at €2040

Family Resource Centres Kerry, South x4:  In-kind contribution calculated at €2000 x4=€8k

Healthy Living Centres Alliance Regional Office: In-kind contribution calculated at €1800

Healthy Living Centres North x4: In-kind contribution calculated at €2000 x4=8k

Kerry Co Co Arts Office/Creative Ireland Office: In-kind contribution calculated at €1800

Healthy Kerry In-kind contribution calculated at: €1500

HSE SW In-kind contribution calculated at: €1632

Contributory in-kind resources from partner centres is valued at: €24,772

(b) 2026 Expenditure - list items of expenditure here and highlight items Creative Ireland Programme funding will be used for

Total Expenditure utilising Creative Ireland Programme Funding: €90k inclusive of statutory tax (VAT) where applicable

Programme Activity

CI Contribution -Traditional Craft Facilitators for Local Centre Workshops (8): €17991.6 inc. statutory tax

CI Contribution -Local Centre Participant Resources (transport, care supports) and Workshop Overheads (venue hire, and workshop associated overheads directly related to programme activity e.g. printing posters, forms  etc)(8 centres and 2 regional teams , 80 participants) : €12,176 inc. statutory tax (VAT)

CI Contribution -All-island Meet-Up Event in NI (70 participants) –venue hire, hospitality, accommod.: €21,800 inc. statutory tax (VAT)

CI Contribution for Traditional Craft Facilitators to deliver workshops at the All-island Meet Up Event in NI: €10,402 inc. statutory tax. (VAT)

CI Contribution -All-island Kick-off Event – partners (remote) -cost neutral and inc. in PM remit.

CI Contribution -All-island Traditional Craft facilitators monthly engagement (remote) - cost neutral and inc. in PM remit.

CI Contribution -All-island Social Prescriber Link Officers monthly engagement (remote) - cost neutral and inc. in PM remit.

Project Management Team – includes project management role, evaluator role, programme activity co-ordinator, administration role, design role and independent auditor.  €27630.82 includes statutory tax (VAT)

Refer to separate attached excel doc for breakdown of project and programme details.

- 2027 Income - list sources of income here showing Creative Ireland funding sought and any other potential sources of funding

CI funding sought: €90k inclusive of vat

Contributory in-kind resources from partner centres is valued at €20944

Family Resource Centre National Forum Cork-Kerry Regional Office:  In-kind contribution calculated at €1632

Family Resource Centres Kerry, South x4:  In-kind contribution calculated at €1700 x4=€6800

Healthy Living Centres Alliance Regional Office: In-kind contribution calculated at €2176

Healthy Living Centres North x4: In-kind contribution calculated at €1700 x4=€6800

Kerry Co Co Arts Office/Creative Ireland Office: In-kind contribution calculated at €1088

Healthy Kerry In-kind contribution calculated at: €1632

HSE SW In-kind contribution calculated at: €816

Contributory in-kind resources from partner centres is valued at: €20944

(b) 2027 Expenditure - list items of expenditure here and highlight items Creative Ireland Programme funding will be used for

Programme Activity

Creative Ireland contribution for Traditional Craft Facilitators for Local Centre Workshops (8): €35983 inc. statutory tax

Creative Ireland contribution for Local Centre Participant Resources (transport, care supports) and Workshop Overheads (venue hire, and workshop associated overheads directly related to programme activity e.g. printing posters, forms  etc)(8 centres and 2 regional teams , 160 participants) : €22494 inc. statutory tax (VAT)

Creative Ireland contribution for All-island Traditional Craft facilitators monthly engagement (remote) - cost neutral and inc. in PM remit.

Creative Ireland contribution for All-island Social Prescriber Link Officers monthly engagement (remote) - cost neutral and inc. in PM remit.

Creative Ireland contribution for All-island Mid Project  Event – partners and new stakeholders (remote) -cost neutral and inc. in PM remit.

Creative Ireland contribution for Project Management Team – includes project management role, evaluator role, programme activity co-ordinator, administration role, design role and independent auditor and technical team for digitalisation.  €31523.74 includes statutory tax (VAT)

Refer to separate attached excel doc for breakdown of project and programme details.

Total Expenditure utilising Creative Ireland Programme Funding: CI Funding Expenditure €90k inclusive of vat

(a) 2028 Income - list sources of income here showing Creative Ireland funding sought and any other potential sources of funding:

CI funding sought: €90k inclusive of statutory tax (VAT)

Partner Contributions – In-kind - €24,772

Family Resource Centre National Forum Cork-Kerry Regional Office:  In-kind contribution calculated at €2040

Family Resource Centres Kerry, South x4:  In-kind contribution calculated at €2000 x4=€8k

Healthy Living Centres Alliance Regional Office: In-kind contribution calculated at €1800

Healthy Living Centres North x4: In-kind contribution calculated at €2000 x4=8k

Kerry Co Co Arts Office/Creative Ireland Office: In-kind contribution calculated at €1800

Healthy Kerry In-kind contribution calculated at: €1500

HSE SW In-kind contribution calculated at: €1632

Contributory in-kind resources from partner centres is valued at: €24,772

(b) 2028 Expenditure - list items of expenditure here and highlight items Creative Ireland Programme funding will be used for

Total Expenditure utilising Creative Ireland Programme Funding: €90k inclusive of statutory tax (VAT) where applicable

Programme Activity

Traditional Craft Facilitators for Local Centre Workshops (8): €17991.6 inc. statutory tax

Local Centre Participant Resources (transport, care supports) and Workshop Overheads (venue hire, and workshop associated overheads directly related to programme activity e.g. printing posters, forms  etc)(8 centres and 2 regional teams , 80 participants) : €12,176 inc. statutory tax (VAT)

All-island Meet-Up Event in Kerry (70 participants) –venue hire, hospitality, accommod.: €21,800 inc. statutory tax

Traditional Craft Facilitators for All-island Meet Up Event in NI: €10,402 inc. statutory tax.

All-island Kick-off Event – partners (remote) -cost neutral and inc. in PM remit.

All-island Traditional Craft facilitators monthly engagement (remote) - cost neutral and inc. in PM remit.

All-island Social Prescriber Link Officers monthly engagement (remote) - cost neutral and inc. in PM remit.

Project Management Team – includes project management role, evaluator role, programme activity co-ordinator, administration role, design role and independent auditor.  €27630.82 includes statutory tax (VAT)

Refer to separate attached excel doc for breakdown of project and programme details.

26 Declaration – to be signed by KCC

27 Signature – to be signed by KCC

28 Date – to be noted by KCC

29 Additional info –

HSE Letter of support

Excel doc with detailed budget, schedule, programme activity details.

Document with links to the toolkit, 2025 report, animation link.

NOTE: KK and JF to upload and submit on Tuesday 24th February at midday.

END.