Project Brief

Tender for the appointment of Project Management and Quantity Surveying Services for the RRDF Category 2 of the Inishturk Multipurpose Hub & Tourism Accommodation Project

1. Introduction	2

1.1 Contracting Authority	3

2. Inishturk Multipurpose Hub & Tourism Accommodation Project	4

3. Specification of Requirements	7

4. Governance and Reporting	8

5. Procurement of Architect-Led Single Point Design Team	9

6. Management of Design Development and Planning Process	10

7. Programme, Cost and Risk Management	11

8. Stakeholder Coordination and Engagement	12

9. Compliance and Standards	14

10. Overall Responsibility	14

11. Project Deliverables	15

12. General Requirements	17

13. Out of Scope	18

Appendix 1	19

A. Project Manager Stage Services	20

B – Quantity Surveyor Stage Services	24

## 1. Introduction

This tender concerns the appointment of professional consultancy services to support the delivery of the RRDF Category 2 Inishturk Multipurpose Hub & Tourism Accommodation Project. The competition is divided into two separate Lots:

Lot 1 – Project Management Services

Lot 2 – Quantity Surveying Services

The scope of the Services is primarily focused on the delivery of the RRDF Category 2 of the Project, including progression through design development, feasibility, stakeholder engagement, the preparation, submission and progression through the planning process.

The RRDF Category 2 phase relates to the design development, feasibility and planning of the Project to enable its progression to a future capital funding application. Subject to funding, subsequent phases may include detailed design, procurement and construction of the proposed development.

The successful Tenderer(s) will support the Contracting Authority in progressing the Project to a capital funding-ready position, including advice on project readiness, programme, cost planning, risk management, procurement strategy and supporting documentation arising from the Category 2 phase. Responsibility for preparing and submitting any future capital funding application shall remain with the Contracting Authority unless otherwise agreed.

Where appropriate and permissible under the Contract and applicable public procurement requirements, the Contracting Authority may require the successful Tenderer(s) to provide continued professional services in support of subsequent phases of the Project, subject to project progression, funding availability and the Contracting Authority's requirements.

This appointment does not extend to subsequent project phases, including detailed design, procurement of works, construction or project delivery beyond the defined scope of this appointment, which will be subject to separate consideration and procurement in accordance with public procurement requirements.

### 1.1 Contracting Authority

South West Mayo Development Company CLG (hereafter referred to as the “Contracting Authority”) is one of a network of 49 Local Development Companies in Ireland. The company implements a range of programmes on behalf of local and national government which address the needs of people, communities, and businesses. In general, the company’s area of operations is the south and west Mayo area, but some programmes cover all of County Mayo, and others extend into counties Galway, Roscommon and Donegal.

These programmes include the Rural Development Programme (LEADER), Social Inclusion & Community Activation Programme (SICAP), social employment schemes (Rural Social Scheme, Tús Initiative and Community Employment), the Walks Scheme, Social Farming, and a range of other programmes supporting vulnerable groups including migrants and refugees.

South West Mayo Development Company’s (SWMDC) core purpose is to sustain and develop people, communities, resources, and environment by supporting grassroots economic and community development activity and enabling people to sustain livelihoods and a good quality of life in the west of Ireland.

SWMDC is a community-based organisation and a company limited by guarantee with charitable status. The company is committed to making a positive impact by promoting employment, inclusion, supporting enterprise, and addressing inequality.

For the purposes of this tender, SWMDC is the lead applicant and Contracting Authority for the Rural Regeneration Development Fund (RRDF) Category 2 project entitled Inishturk Multipurpose Hub & Tourism Accommodation Project, being delivered in partnership with Inishturk Community Club CLG (ICC), which acts as the local community lead and project partner.

## 2. Inishturk Multipurpose Hub & Tourism Accommodation Project

South West Mayo Development Company CLG (SWMDC), in partnership with Inishturk Community Club CLG (ICC), is advancing a Rural Regeneration Development Fund (RRDF) Category 2 project to progress the design and development of a multipurpose hub and tourism accommodation initiative on Inishturk Island, County Mayo, located close to Inishturk Village.

The proposed development is currently estimated to have an indicative capital value of approximately €6 million to €9 million. This estimate is indicative only and will be refined through the design development and cost planning processThis project is a priority enabling action arising from the Inishturk 2050 Vision, a community-led long-term strategic framework that sets out a pathway for sustaining Inishturk as a living, resilient island community. The Vision establishes a clear direction for the island’s future, centered on population sustainability, liveability, cultural vitality and climate resilience, and is underpinned by four interconnected strategic pillars.

Inishturk is at a critical point in its long-term sustainability. Housing constraints limited economic infrastructure, and the challenges of remote island living continue to impact the island’s ability to retain and attract a balanced, year-round population.

At the same time, the island possesses significant strengths — including its landscape, heritage, community cohesion and distinct identity — which position it as a unique and compelling place to live, work and visit.

There is a clear ambition for the development to deliver high-quality, context-responsive architecture that is rooted in the landscape, reflects the identity of Inishturk, and contributes meaningfully to the long-term vision for the island.

The proposed development responds directly to these conditions by delivering key enabling infrastructure aligned with the Culture, Sports, Wellbeing & Enterprise pillar of the Inishturk 2050 Vision. The project will establish a multipurpose hub incorporating remote working facilities, community and cultural space, and complementary tourism accommodation.

This development is intended to set a strong architectural and place-based standard, contributing meaningfully to the long-term vision for the island and reinforcing Inishturk’s identity as a distinctive high-quality destination.

Together, these elements form an integrated platform to support enterprise, enable remote work, strengthen community life and enhance the island’s capacity to welcome visitors in a way that is sustainable, community-led and appropriate to scale.

The project is a critical piece of infrastructure that enables wider economic and social activity on the island. It addresses the current lack of appropriate space for accommodation, enterprise and community use, which limits the island’s ability to translate its inherent strengths into sustainable livelihoods and long-term resilience.

Delivered within a remote island context, the project presents unique logistical, environmental and operational challenges. It will require coordinated engagement across multiple stakeholders, including the local community, statutory bodies and funding partners, and careful alignment with the island’s long-term strategic framework.

Community and stakeholder engagement will be central to the successful delivery of the Project and shall be managed in a structured, proportionate and locally sensitive manner throughout the commission.

Planning permission has not been secured for the proposed development. The current phase (RRDF Category 2) focuses on design development, feasibility and planning, with the objective of bringing the Project to a fully developed and costed position, with the planning process progressed, suitable to support progression to a future capital funding application (RRDF Category 1).

The appointed Project Manager and Quantity Surveyor will each play a central role in supporting this process within their respective areas of responsibility. The Project Manager will provide client-side leadership, coordination, governance and stakeholder management, while the Quantity Surveyor will provide cost planning, cost control and commercial advice. Together, these roles will support the effective management of the Architect-led Single Point Design Team (SPDT) and the development of the documentation required to progression through the planning process.

Τhe Project Manager and the Quantity Surveyor will support effective programme coordination,stakeholder engagement and statutory consultations, and ensuring alignment between design development, programme, cost and planning requirements within their respective areas of responsibility.

The Project will be delivered within a remote island environment and will be subject to logistical, operational, stakeholder and statutory constraints which shall be taken into account throughout the delivery of the Services.

Given the unique characteristics of the Project and its remote island setting, the Contracting Authority strongly encourages Tenderers to familiarise themselves with the Project location and the wider island context prior to submitting a Tender. While attendance at the Project site is not mandatory, Tenderers are expected to satisfy themselves that they have a sufficient understanding of the Project environment, logistical considerations and community context to prepare a robust and informed Tender.

Details of the organised site visit arrangements are set out in the Invitation to Tender.

## 3. Specification of Requirements

South West Mayo Development Company CLG (SWMDC) is seeking to appoint professional consultancy services under two separate Lots to support the delivery of the Rural Regeneration Development Fund (RRDF) Category 2 phase of the Inishturk Multipurpose Hub & Tourism Accommodation Project.

The competition comprises the following Lots:

- Lot 1 – Project Management Services

- Lot 2 – Quantity Surveying Services

The Project Manager will act on behalf of the Contracting Authority as Client’s Representative and in partnership with Inishturk Community Club CLG (ICC) to provide strategic leadership, coordination and oversight of the project from inception through to completion of the Services under this appointment.

This role is a client-side leadership position and is distinct from the Architect-led SPDT. The Project Manager will not form part of the SPDT and will act independently on behalf of the Contracting Authority.

The Quantity Surveyor will provide independent quantity surveying, cost planning and commercial advisory services to support design development, feasibility, planning, funding readiness and informed decision-making throughout the commission.

The Quantity Surveyor will act independently of the Architect-led SPDT and will work collaboratively with the Project Manager, the Contracting Authority, ICC, the Project Steering Group and the SPDT within their respective professional role.

The Project Manager and Quantity Surveyor will each be responsible for delivering the Services within their respective scope of appointment, ensuring that outputs are delivered in line with the agreed programme, funding requirements and governance arrangements, and that the Project is progressed to a fully developed and costed position suitable for progression to a future RRDF Category 1 capital funding application.

For clarity, this commission includes the design development required to progress the Project through the planning process. Detailed design is not included and will form part of a future RRDF Category 1 commission.

Tenderers are required to price the Services associated with the RRDF Category 2 scope up to Stage 2C only, in accordance with this Project Brief and the Pricing Schedule. The total proposed fee covers all services up to stage 2C.

## 4. Governance and Reporting

The Project Manager will be contractually answerable to the Contracting Authority and will report on a regular basis to a Project Steering Group comprising representatives of SWMDC and ICC.

The Project Manager will be responsible for establishing clear reporting structures, maintaining effective communication across all stakeholders, and ensuring that decision-making processes are structured, timely and appropriately documented.

The Quantity Surveyor shall report through the agreed governance structure and provide cost planning, commercial and funding-related advice to support project reporting and decision-making within its respective scope of Services.

The Quantity Surveyor may be required to attend Project Steering Group meetings, design team meetings, cost review meetings and other project meetings where cost, commercial, funding or value-for-money matters are to be considered.

The Project Manager will ensure that reporting outputs are structured to enable direct review by the SWMDC and ICC Boards, avoiding the need for re-interpretation or re-formatting. The Project Manager may be required to attend a limited number of SWMDC and ICC Board meetings (anticipated to be up to four per annum), including preparation and presentation of relevant updates, which may take place outside normal working hours.

The Project Manager will support structured decision-making processes throughout the project in collaboration with the Project Steering Group. Strategic and reserved matters shall progress through the agreed governance structure established between SWMDC and ICC.

The Project Manager will provide clear, timely and well-structured recommendations to support decision making, ensuring that all relevant information, including cost, programme and risk implications, is presented to enable informed decisions. Where appropriate, the Quantity Surveyor shall provide professional cost and commercial advice to inform those recommendations.

The Project Manager shall maintain appropriate project governance records, including meeting minutes, action trackers, programme updates, risk registers and decision logs, and a shared project information repository to support effective project governance and auditability throughout the commission.

The Project Manager will not have authority to make material project decisions without the approval of the Project Steering Group.

## 5. Procurement of Architect-Led Single Point Design Team

The Project Manager will lead and manage the full public procurement process for the appointment of an Architect-led Single Point Design Team (SPDT).

This will include:

- Preparation of tender documentation in line with public procurement requirements.

- Management of the eTenders process, including responding to queries and clarifications.

- Coordination of tender evaluation in collaboration with the Project Steering Group.

- Preparation of recommendation reports and supporting documentation.

- Ensuring full compliance with national public procurement guidelines and RRDF requirements.

The Project Manager shall coordinate with the Quantity Surveyor, where required, in relation to cost-related inputs, pricing structures, cost information and commercial considerations relevant to the procurement of the SPDT.

The Project Manager may be required to support other procurement processes on the project such as site surveys, environmental impact surveys and other necessary works / reports, including appropriate coordination with local community stakeholders where such activities require access arrangements, local knowledge, engagement or logistical support.

## 6. Management of Design Development and Planning Process

Following appointment of the Architect-led SPDT, the Project Manager will be responsible for the overall coordination and management of the design development and planning process, working with the Quantity Surveyor in relation to cost planning, commercial advice and value for money considerations.

This will include, but not limited:

- Managing and coordinating the activities of the Architect-led SPDT

- Ensuring timely delivery of all required surveys, investigations, feasibility studies and technical assessments.

- Overseeing the development and assessment of design options.

- Ensuring alignment between design development, cost planning, value for money and project objectives.

- Coordinating stakeholder engagement, including statutory bodies, local community and project partners.

- Ensuring that all necessary documentation is prepared to support a robust planning application.

- Coordinating the delivery of the services as further described in Appendix 1 – Stage Services.

- Awareness of the logistical constraints associated with remote island delivery, including transport dependency, weather disruption, construction sequencing and material procurement, to support informed decision-making and appropriate project planning.

- Consideration of project risks associated with remote island delivery, including programme, procurement and construction-related risks, and the identification of appropriate mitigation approaches and risk allocation strategies.

The Project Manager will be responsible for driving the Project through the planning process, including the preparation and submission of the planning application, in coordination with the Architect-led SPDT, the Quantity Surveyor and the Project Steering Group. Any services associated with a planning appeal shall only be provided where expressly instructed by the Contracting Authority.

The Project Manager will be responsible for ensuring that the design development process achieves an appropriate balance between architectural quality, island deliverability, cost certainty, value for money and cost.

This includes supporting the development of a high-quality, context-responsive design that reflects the identity and landscape of Inishturk, while ensuring that proposals remain practical, buildable and aligned with available funding and project constraints.

## 7. Programme, Cost and Risk Management

The Project Manager will be responsible for establishing and maintaining overall control of programme, cost and risk throughout the Category 2 of RRDF. The Quantity Surveyor will be responsible for cost planning, cost management and commercial advice, working in coordination with the Project Manager and the Architect-led SPDT.

This will include, but not limited:

- Development and management of a detailed project programme by the Project Manager.

- Monitoring progress against key milestones and deliverables by the Project Manager.

- Coordination of cost planning and commercial advice provided by the Quantity Surveyor, ensuring alignment with programme, available funding and project objectives.

- Identification and management of project risks, including those relating to logistics, programme and stakeholder engagement.

- Ensuring that project outputs are delivered within agreed timeframes and budget parameters.

Note: The Project Manager shall retain overall responsibility for programme management, project coordination and risk reporting. The Quantity Surveyor shall retain responsibility for cost planning, cost management, value for money and commercial advice. Both roles shall work collaboratively to ensure alignment between programme, cost, risk, funding requirements and project objectives.

The anticipated duration for delivery of the RRDF Category 2 phase is approximately fifteen (15) months from appointment. This is an indicative timeframe, and the final programme will be developed by the Project Manager in agreement with the Project Steering Group, taking account of project complexity, statutory processes, stakeholder engagement and logistical considerations.

## 8. Stakeholder Coordination and Engagement

The Project Manager will be responsible for coordinating structured and effective engagement across the key stakeholders required to support the successful progression of the Project.

This will include, but not limited, engagement with:

- SWMDC as Contracting Authority

- Inishturk Community Club CLG Board and representatives

- Local community stakeholders

- Mayo County Council and relevant statutory bodies

- Utility providers and national agencies

- The Quantity Surveyor, where cost, commercial, funding or value-for-money matters are relevant to stakeholder discussions.

The Project Manager will ensure that stakeholder engagement is constructive, coordinated and aligned with the overall objectives of the Project, while maintaining project momentum and clarity of direction.

The Project Manager will also support structured communication of project progress, including engagement with the local community through updates, events or other appropriate formats, ensuring transparency and a shared understanding as the Project develops.

The Project Manager will be expected to maintain a meaningful and visible presence on Inishturk, proportionate to the needs of the Project, to support community engagement, stakeholder coordination, local logistics and effective communication. This may include face-to-face engagement where required, in addition to remote meetings and written communications.

Stakeholder and community engagement will be structured and aligned with key project milestones. The Project Manager will ensure that engagement is appropriately timed to support informed feedback on developed proposals, rather than at early conceptual stages, in order to maintain project clarity and momentum.

Where landowner or land acquisition matters arise during the commission, the Project Manager shall provide a coordination and programme tracking role only. This may include liaison with the Contracting Authority, relevant solicitors, advisers and stakeholders, tracking of key actions and escalation of delays or risks. Legal negotiations, conveyancing, legal advice and decisions relating to land acquisition shall remain the responsibility of the Contracting Authority and its legal advisers.

The Project Manager shall prepare and maintain a proportionate Community and Stakeholder Engagement Plan, aligned with the agreed governance structure and key project milestones.

All engagement activities will be agreed with the Project Steering Group in advance and will be designed to ensure clear communication, manage expectations and support the progression of the Project in a coordinated and efficient manner.

## 9. Compliance and Standards

The Project Manager will be responsible for ensuring that the Project is progressed in a compliant, transparent and properly documented manner throughout the RRDF Category 2 phase. The Quantity Surveyor shall ensure that all cost planning, commercial and quantity surveying services are delivered in accordance with applicable professional standards and the requirements of this commission.

In carrying out the Services, the Project Manager and the Quantity Surveyor will ensure that all aspects of the Project within their respective scope of Services are delivered in compliance with:

- RRDF funding requirements.

- Public procurement regulations.

- The Capital Works Management Framework (CWMF), where applicable.

- Relevant national standards and guidelines.

- Applicable planning and environmental requirements.

The Project Manager will ensure that appropriate governance, documentation and audit trails are maintained throughout the Project, including records of key decisions, procurement activities, stakeholder engagement, approvals, risks and actions required to support effective oversight and funding compliance. The Quantity Surveyor shall maintain appropriate commercial and cost records to support project governance, funding compliance and audit requirements.

## 10. Overall Responsibility

The scope of this appointment is primarily focused on the delivery of the RRDF Category 2 phase of the project, including progression through design development, feasibility, stakeholder engagement and the preparation submission and progression through the planning process.

The successful Tenderer(s)may be required to support future RRDF capital funding application (Category 1 / Measure 1 or equivalent), including advising on project readiness, cost planning, programme, risk and supporting documentation, working in collaboration with the Project Steering Group and relevant stakeholders.

This appointment does not extend to subsequent project phases, including detailed design, procurement of works, construction or project delivery beyond the defined scope of this appointment, which will be subject to separate consideration and procurement in accordance with public procurement requirements.

Successful delivery of the Services will include the appointment and management of the Architect-led SPDT, completion of the required design development and supporting studies, progression of the Project through the planning process, and preparation of the Project for future RRDF Category 1 capital funding consideration.

## 11. Project Deliverables

The Project Manager and Quantity Surveyor will each be responsible for delivering the outputs within their respective scope of Services. Deliverables shall be prepared in a clear, structured and auditable manner and shall support effective governance, decision-making, funding compliance and progression of the Project through design development, feasibility and planning.

The principal deliverables of the commission shall include, but not be limited to, the following:

Project Manager

- Prepare Single Point Design Team scope of requirements and procurement documentation.

- Manage public procurement process for the appointment of the Single Point Design Team.

- Establish and maintain a detailed project programme (including Gantt chart or equivalent).

- Coordinate and manage the design development process. Oversee delivery of feasibility studies, surveys and technical assessments as required.

- Prepare and maintain an Island Delivery and Logistics Strategy addressing transport and ferry logistics, weather dependency, material deliveries, workforce access, accommodation, utilities, construction sequencing, buildability and associated project risks to support project planning, procurement and future delivery.

- Coordinate stakeholder engagement, including community stakeholders, statutory bodies and project partners.

- Prepare and maintain a Community and Stakeholder Engagement Plan

- Oversee and coordinate preparation, submission and progression of planning application documentation.

- Maintain project governance records, including meeting minutes, action trackers, programme updates, decision logs and risk registers in a shared project information repository

- Prepare regular progress reports to the Project Steering Group

- Prepare documentation required to support RRDF drawdowns in collaboration with SWMDC

- Procurement strategy and recommendations for future project phases, supporting continuity of professional services where appropriate.

- Coordinate with the Quantity Surveyor to ensure the timely delivery of cost planning, commercial advice and funding-related information required to support project governance, planning and funding readiness

- Coordinate the delivery of the Services described in Appendix 1 – Stage Services

- Final Project Report for the RRDF Category 2 Phase.

Quantity Surveyor

- Prepare and maintain project cost plans, cost estimates and cost reports;

- Provide cost planning, cost management and commercial advice throughout the commission;

- Monitor project costs against available funding and advise on affordability, value for money and funding readiness;

- Support design development through cost advice, option appraisal, value engineering and value-for-money assessments;

- Provide commercial input to procurement documentation, pricing schedules and tender evaluations, where required;

- Provide cost and commercial input to risk management, programme review and project decision-making;

- Prepare cost information and commercial advice required to support RRDF drawdowns, where applicable;

- Prepare cost information and commercial advice to support future RRDF Category 1 capital funding applications;

- Coordinate with the Project Manager and Architect-led SPDT to ensure cost, programme, design and funding requirements remain aligned;

- Contribute to the delivery of the Services described in Appendix 1 – Stage Services.

The Project Manager and Quantity Surveyor shall work collaboratively with the Contracting Authority, Inishturk Community Club CLG (ICC), the Project Steering Group and the Architect-led Single Point Design Team (SPDT) to ensure the coordinated delivery of the Services described in Appendix 1 – Stage Services. Both appointments shall support the progression of the Project to a fully developed, costed and planning-ready position suitable for progression to a future RRDF Category 1 capital funding application.

## 12. General Requirements

The Project Manager and Quantity Surveyor shall work closely with the Contracting Authority, Inishturk Community Club CLG and the Project Steering Group to ensure the successful delivery of the Services.

The Project Manager and Quantity Surveyor shall attend meetings as required throughout the duration of the commission, including but not limited to Project Steering Group meetings, design team meetings, cost review meetings, stakeholder meetings and statutory consultation meetings, and shall maintain effective communication with all relevant stakeholders.

The Project Manager may be required to attend a limited number of SWMDC and ICC Board meetings, including the preparation and presentation of project updates and recommendations, which may take place outside normal working hours. The Quantity Surveyor may also be required to attend such meetings where cost planning, commercial or funding-related matters are to be considered.

The Project Manager shall maintain a meaningful and visible presence within the Project area, proportionate to the needs of the Project, to support stakeholder engagement, community participation, local coordination and effective project delivery.

The Project Manager and Quantity Surveyor shall ensure continuity of service throughout the duration of the Contract and shall maintain appropriate arrangements to ensure the continued delivery of the Services in the event of the temporary or permanent unavailability of key personnel.

The Project Manager and Quantity Surveyor shall be required to work flexibly, including occasional evening or weekend engagement where necessary to facilitate stakeholder participation, community engagement activities or project requirements.

The Project Manager and Quantity Surveyor shall maintain appropriate records, documentation and audit trails throughout the commission and shall ensure that all information is managed in accordance with applicable legal, contractual and funding requirements.

The Project Manager and Quantity Surveyor shall undertake such additional activities as may reasonably be required to ensure the successful delivery of the RRDF Category 2 phase in accordance with the requirements of this Project Brief.

## 13. Out of Scope

The scope of this appointment is primarily focused on the delivery of the RRDF Category 2 phase of the Project, including progression through design development, feasibility, stakeholder engagement and the preparation, submission and progression through the planning process.

The successful Tenderer(s) may be required to support the preparation of a future RRDF capital funding application (Category 1 / Measure 1 or equivalent), including advising on project readiness, cost planning, programme, risk and supporting documentation, in collaboration with the Project Steering Group and relevant stakeholders.

Services relating to subsequent project phases, including detailed design, procurement of works, construction or project delivery beyond the initial scope of Services, are not included in the initial scope of this appointment. The Contracting Authority may require continued professional services for subsequent phases of the Project, including phases associated with a future RRDF Category 1 capital funding application, where appropriate and permissible under the Contract and applicable public procurement requirements.

## Appendix 1

This Appendix sets out the indicative professional services anticipated during the delivery of the RRDF Category 2 phase of the Project.

The Stage Services are divided into two separate professional appointments:

- A – Project Manager Stage Services

- B – Quantity Surveyor Stage Services

The Project Manager shall act as the Client's Representative and shall provide overall project leadership, governance, programme management, stakeholder coordination and management of the Architect-led Single Point Design Team (SPDT).

The Quantity Surveyor shall provide independent cost planning, cost management and commercial advisory services throughout the commission and shall lead the Project's cost planning and commercial workstream within each project stage.

The Project Manager shall retain overall responsibility for coordinating the delivery of the Project. The Quantity Surveyor shall work collaboratively with the Project Manager, the Contracting Authority, the Project Steering Group and the Architect-led SPDT to ensure that programme, design, cost, funding and commercial considerations remain appropriately aligned throughout the commission.

The Stage Services described in Appendices 1A and 1B are indicative and are intended to provide a common basis for tendering, pricing and delivery of the Services. The successful Tenderer(s) shall provide all professional services reasonably required for the proper delivery of the commission, whether specifically described or necessarily incidental to achieving the objectives of the Project.

Subject to project progression, funding availability, the Contract and applicable public procurement requirements, the Contracting Authority may require continued professional services associated with subsequent project stages.

## A. Project Manager Stage Services

This Appendix sets out the indicative Project Management Services to be provided under Lot 1 – Project Management Services during the RRDF Category 2 phase.

The services are intended to provide a common basis for tendering, pricing and delivery. The Project Manager shall provide all services reasonably required for the proper delivery of the commission.

Subject to project progression, funding availability, the Contract and applicable public procurement requirements, the Contracting Authority may require continued professional services associated with subsequent project stages.

Stage 1A – Project Establishment and Project Initiation

Objective

To establish the governance, programme, procurement strategy and project management arrangements necessary to successfully commence the Project.

Principal Services

The Project Manager shall provide services including, but not limited to:

- Project mobilisation and establishment of governance arrangements.

- Confirmation of project objectives, scope and delivery strategy.

- Development of the overall Project Programme.

- Establishment of project reporting procedures.

- Development of the initial Risk Register.

- Procurement planning for the Architect-led Single Point Design Team (SPDT).

- Early stakeholder and community engagement planning.

- Coordination with the Contracting Authority and ICC.

Key Deliverables

- Project Mobilisation.

- Project Governance Framework.

- Project Programme.

- Procurement Strategy.

- Community and Stakeholder Engagement Plan.

- Initial Risk Register.

- Initial Progress Report.

Stage 1B – Procurement and Appointment of the Architect-led SPDT

Objective

To procure and appoint an Architect-led Single Point Design Team in accordance with public procurement requirements.

Principal Services

The Project Manager shall provide services including, but not limited to:

- Preparation of procurement documentation.

- Management of the eTenders process.

- Coordination of tender clarifications.

- Management of tender evaluation.

- Preparation of evaluation reports and recommendations.

- Coordination of SPDT appointment and mobilisation.

- Programme review and governance reporting.

Key Deliverables

- SPDT Procurement Documentation.

- Tender Clarifications.

- Tender Evaluation Report.

- Recommendation for Award.

- SPDT Appointment.

- Updated Project Programme.

- Updated Risk Register.

Stage 2A – Design Development and Project Coordination

Objective

To coordinate the development of the Project design, stakeholder engagement and statutory consultation activities.

Principal Services

The Project Manager shall provide services including, but not limited to:

- Coordination of the Architect-led SPDT.

- Programme management.

- Stakeholder and community engagement.

- Coordination of statutory consultations.

- Coordination with the Quantity Surveyor.

- Monitoring of project risks.

- Governance and reporting.

Key Deliverables

- Design Coordination Reports.

- Stakeholder Engagement Records.

- Statutory Consultation Records.

- Updated Project Programme.

- Progress Reports.

- Updated Risk Register.

Stage 2B – Planning Development

Objective

To coordinate completion of the documentation required to support submission of the planning application.

Principal Services

The Project Manager shall provide services including, but not limited to:

- Coordination of planning documentation.

- Coordination of stakeholder engagement.

- Management of statutory interactions.

- Programme monitoring.

- Governance reporting.

- Preparation for planning submission.

Key Deliverables

- Coordinated Planning Submission Documentation.

- Governance Reports.

- Stakeholder Engagement Records.

- Planning Progress Reports.

- Updated Programme and Risk Register.

Stage 2C – Project Completion and Funding Readiness

Objective

To complete the RRDF Category 2 commission and prepare the Project for progression to a future RRDF Category 1 capital funding application.

Principal Services

The Project Manager shall provide services including, but not limited to:

- Final coordination of project documentation.

- Project close-out activities.

- Final governance reporting.

- Coordination of project records.

- Preparation of documentation supporting future funding readiness.

- Handover of project information to the Contracting Authority.

Key Deliverables

- Final Project Programme.

- Final Governance Report.

- Final Risk Register.

- Project Close-Out Report.

- Project Records and Handover Documentation.

- Documentation supporting future RRDF Category 1 capital funding readiness.

## B – Quantity Surveyor Stage Services

This Appendix sets out the indicative Quantity Surveying Services to be provided under Lot 2 – Quantity Surveying Services during the RRDF Category 2 phase.

The services are intended to provide a common basis for tendering, pricing and delivery. The Quantity Surveyor shall provide all services reasonably required for the proper delivery of the commission.

Subject to project progression, funding availability, the Contract and applicable public procurement requirements, the Contracting Authority may require continued professional services associated with subsequent project stages.

Stage 1A – Project Establishment and Project Initiation

Objective

To establish the commercial framework and cost management approach for the Project.

Principal Services

The Quantity Surveyor shall provide services including, but not limited to:

- Review of available project information and funding parameters.

- Establishment of cost planning methodology.

- Review of project assumptions and commercial risks.

- Advice on budget strategy and affordability.

- Coordination with the Project Manager and Contracting Authority.

- Attend Project Steering Group and project meetings, where required.

Key Deliverables

- Initial Cost Planning Strategy.

- Initial Budget Review.

- Commercial Risk Advice.

- Cost Planning Methodology.

Stage 1B – Procurement of the Architect-led SPDT

Objective

To support procurement through commercial and cost advice.

Principal Services

The Quantity Surveyor shall provide services including, but not limited to:

- Commercial input into procurement documentation.

- Advice on pricing structures.

- Review of pricing requirements.

- Support during tender evaluation where required.

- Commercial advice during appointment of the SPDT.

- Attend Project Steering Group and project meetings, where required.

Key Deliverables

- Commercial Input to Procurement Documentation.

- Pricing Advice.

- Tender Evaluation Support.

- Commercial Recommendations.

Stage 2A – Design Development

Objective

To support design development through robust cost planning and commercial advice.

Principal Services

The Quantity Surveyor shall provide services including, but not limited to:

- Preparation and development of project cost plans.

- Cost advice during design development.

- Value engineering and value-for-money assessments.

- Cost monitoring against available funding.

- Commercial advice to the Project Manager and SPDT.

- Attend Project Steering Group and project meetings, where required.

Key Deliverables

- Cost Plan.

- Cost Reports.

- Value Engineering Recommendations.

- Cost Monitoring Reports.

Stage 2B – Planning Development

Objective

To ensure that the developing design remains commercially robust and aligned with available funding.

Principal Services

The Quantity Surveyor shall provide services including, but not limited to:

- Update project cost plans.

- Review cost implications of design development.

- Advise on affordability.

- Support funding readiness.

- Commercial advice during planning development.

- Attend Project Steering Group and project meetings, where required.

Key Deliverables

- Updated Cost Plan.

- Commercial Advice Reports.

- Funding Cost Information.

- Affordability Assessment.

Stage 2C – Project Completion and Funding Readiness

Objective

To complete the commercial outputs required to support future capital funding.

Principal Services

The Quantity Surveyor shall provide services including, but not limited to:

- Finalisation of cost plans.

- Preparation of funding cost information.

- Final commercial review.

- Support project close-out.

- Handover of commercial records.

- Attend Project Steering Group and project meetings, where required.

Key Deliverables

- Final Cost Plan.

- Final Cost Report.

- Funding Cost Information.

- Commercial Close-Out Report.

- Commercial Handover Documentation.