# Project Brief for the Engagement of Consultancy Services

Monaghan-Blackwater Scheme: Design of Improved Access Infrastructure for Inspection and Maintenance of 22 Sluices

Contents

1.	Project Overview	5

2.	Background to the Scheme	6

2.1 Scheme Overview	6

2.2 Role of Sluices	7

3.	Project Objectives	8

4.	Site Locations	9

SL1	11

SL2	12

SL3	13

SL4	14

SL5	15

SL6	16

SL7	17

SL8	18

SL10	19

SL12	20

SL13	21

SL14	22

SL15	23

SL16	24

SL17	25

SL18	26

SL19	27

SL20	28

SL21	29

SL22	30

SL23	31

SL25	32

5.	Scope of Services (5.1 to 5.5) and Deliverables (5.6 to 5.10)	33

5.1	Stage 1 – Surveys & Preliminary Assessments	33

5.2	Stage 2 – Detailed Design	33-34

5.3	Stage 3 - Detailed Design and Specifications documentation for Tender for construction                                                                                                             34

5.4      Stage 4-Project Supervisor Design                                                                         35

5.5       Stage 5 – Safety File and as constructed drawings                                             35

5.6       Deliverables                                                                                                              36

5.7	Stage 1 – Surveys & Preliminary Assessments 	36

5.8	Stage 2 – Detailed Design 	36

5.9	Stage 3 – Detailed Design and Specifications documentation for Tender for construction 	36-37

5.10     Stage 4-PSDP-Construction                                                                                       37

5.11	Safety File and as constructed drawings 	37

6.	Programme                                                                                                                            38

Version Control

| Version | Date | Description of Changes | Approved By: | Document Control |
| --- | --- | --- | --- | --- |
| D01 | 03.03.2026 |  | Shane Hayes |  |
| D02 | 06.07.2026 |  | Shane Hayes |  |
| D03 | 08.07.2026 |  | Shane Hayes |  |

Change Request/Control

This report has been/not been approved for submission to …...

# Project Overview

Figure 1. Sluices located within the Monaghan Blackwater Scheme.

The Office of Public Works (OPW) invites tenders from suitably qualified consultants to provide design services for improved access infrastructure to 22no sluices (non-return valves) located within the Monaghan Blackwater Arterial Drainage Flood Relief Scheme in Co. Monaghan.

The overall objective is to develop practical, safe and durable access solutions to facilitate inspection and maintenance of the sluices.

# Background to the Scheme

## 2.1 Scheme Overview

The OPW has a statutory responsibility for and carries out a programme of Arterial Drainage Maintenance. These maintenance works relate to arterial drainage schemes completed by the OPW under the Arterial Drainage Acts 1945, with the primary purpose to improve the drainage of agricultural lands.

The OPW’s annual Arterial Drainage Maintenance Works Programme protects 260,000 hectares (650,000 acres) of agricultural lands and comprises 11,500km (7,150 miles) of river channel and approximately 800km (500 miles) of embankments.

The Monaghan Blackwater Scheme falls within the East Region operations of the Arterial Drainage Maintenance section of the OPW. This scheme benefits approximately 5850 acres of land and was completed from 1984-1992. It contains 290km of channels, over 400 bridges and 22 sluices which all require maintenance.

Figure 2. Monaghan Blackwater Scheme Channels.

## 2.2 Role of Sluices

The sluices in the scheme were installed where arterial drainage channels connect to major channels to control the direction of water flow.

Their main purpose is flood protection and efficient drainage. The non-return valve automatically closes when the river level is higher than the drainage channel level to prevent flooding of lands upstream and agricultural land being inundated. When the water level of the drainage channel becomes higher than the river, the flap/gate opens and allows water to drain out naturally.

# Project Objectives

The primary objective of this project is to develop appropriate and practical design solutions to improve access to the 22 sluices within the scheme. Structures designed in 5No batches to facilitate tendering of 4 / 5 access structures works in a phased manner as designs completed. The improved access arrangements will facilitate the safe inspection, operation and maintenance of these structures by OPW personnel.

Following inspections carried out in 2025, the existing access arrangements to a number of sluices were identified as being inadequate for safe and efficient maintenance activities. Each sluice location was assessed using risk factors including the following:

- Lack of fall protection – an absence of railings or barriers present to protect against fall from heights.

- Deep fall – fall from heights considered very dangerous.

- Ground Conditions - Factors such as the condition and gradient of banks adjacent to sluices taken into account.

The purpose of this project therefore is to develop design proposals that address these deficiencies while taking into account the operational requirements of the scheme and the constraints associated with working within river channels and drainage infrastructure.

The key objectives of the project are:

- Provide safe and reliable access to each sluice for inspection and maintenance purposes.

- Develop practical and cost effective design solutions that are suitable for the local site conditions at each sluice.

- Ensure all proposed access infrastructure is durable, robust and fit for purpose.

- Ensure designs comply with relevant health and safety legislation, engineering standards and environmental requirements.

- Minimise potential environmental disturbance and impacts on surrounding lands and watercourses where possible.

- Produce design documentation that will allow the OPW to procure construction works for access improvements at a later stage.

# Site Locations

The sluices are located in predominantly rural settings and are typically accessed via agricultural lands or tracks. The name and location of each of the 22 sluices included in the scope of this project are outlined in Table 1 below. Photographs and location plans for each sluice are also provided to illustrate the existing site conditions.

Figure 3. Overview of MBW Sluice locations.

| Sluice Name | Channel | Grid Reference | Townland |
| --- | --- | --- | --- |
| SL1 | C1/1/5/14 | 54.2686, -6.9954 | Drumbenagh |
| SL2 | C/1/1/5 | 54.2712, -7.054 | Kilmore |
| SL3 | C1/3 | 54.3240, -6.8887 | Castle Leslie |
| SL4 | C1/3 | 54.3311, -6.8787 | Mullyjordan |
| SL5 | C1/1 | 54.2903, -6.8707 | Sillis |
| SL6 | C1/1/3 | 54.2900, -6.8590 | Annareagh |
| SL7 | C1/1/2 | 54.3115, -6.8581 | White Island |
| SL8 | C1/4 | 54.3385, -6.8756 | Corraghdown |
| SL10 | C1/2 | 54.3295, -6.8644 | Kiltybegs |
| SL12 | C1/3/6 | 54.3332, -6.9511 | Derrygassan Upper |
| SL13 | C1/5 | 54.3496, -6.9000 | Killyrean |
| SL14 | C1/9 | 54.3717, -6.9127 | Figullar |
| SL15 | C1/10 | 54.3763, -6.9154 | Figullar |
| SL16 | C1/111 | 54.3756, -6.9260 | Figullar |
| SL17 | C1/12 | 54.3863, -6.9452 | Kilfahavon |
| SL18 | C1/16 | 54.4137, -7.0154 | Drumartigan |
| SL19 | C1/16/1 | 54.4129, -7.0170 | Drumartigan |
| SL20 | C1/14 | 54.4048, -6.9947 | Aghaderry |
| SL21 | C1/14/1 | 54.4038, -6.9956 | Aghaderry |
| SL22 | C1/14/2 | 54.4013, -6.9929 | Aghaderry |
| SL23 | C1/12/5 | 54.3515, -6.9683 | Knockakirwan |
| SL25 | C1/4 | 54.3378, -6.8792 | Leek |

Table 1. Sluice locations list.

## SL1

Figure 4. SL1 Location map.

Image 1. SL1

## SL2

Figure 5. SL2 Location map.

Image 2. SL2

## SL3

Figure 6. SL3 Location map.

Image 3. SL3

## SL4

Figure 7. SL4 Location map.

Figure 4. SL4

## SL5

Figure 8. SL5 Location map.

Image 5. SL5

## SL6

Figure 9. SL6 Location map.

Image 6. SL6

## SL7

Figure 10. SL7 Location map.

Image 7. SL7

## SL8

Figure 11. SL8 Location map.

Image 8. SL8

## SL10

Figure 12. SL10 Location map.

Image 9. SL10

## SL12

Figure 13. SL12 Location map.

Image 10. SL12

## SL13

Figure 14. SL13 Location map.

Image 11. SL13

## SL14

Figure 15. SL14 Location map.

Image 12. SL14

## SL15

Figure 16. SL15 Location map.

Image 13. SL15

## SL16

Figure 17. SL16 Location map.

Image 14. SL16

## SL17

Figure 18. SL17 Location map.

Image 15. SL17

## SL18

Figure 19. SL18 Location map.

Image 16. SL18

## SL19

Figure 20. SL19 Location map.

Image 17. SL19

## SL20

Figure 21. SL20 Location map.

Image 18. SL20

## SL21

Figure 22. SL21 Location map.

Image 19. SL21

## SL22

Figure 23. SL22 Location map.

Image 20. SL22

## SL23

Figure 24. SL23 Location map.

Image 21. SL23

## SL25

Figure 25. SL25 Location map.

Image 22. SL25

# Scope of Services (5.1 to 5.5) and Deliverables (5.6 to 5.11)

## Stage 1 – Survey, Preliminary Assessments & Concept Design

The consultant shall:

- Review all available existing information provided by the OPW, including inspections records and any relevant drawings and reports.

- Undertake site visits to each of the sluice locations to survey, assess existing site conditions, access constraints and site specific considerations.

- Identify any constraints that may influence the design, such as ground conditions, existing access routes and land use/agricultural activity.

- Develop appropriate concept design options for improved access to each sluice location.

- Consider a range of potential solutions, which may include:

  - Access tracks.

  - Harness attachments.

  - Steps, ladders or platforms.

  - Safety barriers, handrails or gates.

- Ensure that all options:

  - Prioritise health and safety.

  - Are practical and constructible.

  - Are appropriate to the rural and environmental setting they are in.

- Present these concept design to the OPW.

- Prepare drawing/sketch of proposals with estimated cost, for OPW/landowner to review and make comments.

## Stage 2 – Detailed Design

Upon agreement of preferred options, the consultant shall:

- Develop detailed designs for the proposed access improvements at each sluice location in phased manner as set out in the Monaghan-Blackwater Access Structures Design Programme.

- Ensure that design proposals take into account Environmental impacts:

  - Potential impacts on the watercourses.

  - Surrounding land use and habitats.

  - Advise the OPW on any permissions or assessments that may be required to progress the works to constructions stage.

- Prepare all necessary design documentation, which will include:

  - General arrangement drawings.

  - Construction details.

  - Specifications.

  - Any associated schedules or quantities.

- Ensure that all designs comply with relevant health and safety legislation.

- Consider safe access for inspection, operation and maintenance in all design proposals.

- Identify and communicate any residual risks associated with the proposed works.

  - Technically robust and suitable for construction.

  - Proportionate to the scale and complexity of the works.

  - Consistent across locations where deemed appropriate.

- Fulfil all obligations under current Health & Safety legislation. Prepare a Preliminary Health and Safety Plan and develop the Safety File in accordance with Safety, Health & Welfare at Work Act 2005, and Safety, Health and Welfare at Work (Construction) Regulations 2013 and all other relevant legislation, regulations and codes of practice.

## Stage 3 – Construction Tender Documentation – Construction 5No Construction Tenders for Sluice Batches 1, 2, 3, 4 & 5

The consultant shall:

- Prepare documentation suitable for use in the procurement of construction works, as required by the OPW, including, Prelim Health and Safety Plan, detailed design drawings and specifications.

- Be of professional standard suitable for inclusion in public procurement documentation (eTenders & SupplyGov).

- Assist in review of tender returns.

- Transfer the role of PSCS (Project Supervisor Construction Stage) to the successful contractor in accordance with Safety, Health & Welfare at Work Act 2005 and Safety, Health & Welfare at Works (Construction) Regulations 2013 and all other relevant regulations and legislation.

## Stage 4 – Project Supervisor Design Process (PSDP) for Construction of the 22 sluice access structures in Sluice Batches 1, 2, 3, 4 & 5

The consultant shall:

Role as PSDP for the works for all the sluices in Batches 1, 2, 3, 4 & 5

Carry out a supervisory role on behalf of the OPW as PSDP & management of project safety files for the duration of the construction and commissioning of the works to all 22 sluices, including responding to technical queries & clarifications, administration of the contract, approval of all materials, site visits and meetings and certification of works.

## Stage 5 - Safety File and as Constructed Drawings

The consultant shall:

- Completed Safety File for each project/sluice.

- Electronic copy and two A0 hard copies of all as constructed drawings for each structure issued to the OPW.

# Deliverables in 5 No batches of Sluices.			No 1 (sluices 1, 2, 3, 4 &5), 					No2 (sluices 6, 7, 8, 10 & 12), 				No3 (sluices 13, 14, 15 & 16), 				No4 (sluices 17, 18, 19 & 20) and				  No5 (sluices 21, 22, 23 & 25).

## Stage 1 – Survey, Preliminary Assessments & Concept Design

- A Site Assessment Report summarising:

  - Existing site conditions at each sluice.

  - Key constraints and considerations.

  - Photographic records (where required to supplement report).

  - Site specific access issues.

- A Concept Design Drawing/Sketch and Report outlining:

  - Design options considered for each sluice location.

  - Assessment of options (including safety, buildability and cost considerations).

  - Identification of preferred option for each sluice, Draft for OPW review.

## Stage 2 – Detailed Design

- A Detailed Design Package for each sluice location, including:

  - General arrangement drawings.

  - Construction detail drawings.

  - Technical specifications for the proposed works.

  - A cost estimate for proposed access improvements.

## 5.9 Stage 3 – Detailed Design and Specifications Documentation for Construction Tender – Construction 5No Construction Tenders for Sluice Batches 1, 2, 3, 4 & 5

The consultant shall prepare documentation suitable for use in procurement of construction works, such as:

- Drawings of a suitable standard and level of detail to allow works to be tendered and constructed.

- Works information/Technical Specifications.

- Pricing documentation.

- Drawings and supporting information for inclusion in tender documents.

## Stage 4 – Project Supervisor Design Process (PSDP) for Construction of the 22 sluice access structures in Sluice Batches 1, 2, 3, 4 & 5.

The consultant shall manage the safety files and responsible as PSDP to completion of construction of all 22 sluice access structures.

## Stage 5 Safety File and as Constructed Drawings

- Completed Safety File for each project/sluice.

- Electronic copy and two A0 hard copies of all as constructed drawings for each structure issued to the OPW.

- Be submitted in electronic format, including:

  - Reports in PDF format.

  - Drawings in PDF and CAD (dwg) format.

- Be clearly structured and labelled.

- All deliverables shall be subject to review and acceptance by the OPW.

# Programme

- Design works should be completed to programme in table below

| Monaghan-Blackwater Access Structures Design Programme |  |  |
| --- | --- | --- |

|  | Sluices | Draft Design | Detailed Design | Tender Docs/Supplygov | Appointment of contractor | Completion of works |
| --- | --- | --- | --- | --- | --- | --- |
| Batch 1 | 1, 2, 3, 4 & 5 | Sept-26 | Oct-26 | Nov-26 | Jan-27 | May-27 |
| Batch 2 | 6, 7, 8, 10 & 12 | Nov-26 | Dec-26 | Jan-27 | Mar-27 | Jul-27 |
| Batch 3 | 13, 14, 15 & 16 | Dec-26 | Jan-27 | Feb-27 | May-27 | Aug-27 |
| Batch 4 | 17, 18, 19 & 20 | Feb-27 | Mar-27 | Apr-27 | Jun-27 | Dec-27 |
| Batch 5 | 21, 22, 23 & 25 | Mar-27 | Apr-27 | May-27 | Jul-27 | Jan-28 |

- The consultant shall submit a detailed programme as part of their tender submission, outlining how they propose to deliver the services within specified timeframes.

- The programme should aim to the project programme and include for:

  - Ongoing liaison with the OPW.

Timely completion of deliverables to facilitate progression to construction procurement.