## Summary
Prelims - Heating Upgrade
Code | Description | Total
| (00) PRELIMINARIES | 0
| TOTAL | 0

## 4-00 PRELIMINARIES
(00) PRELIMINARIES
Code | Description | Quantity | Unit | Rate | Total
| PRELIMINARIES (HEATING UPGRADE) |  |  |  | 0
| NOTES: |  |  |  | 0
| 1. All items shall be deemed to include full compliance with the Public Works Contract (PW-CF) obligations, including all coordination, supervision, labour, plant, materials, temporary works, overheads and profit. |  | Note |  | 0
| 2. The Contractor shall be responsible for full coordination with the Employer, Works Contractor and ESCO at all interface points. |  | Note |  | 0
| 3. Works are to be undertaken in live operational school environments and shall include all necessary safeguarding, phasing and access control measures. |  | Note |  | 0
| 4. All interface works shall include for coordination with ESCO-provided Energy Cabin systems including isolated and capped pipework connections. |  | Note |  | 0
| 5. No additional payment shall be made for compliance with statutory obligations, contract administration or interface coordination unless expressly stated in the Contract. |  | Note |  | 0
| 1.0 CONTRACT MANAGEMENT & CONTRACTOR’S OBLIGATIONS |  |  |  | 0
| Provide full contract management, coordination, supervision and execution of the Works, including compliance with all obligations under the Public Works Contract (PW-CF), complete | 1 | Item |  | 0
| Attendance at all site meetings, progress meetings, interface meetings and coordination workshops with the Employer, Works Contractor and ESCO | 1 | Item |  | 0
| Preparation, submission and maintenance of the construction programme in accordance with contract requirements | 1 | Item |  | 0
| Coordination and management of all subcontractors, suppliers and specialist installers | 1 | Item |  | 0
| 2.0 DESIGN COORDINATION & INTERFACE MANAGEMENT |  |  |  | 0
| Coordination of all design and installation works with ESCO Energy Cabin supplier including interface compliance with SSRH heat interface requirements | 1 | Item |  | 0
| Review, coordination and integration of all free-issued ESCO design information | 1 | Item |  | 0
| Attendance at interface coordination meetings and joint technical workshops | 1 | Item |  | 0
| Coordination of all service interfaces including isolated and capped pipework provided by ESCO for connection by others | 1 | Item |  | 0
| Resolution of all interface discrepancies between plantroom works and Energy Cabin installation | 1 | Item |  | 0
| 3.0 SITE ESTABLISHMENT & TEMPORARY WORKS |  |  |  | 0
| Site establishment, mobilisation and demobilisation of labour, plant and equipment | 1 | Item |  | 0
| Provision and maintenance of temporary site accommodation, welfare facilities and storage | 1 | Item |  | 0
| Provision of temporary utilities including water, electricity and lighting | 1 | Item |  | 0
| Provision of hoarding, fencing, signage and access control in live school environments | 1 | Item |  | 0
| Temporary protection of existing buildings, services and finishes | 1 | Item |  | 0
| 4.0 HEALTH, SAFETY & ENVIRONMENTAL COMPLIANCE |  |  |  | 0
| Compliance with all statutory Health & Safety legislation including Construction Regulations | 1 | Item |  | 0
| Preparation and implementation of Construction Stage Safety Plan | 1 | Item |  | 0
| Management of works in live school environments including safeguarding measures | 1 | Item |  | 0
| Environmental protection including waste management, noise, dust and vibration control | 1 | Item |  | 0
| 5.0 ACCESS, TEMPORARY WORKS & LIFTING OPERATIONS |  |  |  | 0
| Provision of all lifting operations including cranes, hoists and associated certification | 1 | Item |  | 0
| Temporary works design, installation and removal including access platforms and supports | 1 | Item |  | 0
| Working at height systems including scaffolding and edge protection | 1 | Item |  | 0
| Protection of existing building fabric and services during execution of the Works | 1 | Item |  | 0
| 6.0 INTERFACE WITH ESCO / ENERGY CABIN SYSTEM |  |  |  | 0
| Coordination with ESCO for Energy Cabin installation, commissioning and interface works | 1 | Item |  | 0
| Attendance at joint inspection and witnessing of interface connection works | 1 | Item |  | 0
| Coordination of primary LPHW pipework interfaces including ESCO-provided isolated and capped connections | 1 | Item |  | 0
| Verification and sign-off of all service interfaces including water, electrical and BMS connections at Energy Cabin envelope | 1 | Item |  | 0
| Interface risk management and resolution of coordination issues between ESCO and Works Contractor scopes | 1 | Item |  | 0
| 7.0 QUALITY ASSURANCE, TESTING & COMMISSIONING SUPPORT |  |  |  | 0
| Implementation of quality assurance procedures and inspection & test plans | 1 | Item |  | 0
| Coordination and witnessing of commissioning activities and system testing | 1 | Item |  | 0
| Integration of plantroom commissioning with Energy Cabin commissioning activities | 1 | Item |  | 0
| Compilation and submission of commissioning records and certificates | 1 | Item |  | 0
| 8.0 HANDOVER, DOCUMENTATION & CLOSE-OUT |  |  |  | 0
| Preparation and submission of operation and maintenance manuals in approved format | 1 | Item |  | 0
| Preparation and submission of as-built drawings and record documentation | 1 | Item |  | 0
| Provision of training to Employer’s representatives | 1 | Item |  | 0
| Snagging, rectification and final completion works | 1 | Item |  | 0
| Final account support and contract close-out documentation | 1 | Item |  | 0
| 9.0 OTHER |  |  |  | 0
| Security: Provision and maintenance of site security measures including fencing, hoarding, access control and protection against theft or vandalism, complete. | 1 | Item |  | 0
| Temporary Services: Provision and maintenance of temporary water, electricity, lighting and other site services required for execution of the Works, complete. | 1 | Item |  | 0
| Coordination Meetings: Attendance at all site, design, coordination and progress meetings as required under the Contract, complete. | 1 | Item |  | 0
| Provide for all additional preliminary obligations, attendance, coordination, supervision, temporary works, protections, and any other requirements reasonably inferred as necessary for the proper execution and completion of the Works in accordance with the Contract, whether expressly described or not, deemed included, complete. | 1 | Item |  | 0
| Asbestos Compliance |  |  |  | 0
| Allow for compliance with all asbestos management requirements, including review of asbestos survey information, avoidance of disturbance to identified asbestos-containing materials, implementation of safe working procedures, and coordination with the Employer and specialist asbestos contractors where required, complete. | 1 | Item |  | 0
| Asbestos Discovery Contingency |  |  |  | 0
| The Contractor shall confirm, through pre-start surveys, the absence or otherwise of asbestos-containing materials in areas being disturbed. Where ACMs are identified, a licensed specialist shall be engaged and the works replanned; no disturbance shall occur without a refreshed asbestos register and method statement being in place. | 1 | Item |  | 0
| Before any decommissioning works commence, the Works Contractor shall undertake a pre-decommissioning survey of each affected plantroom. The survey shall record the make, model, age, fuel type, rated thermal output, condition and remaining fuel inventory of each item of plant scheduled for removal, and shall record the routing, support method and condition of any pipework, flues, fuel lines, fuel storage tanks and electrical supplies serving the plant. The survey shall identify any asbestos-containing material in the vicinity of the plant; where such material is identified, decommissioning shall not proceed until a specialist asbestos removal contractor has discharged the Asbestos Regulations 2006 and 2010 in respect of the affected zone. The survey report shall be submitted to the Engineer for review before decommissioning commences. | 1 | Item |  | 0
| Total |  |  |  | 0