Explanatory documents for the employment of
 Consultant Engineer
For Bodyke Group Water Scheme Bodyke Co. Clare Ireland

This tender requested will be to appoint a Consultant Engineer (CE) to deliver the project on behalf of Bodyke PrGWS. The estimated works are to construct an interconnecting main between Scarriff/ Tuamgraney PWS and Bodyke PriGWS including the construction of required pumping stations, and upgrade of Bodyke PriGWS to the minimum basic standards for Uisce Eireann Taking in charge,.
The CE appointed will undertake the Duties and Services for the Works as defined below.  

Duties should include but not be limited to. 
1. Survey of Site to allow for Design Process  
1. Design of upgrade works required to bring the GWS up to the minimum basic standard for Uisce Eireann (UE) Taken in Charge including design of an interconnecting mains to Scarriff/ Tuamgraney PWS . Design to be in accordance with the UE Code of Practise for Water Infrastructure and Basic Standards for Taking in Charge
1. Submission of AF1 to HSA 
1. Liaison with Roads Area Engineer to assess ROL requirements and reinstatement requirements for inclusion in Contract Documents 
1. Delivery of all Planning Permission Requirements 
1. Complete and Satisfy Environmental Screening Requirements. Complete all other reports as necessary (e.g. stability of adjoining walls & buildings, protected structures, archaeological, asbestos, contamination, temporary works design, etc)  
1. Carry out survey of services on site (drainage of chambers, foul & surface water network pipes, existing water mains, ESB, Telecom, Eirgrid, Bord Gais, ESAT, Eircom, Broadband, etc.)  
1. Acceptance of Role as Designer and PSDP and assist the GWS with their requirements under Health and Safety Legislation. 
1. Preparation of wayleaves agreements/ Land Transfer documents as required (Pump station, Reservoir, Network on Third Party Lands, etc) 
1. Preparation of Contract Documents and Publish to E-Tenders including Preliminary Safety and Health Plan. 
1. Excavation, Inspection and Site Investigation of Trial Holes for inclusion in the contract 
1. Ensure that the successful contractor provides all necessary insurance requirements and tax clearance certificates to the GWS 
1. Assessment of Tenders including any potential contract clarifications 
1. Ensure the Contract Documents include: 
· Pricing Document. 
· Design Drawings 
· Works Requirements 
· Any further specification needed. 
1. Preparation of Tender Report and Issue to GWS and CCC with recommendation of appointment, to include but not limited to: 
· Report procedure 
· Summary of Tenders 
· Assessment process 
· Recommendation 
1. Award of Contract to Successful Tender and Issue of Appointments as Contractor and PSCS 
1. Submission of Payment Certificates to GWS  
1. On Site Supervision including supervision of pressure testing of mains. 
1. Allowance for weekly site visit for construction period and any additional visits as required. 
1. Preparation and submission of weekly report 
1. Preparation of Snag List and Ensuring all Items are addressed by Contractor 
1. Submission of Certificate of Substantial Completion and Sign off of Works 
1. Representation on behalf of GWS for any Compensation Events / Post Works Meeting / Final Contract Sum 
1. Preparation and submission to CCC of the full Taking in Charge Documents on behalf of the GWS for forward submission to UE taking in charge consideration including the following:  
· Application Form,  
· Consent Form,  
· Connection Schedule,  
· As-Constructed Drawings (.dxf or .dwg AutoCAD drawings) 
· Wayleave Agreements.




