# Tender and Schedule

for

| The Provision of | Transport Led Multidisciplinary Consultancy Services |
| --- | --- |
| For | Area Based Transport Assessment, District Level Transport Plan and Local Level Transport Plans for Western Side of South Dublin County. |

using the

Standard Conditions of Engagement for Consultancy Services (Technical)

Office of Government Procurement

Conditions of Engagement for Consultancy Services (Technical)

Document Reference FTS 9 v1.10

16 September 2024

© 2024 Office of Government Procurement

Published by: Office of Government Procurement

Department of Public Expenditure NDP Delivery and Reform
Government Buildings
Upper Merrion Street
Dublin 2

# Tender

| To | The Contracting Authority | South Dublin County Council |
| --- | --- | --- |
|  | Address of Contracting Authority | County Hall, Tallaght, Dublin 24, D24 A3XC |
|  | For the attention of | Procurement Officer |
| Date: |  |  |

| Contract | For the provision of | Transport Led Multidisciplinary Consultancy Services |
| --- | --- | --- |
| In relation to | Project title | Area Based Transport Assessment, District Level Transport Plan and Local Level Transport Plans for Western Side of South Dublin County. |

A Dhaoine Uaisle

We have examined and understand the Conditions of Engagement for Consultancy Services (Technical), the completed Schedules A and B (where appropriate), and any other tender information supplied, all as amended by any supplemental information, for the above contract.

Terms used in this tender that are defined in those documents have the same meaning in this tender.  We submit with this tender a detailed breakdown of the tender price (if requested). We offer to provide and complete the Services required on the terms of and in conformity with the documents referred to in the preceding paragraph for:

### the lump sum fee of:

insert amount euro excluding VAT for the entire Commission including all stages of the Area Based Transport Assessment process and the formulation of District Level Transport Plan and Local Level Transport Plans for the Western Side of South Dublin County.

as adjusted in accordance with the contract.

and/or

an overall percentage fee of:

Not Applicable % for the Whole Stage/Stage(s),

together with the rates for Time Charges to be determined in accordance with the provisions of the Invitation to Tender.

The amounts set out in this Form of Tender include for expenses, for any intellectual property rights required and, where the Services include acting as Project Supervisor for the Design Process, Assigned Certifier, or signing of the Design Certificate, any fee for so acting.

Rates for Tendered Time Charges

| Grade | Hourly rate |
| --- | --- |
| Project Director - Minimum 10 years Post Qualification Experience | € |
| Project Manager - Minimum 7 years Post Qualification Experience | € |
| Senior Transport Planner - Minimum 7 years Post Qualification Experience | € |
| Transport Modeller - Minimum 5 years Post Qualification Experience | € |
| Civil/Transport Engineer- Minimum 7 years Post Qualification Experience | € |
| GIS & Technical Drawing Specialist - Minimum 5 years Post Qualification Experience | € |
| Clerical/Administrative Officer- Minimum 3 years Experience | € |
| Senior Public Consultation Specialist - Minimum 7 years Post Qualification Experience | € |
| Public Consultation Specialist - Minimum 5 years Post Qualification Experience | € |
| Senior Quantity Surveyor - Minimum 7 years Post Qualification Experience | € |
| Land Use and Urban Planner- Minimum 7 years Post Qualification Experience | € |
| Senior Consultant in Strategic Environmental Assessment - Minimum 7 years Post Qualification Experience Senior Consultant in Appropriate Assessment- Minimum 7 years Post Qualification Experience Flood Risk Assessment Specialist - Minimum 5 years Post Qualification Experience Graphic Designer - Minimum 5 years Post Qualification Experience Web Designer - Minimum 5 years Post Qualification Experience | € € € € € € |

In consideration of your providing us with the contract documents, we agree not to withdraw this offer until the later of:

- 365 days after the end of the last day for submission of this Tender

- expiry of at least 21 days written notice to terminate this Tender given by us.

Your acceptance of this Tender within that time will result in the Contract being formed between us.

We agree that you are not bound to accept the lowest or any tender you may receive.

We agree that if any contract formed by acceptance of this Tender is determined to be void, voidable, unenforceable, or ineffective, any damages for which you may be liable will not exceed the amount that would have been payable under Clause 14.29 of the Conditions of Engagement on termination under clause 14.9 of the Conditions.

We agree that if, at the date of the Contract formed by the acceptance of this Tender, we have in place Annual Aggregate Insurance:

(a)	we shall monitor the EU and UK market at no longer than yearly intervals to establish whether (i) the Each and Every Insurance, or (ii) better cover than the cover in place at the later of the date of the Contract formed by the acceptance of this Tender or the latest relevant annual renewal, can be obtained at the Increased Premium Rates; and

(b)	if the Each and Every Insurance:

- becomes available to us at the Increased Premium Rates; or

- is not available (or not available to us at the Increased Premium Rates) but better cover than the Annual Aggregate Insurance in place at the later of the date of the Contract formed by the acceptance of this Tender or the latest relevant annual renewal becomes available to us at the Increased Premium Rates,

we shall immediately effect such available cover (subject to having obtained your prior written approval, such approval not to be unreasonably withheld or delayed) and notify you in writing within seven days that we have so effected the cover.

For the purposes of this Tender,

the “Increased Premium Rates” means premium rates that do not exceed 125% of the premium rates payable by us for cover on an annual aggregate basis at the time of the applicable annual renewal PROVIDED THAT any difference between (i) premium rates for cover on an annual aggregate basis and (ii) premium rates for the Required Insurance or better cover than the cover in place at the later of the date of the Contract formed by the acceptance of this Tender or the latest relevant annual renewal (whichever is applicable), is not due to any act, omission, default, claim, notice of claim, negligence or otherwise of or against us;

“Each and Every Insurance“ means professional indemnity insurance on an each and every claim basis at the level set out in the Schedule; and

“Annual Aggregate Insurance” means professional indemnity insurance on an annual aggregate basis at the level set out in the Schedule.

Is sinne, le meas,

| Signed on behalf of |  |
| --- | --- |
| Name of Tenderer |  |
| Signature of authorised person |  |
| In the presence of |  |
| Signature of witness |  |
| Name of witness |  |
| Witness’s occupation |  |
| Witness’s address |  |

OR (If the Tenderer is an individual)

| Signed by |  |
| --- | --- |
| Signature of Tenderer |  |
| Name of Tenderer |  |
| In the presence of |  |
| Signature of witness |  |
| Name of witness |  |
| Witness’s occupation |  |
| Witness’s address |  |

STANDARD CONDITIONS OF ENGAGEMENT

FOR CONSULTANCY SERVICES (TECHNICAL)

SCHEDULES

SCHEDULE A: CONTRACT PARTICULARS

##### INTERPRETATION

The Agreement is organised in elements, by individual numbers and line breaks, and titled groups, within each clause. One purpose is to identify clearly which contents go together as part of the same element, especially which qualifications, modifications and exceptions apply to what, and the relationships between elements.

Element numbers provide precise references, They are preceded by clause numbers in larger font except where the reference is in and to the same clause [e.g.‘1, 5,6,7’ in clause 2.4, but ‘7‘ alone in 2.10].

Instead of including ‘and’ or ‘or’ where either would cause ambiguity, commas are used between contents of an element, and semi-colons between elements in a sentence (with indenting where convenient for listing them), to show that they apply individually and together as relevant to the subject.

Square brackets are included where useful to identify as such clarifications, explanations, reminders of purposeful implications or of general law, and cross-references, to show that significance is not to be given to their absence elsewhere, or in the case of general law that it is not being changed.

In the Agreement, Schedules, except where the context indicates, words in the singular include the plural and the reverse.

1. APPOINTMENT

1 Client, Consultant, Contact Details

|  | Client |
| --- | --- |
| Name | South Dublin County Council |
| Telephone | 01 4149000 |
| Mobile |  |
| Email |  |

|  | Client’s Representative |
| --- | --- |
| Name |  |
| Telephone |  |
| Mobile |  |
| Email |  |

|  | Consultant |
| --- | --- |
| Name |  |
| Telephone |  |
| Mobile |  |
| Email |  |

|  | Consultant’s Representative |
| --- | --- |
| Name |  |
| Telephone |  |
| Mobile |  |
| Email |  |

2 Project

Transport Led Multidisciplinary Consultancy Services -Area Based Transport Assessment, District Level Transport Plan and Local Level Transport Plans for Western Side of South Dublin County.

7 Whole, parts, of other documents included in the Contract

1. Letter of Acceptance 2. Pricing Schedule 3. Service Requirements - Standard Conditions of Engagement for Consultancy Services (Technical) including Schedules A & B. - Tenderer's submission including fee breakdown. - Tender Queries and Responses (if any) considered relevant - Post tender clarifications and Responses (if any) considered relevant - Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) - Instruction to Tenderers - Tender Submission documents

2. PERFORMANCE

12 Consultant has no authority –

| to make any Change Order with an extra value above: | € N/A exclusive of VAT |
| --- | --- |
| to make Change Orders in any three month period with a cumulative extra value above: | € N/A exclusive of VAT |
| any Change Order causing or contributing to a reduction in safety, quality, usefulness, of the Project. to waive any of the Client’s rights or the Contractor’s obligations under a Project construction contract without limitation to notice periods such as those set out in sub-clause 10.3 of the Public Works Contracts (PW-CF1 to PW-CF5). |  |
| Claims from the Consultant/Consultancy Team for additional fees or costs over runs will not be paid by the Client in instances where the Client was not given prior notice and did not give prior written approval in the form of a signed Change Order. . |  |

17 Limit of Liability

| The Liability Cap is: | € For insured risks, the relevant indemnity limits for insurance as required in respect of this contract and, in respect of uninsured risks, €1,500,000 or any higher monetary amount stated here /One million five hundred thousand( euro) |
| --- | --- |
| The Liability Cap shall not apply to any claim, loss, damage, cost, expense or liability relating to - death, personal injury or illness; - fraud or fraudulent misrepresentation; - wilful default; - gross negligence; - third party property; - sub-clause 13.26 of this Agreement; or - any liability which the Consultant cannot lawfully exclude or limit. |  |

19 Insurance types, terms

| COVER | Minimum cover | Permitted deductible each and every occurrence | Period |
| --- | --- | --- | --- |
| Annually renewable Professional Indemnity policy, against liability for losses due to professional negligence. The conditions provide for claims for breach of professional duty or civil liability as well as negligence. The jurisdiction in which claims can be lodged and settled includes IRELAND | Each and every claim or series of claims arising out of the same originating cause €1,250,000 OR Per claim and limited in the Annual Aggregate € | 2.0% of gross fee turnover, or €5,000 whichever is greater | From start to completion of the Services; and six years from certified execution subject to reasonable adjustment of cover for any exceptional increases in insurance market rates. |
| Public Liability for death, personal injury [except EL, next type]; loss of, damage to, property; with indemnity to the Client as principal | € 6.5 | € None | From start to completion of the Services. |
| Employers’ Liability for death, injury, to employees | € 13,000,000 | None | From start to completion of the Services. |
| Insurance of plans, documents | € N/A | None | From start to completion of the Services. |

25 Key Team Members

Key Team Members are the members of the Consultant’s team that are named in the Consultant’s tender submission for the Services and/or named in the Consultant’s suitability assessment questionnaire response for the Services, as applicable.

##### 7. COORDINATION

5 Facilities from the Client

N/A

6 Client’s resident staff

N/A

11 Team Leader

The Consultant  team leader.

##### 9. PAYMENTS

13 Inflation Adjustment

First Adjustment Date means for any element of the Fee that is

- a Lump Sum [by Schedule B only, not by conversion under 9.11,12], the date that is the Base Date;

- based on Tendered Time Charges, the date that is the Base Date;

- a Lump Sum [by conversion under 9.11,12 only] the date that is the later of:

  - the Base Date; or

  - the Percentage Fee Conversion Date;

- a percentage applied under 9.7,8 the date that is the later of:

- the Base Date; or

- the Percentage Fee Application Date.

Base Date means the date that is the first day of the 25th month falling after the date that is 10 days before the last date of receipt of the Consultant’s tender for the Services, or, if there was none, 10 days before the Client received the Consultant’s tender for the Services.

Calculated Time Charges means Time Charges that are calculated by the Client in accordance with Section 5.5 (Pricing) of the Instructions to Tenderers for Consultancy Services using a formula to calculate hourly rates and carrying a document reference of ITT-S1a or ITT-S2a, as applicable. Calculated Time Charges shall only apply where ITT-S1a or ITT-S2a was used in the tender for the Contract.

COE Fee Adjustment Factor is the figure for a Relevant Quarter in an Indexation Year published on the constructionprocurement.gov.ie [or any successor] website.

Indexation Year means a period of a year with the first Indexation Year being the period starting on the First Adjustment Date and ending on the day before the anniversary of the First Adjustment Date; for each subsequent Indexation Year it shall be the period of a year from the last anniversary of the First Adjustment Date and ending on the day before the next anniversary.

Percentage Fee Application Date means the date upon which the Client applies a Scheduled Percentage for the Total Fee under 9.7,8.

Percentage Fee Conversion Date means the date upon which the Client converts a Scheduled Percentage Total Fee to a Lump Sum Fee under 9.11,12.

Quarter means a period of 3 months ending on 31 March, 30 June, 30 September or 31 December in any calendar year.

Relevant Quarter means the Quarter in which a First Adjustment Date occurs.

Tendered Time Charges means Time Charges tendered by the Consultant in accordance with Section 5 (Pricing) of the Instructions to Tenderers for Consultancy Services using tendered hourly rates and carrying a document reference of ITT-S1b or ITT-S2b, as applicable. Tendered Time Charges shall only apply where ITT-S1b or ITT-S2b was used in the tender for the Contract.

##### 10. DEBTS TO CLIENT

4	Interest

The rate of interest payable on Client’s wrongful deduction is 0.00% p.a.

##### 12. BUDGETARY CONTROL

2	Excess Percentage

'Excess Percentage' means the percentage [if any] in excess of N/A% of the tendered amount accepted by the Client for the Project construction by which that amount is above or below the last estimate approved by the Client before giving permission to start Stage (iii).

##### 13. INTELLECTUAL PROPERTY etc

11 Assignment

There    assignment to the Client instead of a licence.

| Document, design or deliverable | All material produced by the Consultancy Team aswell as third party service providers during the lifetime of this Commission including all mathematical models, transport modelling data, survey data, drawings (including GIS and dwg files), documents and graphic design material (logos, templates, images, infographics, colour schemes, webpage content, survey and public consultation display material) etc. |
| --- | --- |

14 Licence

Client may use Consultant’s design etc. for –

Individual projects:; All and any.. Types of project:; All and any..

15 Fees [if any]

The only fees payable by the Client for its rights under this clause are: n/a.

18 Publicity

Consent to publicity is required from .

##### 14. TERMINATION

9 Scheduled termination events

The following are Scheduled termination events:

- Where the Contract is subject to Statutory Instrument 284 of 2016 European Union (Award of Public Authority Contracts) Regulations 2016 or Statutory Instrument 286 of 2016 European Union (Award of Contracts by Utility Undertakings) Regulations 2016 and:

- the Consultant has, at the time of Contract award, been in one of the situations referred to in Article 57(1) of SI 284 of 2016 and, in the opinion of the Employer, should therefore have been excluded from the procurement procedure; or

- the Contract should not have been awarded to the Consultant in view of a serious infringement of the obligations under the Treaties and Directives 2014/24/EU or Directive 2014/25/EU that has been declared by the Court of Justice of the European Union in a procedure pursuant to Article 258 of the Treaty on the Functioning of the European Union; or

- in the opinion of the Employer, the Contract has been subject to a substantial modification which would have required a new procurement procedure pursuant to Regulation 72 of SI 284 of 2016 or Regulation 97 of SI 286 of 2016; or

- the Consultant (or its or sub consultant(s), if any) falls within the category of prohibited economic operators identified in Regulation (EU) No 833/2014 of 31 July 2014 (as amended by EU Regulation 2022/576 amending Regulation (EU) No 833/2014 concerning restrictive measures in view of Russia’s actions destabilising the situation in Ukraine or any subsequent amendments to same).

- Any breach of clause 2.22,23 Corrupt Gifts or the commission of any offence by the Consultant, any subcontractor, agent or employee under the Criminal Justice (Corruption Offences) Act 2018. [Without affecting its other rights], the Client shall be entitled to recover from the Consultant the amount or value of any gift, consideration or commission.

In this Form of Tender and Schedule, the reference to “Treaties” means the Treaty on European Union, the Treaty on the Functioning of the European Union, the Treaty establishing the European Atomic Energy Community and the Charter of Fundamental Rights of the European Union.

30 Payment where Client terminates at will

Where the Client terminates Services at will although the Project is continuing, the Consultant is entitled to 0.00% of the difference between the Fees payable under clause 14.27 [without any apportionment under 14.28], and the total fee that would, as estimated at termination, have been payable on completion of the Services for the last Stage in or after which the termination occurred.

##### 16. DISPUTES

1 Initial resolution method

Any dispute or difference arising out of or in connection with this Agreement shall, in the first instance, be referred for conciliation to the Conciliator to be agreed between the Parties in dispute. In the event that such Parties are unable to agree on a Conciliator then the matter shall be referred to the Chairman for the time being of the Chartered Institute of Arbitrators, Irish Branch, who shall appoint the Conciliator. The IEI Conciliation Rules shall govern the conciliation

4 Nominator

In default of agreement, an arbitrator, conciliator or other for 16.1, will be nominated at the request of either party by the following person[s]: President of Engineers Ireland

In default of agreement an adjudicator, under the Construction Contracts Act 2013, will be appointed at the request of either party by the Chairperson of the Panel of Adjudicators.

5 Rules

The applicable Rules are the following published for use with these Standard Conditions of Engagement:

In the case of Arbitration, the arbitration rules are the Capital Works Management Framework (CWMF) Arbitration Rules for use with Public Works and Construction Services Contracts (AR1) published on http://constructionprocurement.gov.ie/arbitration-rules/ on the date 10 days before the latest date for submission of Tenders for this contract (disregarding any amendments posted on that date).

SCHEDULE B: CONSULTANT’S SERVICES AND FEES

##### CONSULTANT’S STAGE SERVICES

The Consultant’s appointment is for   as tabled below.

##### PSDP SERVICES

Performance of all the duties of Project Supervisor for the Design Process  included in the Services as tabled below [and the Stage Fees].

##### Assigned Certifier sERVICES

Performance of all the duties of Assigned Certifier under the Building Control (Amendment) Regulations 2014  included in the Services [and the Stage Fees].

##### Design Certificate SERVICES

The Consultant  required to sign the Design Certificate in accordance with the Building Control (Amendment) Regulations 2014.

##### TOTAL FEE [9]

##### STAGE SERVICES

|  | BASELINE ASSESSMENT & REPORT/ISSUES PAPER: Refer to Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for more details on Milestonesand full list of services and deliverables sought. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stage services | Performance Period from permission to start [4.4] () | Milestones (if any) | Percentage of Total Fee for Stage | Stage Fee | Percentage of Stage Fee for suspension [4.18,19] |
| Stage I Baseline Assessment | Approx. 16 weeks (Total) | See milestones and approx. performance period for each Stage I Milestone and associated Milestone payments below. | Approx. 10% of total lump sum fee | To be detailed in reponse to Award Criteria | N/A |
| “ | Approx. 8 weeks | Baseline Report/Issues Paper | To be detailed in response to Award Criteria |  |  |
| “ | Carry out parallel to Baseline Report | Detailed Stakeholder Management Plan and Public Consultation Strategy. | To be detailed in response to Award Criteria |  |  |
| “ | Carry out parallel to Baseline Report | SEA Pre-Screening Considerations Report | To be detailed in response to Award Criteria " |  |  |
| “ | Carry out parallel to Baseline Report | AA Pre-Screening Considerations Report | To be detailed in response to Award Criteria |  |  |
| “ | In parallel to prior milestones plus approx. 8 weeks | Public Consultation and Report | To be detailed in response to Award Criteria |  |  |

##### STAGE SERVICES

|  | CONTEXT: Refer to Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for more details on Milestones and full list of services and and full list of services and deliverables sought. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stage services | Performance Period from permission to start [4.4] () | Milestones (if any) | Percentage of Total Fee for Stage | Stage Fee | Percentage of Stage Fee for suspension [4.18,19] |
| STAGE II: CONTEXT | Approx. 20 weeks (Total) | See milestones and approx. performance period for each Sub-Stage Milestone and associated Milestone payments below. | Approx. 10% of total lump sum fee % | To be detailed in reponse to Award Criteria | N/A% |
| Sub-Stage (ii a) Establish Context for ABTA/LTPs: |  |  |  |  |  |
|  | Carry out parallel to Future Scenarios Report | Statement of Principles and Objectives. | To be detailed in response to Award Criteria |  |  |
|  | Approx. 4 weeks | Future Scenarios Report | To be detailed in response to Award Criteria |  |  |
|  | Approx. 4 weeks | Demand Analysis Report | To be detailed in response to Award Criteria |  |  |
| Sub-Stage (ii b) Options Development |  |  |  |  |  |
|  | Approx. 4 weeks | Options Development Document | To be detailed in response to Award Criteria |  |  |
|  | In parallel to prior milestones plus approx. 8 weeks | Public Consultation & Report | To be detailed in response to Award Criteria |  |  |
| Sub-Stage (ii c) |  |  |  |  |  |

##### STAGE SERVICES

|  |  |  | NETWORK DEVELOPMENT & ASSESSMENT: Refer to Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for more details on Milestones and full list of services and deliverables sought.. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Stage services | Performance Period from permission to start [4.4] () | Milestones (if any) |  | Percentage of Total Fee for Stage | Stage Fee | Percentage of Stage Fee for suspension [4.18,19] |
| STAGE III: NETWORK DEVELOPMENT & ASSESSMENT | Approx. 36 weeks (Total) | See milestones and approx. performance period for each Sub-Stage Milestone and associated Milestone payments below. |  | Approx. 30% of total lump sum fee | To be detailed in reponse to Award Criteria |  |
| Sub Stage IIIA - Screening of Long List Options | Approx. 4 weeks | Updated Options Development Document |  | To be detailed in response to Award Criteria |  |  |
| Sub Stage IIIB - Package Land Uses and Transport Options | Approx. 12 weeks | Future Year Scenarios Document |  | To be detailed in response to Award Criteria |  |  |
| Sub Stage IIIC - Assessment of Transport Measures | Approx. 10 weeks | Scenarios Assessment Document |  | To be detailed in response to Award Criteria |  |  |
| " | Carry out parallel to Stage III Milestones | SEA Screening Report (if determined to be required under Stage I) and SEA Scoping Report |  | To be detailed in response to Award Criteria |  |  |
| " | Carry out parallel to Stage III Milestones | AA Screening Report. |  | To be detailed in response to Award Criteria |  |  |
|  | In parallel to prior milestones plus approx. 10 weeks | Public Consultation & Report |  |  |  |  |

STAGE SERVICES

|  |  | DRAFT LOCAL TRANSPORT PLANS (LTPs): Refer to Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for more details on Milestones and full list of services and deliverables sought. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Stage services | Performance Period from permission to start [4.4] () |  | Milestones (if any) | Percentage of Total Fee for Stage | Stage Fee | Percentage of Stage Fee for suspension [4.18,19] |
| STAGE IV: DRAFT LTPs | Approx. 42 weeks total |  | See milestones and approx. performance period for each Stage IV Milestone and associated Milestone payments below. | Approx. 35% of total lump sum fee | To be detailed in reponse to Award Criteria |  |
| " | Approx. 2 weeks |  | Update Scenarios Assessment Document. | To be detailed in response to Award Criteria |  |  |
| " | Approx. 14 weeks |  | Draft District Level LTP & Implementation Plan | To be detailed in response to Award Criteria |  |  |
| " | Approx. 16 weeks |  | Draft Local Level LTPs & Implementation Plan(s) | To be detailed in response to Award Criteria |  |  |
| " | Carry out in parallel with LTPs |  | Environmental/SEA Report(s) | To be detailed in response to Award Criteria |  |  |
| " | Carry out in parallel with LTPs |  | AA Screening Report(s) | To be detailed in response to Award Criteria |  |  |
| " | In parallel to prior milestones plus approx. 10 weeks |  | Public Consultation & Report | To be detailed in response to Award Criteria |  |  |

##### STAGE SERVICES

|  |  | Finalise LTPs: Refer to Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for more details on Milestones and full list of services and deliverables sought.. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Stage services | Performance Period from permission to start [4.4] () |  | Milestones (if any) | Percentage of Total Fee for Stage | Stage Fee | Percentage of Stage Fee for suspension [4.18,19] |
| STAGE V: FINALISE LTPs | Approx. 18 weeks total |  | See milestones and approx. performance period for each Stage V Milestone and associated Milestone payments below. | Approx. 15% of total lump sum fee | To be detailed in reponse to Award Criteria |  |
| " | Approx 6 weeks |  | Material Alterations Document(s) | To be detailed in response to Award Criteria |  |  |
| " | Carry out in parallel with Material Alterations Doc(s) |  | Update/revise Environmental Report(s) | To be detailed in response to Award Criteria |  |  |
| " | Carry out in parallel with Material Alterations Doc(s) |  | Update/revise AA Screening(s) | To be detailed in response to Award Criteria |  |  |
| " | In parallel to prior milestones plus approx. 8 weeks |  | Public Consultation & Report | To be detailed in response to Award Criteria |  |  |
| " | Approx. 4 weeks |  | Finalise District and Local LTPs | To be detailed in response to Award Criteria |  |  |
| " | In parallel with finalisation of District and Local LTPs |  | Finalise SEA Statement(s) | To be detailed in response to Award Criteria |  |  |

Details of stage services referred to above

A summary of the Stage Services, which are further detailed in the accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) is as follows: ## Stage 1: Baseline Assessment and Report/Issues Paper Review the Indicative Study Area to confirm a Study Area Boundary and, from transport demand perspective, its Area of Influence etc. Carry out baseline analysis to establish the characteristics of the Study Area and its Area of Influence, in terms of transport demand / demand patterns, mode split, transport infrastructure/services and land uses (trip generators and tip attractors) etc. Review the boundaries for the Study Area and Area of Influence in an iterative manner before apportioning the Study Area for the formulation of Local Level LTPs. Undertake an AA and SEA Pre-Screening exercise and capture in a SEA and AA Pre-Screening/Considerations Reports. Draft and agree a Detailed Stakeholder Management Plan and Public Consultation Strategy, before carrying out public consultation on a Baseline Report/Issues Paper and capturing outcome in a Public Consultation Report. ## Stage 2: Context #### Stage 2a: Establish Context for the ABTA/LTPs Establish Transport Planning Principles and SMART Objectives and capture in a Statement of Principles and Objectives. Establish future land use scenarios within the Area of Influence for a minimum of two future forecast years and forecast future Transport Demand and Travel Demand Patterns, before capturing in a Future Scenarios Report and Demand Analysis Report. #### Stage 2b: Options Development Develop a long list of options/measures for different modes of transport in the Study Area in a manner that seeks to satisfy the established future Transport Demand and Travel Demand patterns for future forecast years. Review against Transport Planning Principles and SMART objectives to identify measures for assessment at the next stage of the commission. Identify Interim Measures from long list of options that have already been included in wider transport investment plans and programmes. Capture in an Options Development Document. Carry out public consultation on the Statement of Principles and Objectives, Demand Analysis Report and Options Development Document and capture in a Public Consultation Report. ## Stage 3: Network Development & Options Assessment #### Stage 3a: Screening of Long List Options Further screen Long List of Options and any additional feasible measures on foot of Stage 2 Public Consultation before updating and refining list of Emerging Preferred Transport Options in an Updated Options Development Document to be brought forward for further analysis. #### Stage 3b: Packaging of Transport Options Bring together forecasted land uses with emerging preferred transport and demand management measures/options to identify and test demand and supply scenarios for the Agreed Future Years. Package into a Future Year Scenarios Document. #### Stage 3c ABTA: Assessment of Transport Measures Carry out assessment of the Supply Scenarios using Multi Criteria Analysis, present results in the form of a performance matrix and identify Preferred Supply Scenario for each Agreed Forecast Year. Capture in a Scenarios Assessment Document. Carry out and prepare SEA Screening Report (if determined to be required under Stage 1) and SEA Scoping Report including necessary statutory consultations. Carry out and prepare AA Screening Report. Carry out public consultation on Updated Options Development Document; Future Year Scenarios Document; Scenarios Assessment, SEA Screening Report, SEA Scoping Report, AA Screening Report and on any additional assessments carried out as additional deliverables outside the lump sum fee/tender price for this commission. Capture outcome in a Public Consultation Report. ## Stage 4: Draft LTPs Review and update the Scenario Assessment Document, on foot of public consultation, and utilise to formulate 1 no. Draft District Level LTP for the Study Area, which shall focus on strengthening and augmenting transport connections through and between centres of activity and settlements in the form active travel, public transport and roads infrastructure and services. Translate and distil into a series of supporting Draft Local Level LTP’s (approx. 4 no.), which should integrate with and augments the District Level LTP by way of strengthening and connecting district level transport measures with local transport connections within centres of activity and settlements in the form of active travel, public transport and roads infrastructure and services. Support District Level and Local Level LTPs with an Implementation Plan(s) that includes details regarding costings, phasing and mechanisms for delivery of transport infrastructure / services including financial requirements. Draft Environmental/SEA Report(s) and update/finalise AA Screening Report(s). Carry out public consultation on LTPs, Environmental Report and AA Screening Report before capturing in a Public Consultation Report as well as on any additional assessments carried out as additional deliverables outside the lump sum fee/tender price for this commission. ## Stage 5: Finalise LTPs Identify material and non-material alterations for Draft LTPs from Stage 4 Consultation. Prepare and carry out Public Consultation on a Material Alterations Document(s) and any revised/updated Environmental Report(s) and AA Screening(s). Finalise LTPs and SEA Statement(s) after final consultation. Note: The above summary of stage services must be read in conjunction with the accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026), which provides further details of the stage services, milestones and deliverables.

| Project Supervisor for the Design Process Services | Performance period |  |
| --- | --- | --- |
| All the duties of Project Supervisor for the Design Process according to the Safety, Health and Welfare (Construction) Regulations 2013, notwithstanding any inconsistent Contract contents. | While required for these Services [subject to any later appointment, earlier clause 14 Termination, by the Client]. | No additional payments |

##### TIME CHARGES

The following Tendered Time Charges apply to suspension [4.21], Client’s Changes [clause 11] (unless the Time Charges are Calculated Time Charges, in which case Calculated Time Charges apply)

| Grade | € per hour (exclusive of VAT) |
| --- | --- |
| N/A |  |

##### MANAGEMENT SERVICES

[Included in Stage Services as relevant, and in the Total Fee and Stage Fees]

| Reporting |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Timing of Report related Management Services to be included in the Total Fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Content of Report related Management Services to be included in the Total Fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Method of Report related Management Services to be included in the Total Fee and Stage Fees. |

| Transfers [3] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Timing of Transfers to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Content of Transfers to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Method of Transfers to be included in in the Total fee and Stage Fees. |

| Communications [6] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Timing of Communications to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Contents of Communications to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Contents of Communications to be included in the Total fee and Stage Fees. |

| Coordination [7] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Timing of Management Services to be included in the Total fee and Stage Fees.. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on tManagement Services to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Method of Management Services to be included in the Total fee and Stage Fees. |

| Cooperation [8] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Timing of Cooperation related Management Services to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on Cooperation related Management Services to be included in the Total fee and Stage Fees. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on Cooperation related Management Services to be included in the Total fee and Stage Fees. |

| Payments [9] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) and above Stage Services Tables for details on the Timing of Payments to be included in the Total fee and Stage Fees. |  |  |

| Client’s Changes [11] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for the prescribed approach to any Client Changes. |  |  |

| Termination [14] |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) and Conditions of Engagement for precibed approach on termination. |  |  |

| Alerts, Follow up |  |  |
| --- | --- | --- |
| Timing | Contents | Method |
| Conflict of Interest [2.29] | Details of Conflict of Interest- Full details of the conflict of interest or potential conflict of interest together with any further information which the Client may require [including any steps proposed to manage the conflict or potential conflict]. | See accompanying Brief for Transport Led Multidisciplinary Consultancy Services (SDCC, July 2026) for details on the Method for informing the Cient of any Conflict of Interest. |

Completed by the Client

If no sum is stated, the applicable amount is €1,500,000 (one million, five hundred thousand euro)

The Each and Every Insurance for the purpose of the Tender

The Annual Aggregate Insurance for the purpose of the Tender

If no rate of interest is specified, the European Central Bank main refinancing rate (‘ECB’) plus eight percentage points (ECB+8%) shall apply.