Project Brief

Tender for the appointment of an Architect-led Integrated Design Team Services for Refurbishment and Upgrade Works at ERC Offices, DCU St Patrick's Campus, Drumcondra, Dublin 9

1. Introduction	3

2. Project Background	4

3. Project Description	5

3.1 Proposed Scope of Works	5

3.2 Project Objectives	6

4. Integrated Design Team and Scope of Services	8

4.1 Main Service Providers – Integrated Design Team	8

4.2 Specialist Services	11

4.3 Additional Specialist Services	12

4.4 Integrated Design Team Coordination	13

5. Scope of Services	14

5.1 Review of Existing Information	14

5.2 Design Development	14

5.3 Statutory Compliance and Approvals	15

6. Project Governance	19

7. Communications and Reporting	20

8. Health & Safety (PSDP)	21

9. Quality Assurance and Information Management	22

10. Statutory Compliance	23

11. Project Programme	24

12. Deliverables	25

12.1 Design & Coordination Documents	25

12.2 Statutory & Compliance Documentation	25

12.3 Procurement & Technical Documentation	25

12.4 Construction Stage Services Documentation	26

12.5 Handover & Completion Documentation	26

13. General Requirements	27

## 1. Introduction

ERC intends to appoint an Architect-led Integrated Design Team to support the development and delivery of refurbishment and accessibility upgrade works at ERC Offices, Dublin City University (DCU) St Patrick’s Campus, Drumcondra, Dublin 9.

The successful Tenderer will be required to provide Architect-led Integrated Design Team services from Stage 2b / Stage 2c, as applicable, through statutory approvals, procurement, construction and project completion. The services shall include the coordination of all design disciplines and specialist consultants required for the successful delivery of the project.

The Architect shall act as Lead Consultant and shall undertake the roles of Assigned Certifier and Employer’s Representative for the project.

This document should be read in conjunction with the documents included in the Tender Package and all supporting documentation issued as part of this competition.

The services shall be provided in accordance with the Capital Works Management Framework (CWMF) and the applicable Conditions of Engagement.

## 2. Project Background

ERC occupies existing office accommodation within DCU St Patrick's Campus, Drumcondra, Dublin 9. As part of its ongoing commitment to providing an accessible, functional and inclusive working environment, ERC intends to undertake refurbishment and accessibility upgrade works within the existing accommodation.

The ERC premises are situated on the DCU St Patrick’s Campus. In its capacity as landlord, DCU has the right to review, approve, and provide formal sign-off for all proposed building works, alterations, or other modifications to the premises prior to implementation.

The proposed project comprises defined works to provide kitchen facilities, platform lift access and accessible toilet and shower facilities, together with associated works necessary to facilitate these elements.

Initial design development has been undertaken to establish the scope of the proposed works and to identify the principal accessibility and accommodation requirements. Concept design drawings have been prepared together with an Order of Magnitude Cost Estimate to support the development of the project.

The project will be developed and delivered in accordance with the Capital Works Management Framework (CWMF) and will require the appointment of an Architect-led Integrated Design Team to progress the project from Stage 2b / Stage 2c, as applicable, through statutory approvals, procurement, construction and completion.

The following information is available to the successful Tenderer and shall be reviewed as part of the services:

- Existing and proposed architectural drawings prepared by ODKM Architects;

- Order of Magnitude Cost Estimate Report prepared by Bolger Quantity Surveyors;

- Existing accommodation layouts and building information available to ERC;

- Existing building services information available to ERC;

- Existing fire safety, accessibility and statutory documentation, where available; and

- Existing surveys, investigations and record information available to ERC.

The successful Tenderer shall review all available information and advise ERC regarding any additional surveys, investigations, assessments or specialist reports considered necessary to support the successful delivery of the project.

## 3. Project Description

The project comprises the refurbishment and accessibility upgrade of existing office accommodation at ERC Offices, DCU St Patrick's Campus, Drumcondra, Dublin 9.

The proposed development is intended to improve accessibility, enhance staff facilities and optimise the functionality of the existing accommodation through a coordinated programme of internal alterations and associated building works.

The project will involve the modification of existing accommodation layouts, the provision of improved accessibility infrastructure and associated upgrades to the building fabric and building services systems. The proposed works will be developed within the constraints of an existing operational building and will require careful coordination of design, statutory compliance and construction activities.

The appointed Integrated Design Team will be required to review the existing design information, further develop the design proposals and ensure that the project is delivered in accordance with applicable statutory requirements, programme objectives and budgetary constraints.

### 3.1 Proposed Scope of Works

While the final scope will be developed through the design process, the project is currently anticipated to include the following principal elements:

Accessibility Improvements

The project includes a number of accessibility enhancement measures intended to improve universal access throughout the accommodation.

These measures are anticipated to include:

- Installation of a platform lift to provide accessible movement between the ground floor and first floor. .

- Provision of a wheelchair-accessible shower and WC facility.

Staff Accommodation Improvements

The project includes the reconfiguration and enhancement of existing staff facilities.

These works are anticipated to include:

- Enlargement and refurbishment of staff canteen facilities.

- Associated furniture, fittings and equipment requirements.

Building Fabric Alterations

The project will require alterations to the existing building fabric to facilitate the above accommodation and accessibility improvements.

These works may include:

- Internal demolition and alteration works.

- New partitions and associated building works.

- New doors, glazed screens and associated joinery works.

- Alterations to floor, wall and ceiling finishes.

- Localised structural interventions associated with the accessibility works.

Building Services Modifications

The project will require modifications to existing building services infrastructure to facilitate the above accommodation and accessibility improvements.

These works may include:

- Mechanical services alterations and extensions.

- Plumbing and sanitary services works.

- Electrical services alterations and upgrades.

- Lighting and emergency lighting modifications.

- Fire alarm modifications.

- Associated builders' works and coordination requirements.

### 3.2 Project Objectives

The principal objective of the project is to provide a modern, accessible and functional working environment that supports the operational requirements of ERC while ensuring compliance with applicable statutory requirements.

In delivering the project, the Contracting Authority seeks to achieve the following objectives:

Accessibility

To improve accessibility throughout the accommodation through the provision of appropriate accessibility infrastructure and facilities, ensuring that the building supports inclusive access for all users and complies with relevant accessibility requirements.

Functional Improvement

To improve the functionality, usability and efficiency of the existing accommodation through the reconfiguration of selected spaces and enhancement of staff facilities.

Statutory Compliance

To ensure that the accommodation complies with all applicable statutory requirements, including building regulations, accessibility requirements, fire safety requirements and other relevant regulatory obligations.

Quality and Value for Money

To deliver a high-quality design solution that represents value for money and is appropriate to the scale, budget and operational requirements of the project.

Sustainability

In Line with the ERCs climate action roapmap (here) to  incorporate appropriate sustainability considerations within the design development process, including energy efficiency, durability, maintainability, responsible material selection and whole-life value principles where appropriate.

Delivery and Coordination

To ensure that the project is developed and delivered through a coordinated multidisciplinary design approach that effectively manages programme, risk, statutory approvals and procurement requirements.

## 4. Integrated Design Team and Scope of Services

ERC intends to appoint an Architect-led Integrated Design Team (IDT) to support the development, coordination and delivery of the project from Stage 2b / Stage 2c, as applicable, through to completion.

The Integrated Design Team shall be responsible for the management and coordination of all design disciplines and specialist services required for the successful delivery of the project and shall ensure that the project is developed and delivered in accordance with the Capital Works Management Framework (CWMF), applicable statutory requirements, recognised professional standards and the requirements of this project brief.

The Architect shall act as Lead Consultant and shall be responsible for the overall management and coordination of the Integrated Design Team throughout the duration of the project. The Architect shall also undertake the roles of Assigned Certifier and Employer’s Representative, where required, and shall provide all associated contract administration, certification, coordination and reporting services necessary for the effective administration and delivery of the project.

The Integrated Design Team shall ensure that all architectural, structural, building services, fire safety, accessibility, statutory compliance and contract administration requirements are appropriately integrated into the design development process and reflected within all project deliverables.

### 4.1 Main Service Providers – Integrated Design Team

The Integrated Design Team shall include the following Principal Service Providers:

Architect (Lead Consultant)

The Architect shall act as Team Lead and shall be responsible for the overall coordination, management and delivery of the services. The Architect shall also undertake the roles of Assigned Certifier and Employer’s Representative, where required, for the effective administration and delivery of the project.

The Architect shall include, but not be limited to:

- Leading and coordinating all design disciplines and specialist consultants

- Reviewing, validating and further developing the existing design information and design proposals prepared to date

- Managing design development and multidisciplinary coordination

- Coordinating statutory approval submissions and Building Control requirements

- Acting as Assigned Certifier and coordinating BCAR compliance requirements, where applicable

- Acting as Employer’s Representative during the procurement and construction stages of the project

- Leading stakeholder engagement and project reporting

- Preparing and coordinating procurement and tender documentation

- Administering the Works Contract during the construction stage

- Coordinating project handover and completion activities

- Providing technical advice and recommendations to ERC throughout the project lifecycle.

The Architect shall be registered with the Royal Institute of the Architects of Ireland (RIAI) or equivalent and shall hold the appropriate professional registration and statutory eligibility required to fulfil the role of Assigned Certifier in accordance with the Building Control (Amendment) Regulations.

Civil & Structural Engineer

The Civil & Structural Engineer shall be responsible for all civil and structural engineering services associated with the project, including assessment, design, coordination and certification of structural works required to support the refurbishment and accessibility upgrade works.

The Civil & Structural Engineer’s services shall include, but not be limited to:

- Review the structural implications of the existing design proposals, develop the structural design as required and advising on any additional investigations required

- Assessing the impact of the proposed internal alterations, floor openings, platform lift installation and associated builders’ works on the existing structure

- Designing and certifying all required structural interventions, supports, openings, alterations and making-good works

- Coordinating structural requirements with the Architect, M&E Engineer, Fire Safety Consultant and Disability Access Consultant

- Providing structural input to statutory approval submissions, tender documentation, construction stage inspections, contractor queries, completion certification and handover documentation.

The Civil & Structural Engineer shall hold Chartered status with Engineers Ireland, or equivalent.

Mechanical & Electrical Engineer

The Mechanical & Electrical Engineer shall be responsible for the design, coordination and certification of all mechanical and electrical building services associated with the project.

The Mechanical & Electrical Engineer’s services shall include, but not be limited to:

- Reviewing and validating the available building services information and design proposals prepared to date, and advising on any additional surveys, investigations or assessments required

- Taking responsibility for the mechanical and electrical aspects of the project, including services modifications required to support the refurbishment and accessibility upgrade works

- Developing and coordinating the detailed mechanical and electrical services design required to support the project

- Developing coordinated mechanical, electrical, plumbing, ventilation, lighting, emergency lighting, fire alarm and lift-related services design proposals

- Preparing comprehensive performance specifications, drawings, schedules and technical requirements for inclusion in the Works tender documentation

- Advising the Client on appropriate energy efficiency measures and practical opportunities to maximise the efficiency, performance and maintainability of the building services systems

- Coordinating building services requirements with the Architect, Civil & Structural Engineer, Fire Safety Consultant and Disability Access Consultant

- Supporting statutory approval submissions, tender evaluation, construction stage inspections, contractor queries, commissioning, completion certification and handover documentation and

- Inspecting the Works during construction to confirm compliance with the Works Requirements, specifications and applicable technical standards.

The Mechanical & Electrical Engineer shall hold Chartered status with Engineers Ireland, or equivalent.

Quantity Surveyor

The Quantity Surveyor shall be responsible for the provision of all quantity surveying, cost management and commercial services associated with the project throughout the design, procurement, construction and close-out stages.

The Quantity Surveyor's services shall include, but not be limited to:

- Reviewing and validating the existing Order of Magnitude Cost Estimate and advising ERC on its suitability for progression of the project.

- Preparing and maintaining cost plans throughout the design development process in accordance with the Capital Works Management Framework (CWMF).

- Providing cost advice to support design development and ensuring that the evolving design remains aligned with the approved budget.

- Preparing elemental cost analyses and advising on opportunities for value engineering, whole-life value and cost optimisation without compromising the project objectives or statutory compliance.

- Advising the Integrated Design Team on procurement strategy, packaging of the Works Contract and commercial matters.

- Preparing Bills of Quantities, pricing documents, schedules of rates or other pricing documentation appropriate to the selected procurement strategy.

- Preparing pre-tender estimates and advising ERC on the anticipated construction cost prior to the issue of tender documentation.

- Supporting the procurement process by responding to tender queries, preparing pricing clarifications, analysing tender returns, identifying abnormally low or unbalanced tenders where appropriate and preparing tender evaluation reports relating to price.

- Providing commercial advice during contract award and assisting in the preparation of contract documentation.

- Monitoring the financial performance of the Works Contract during the construction stage, including the assessment of interim payment applications, valuation of variations, change control and cost reporting.

- Preparing regular financial reports, including updated forecasts of the anticipated final account and advising ERC of any emerging budgetary risks.

- Assessing contractor claims and providing commercial recommendations to ERC.

- Agreeing and preparing the Final Account and supporting the commercial close-out of the project.

- Coordinating with the Architect, Civil & Structural Engineer, Mechanical & Electrical Engineer and other members of the Integrated Design Team to ensure that cost considerations are integrated into design development and procurement decisions.

The Quantity Surveyor shall be a Chartered Quantity Surveyor, registered with the Society of Chartered Surveyors Ireland (SCSI), or an equivalent recognised professional body.

PSDP (Project Supervisor Design Process)

The PSDP shall fulfil the statutory duties assigned under the Safety, Health and Welfare at Work (Construction) Regulations.

The PSDP’s services shall include, but not be limited to:

- Coordinating design risk management activities throughout the design development, tender and construction stages

- Preparing, updating and maintaining the Design Risk Register

- Preparing and updating the Preliminary Safety and Health Plan

- Coordinating health and safety information across all design disciplines and specialist consultants

- Ensuring that residual design risks are identified, recorded and communicated within the project documentation

- Liaising with the project Supervisor Construction Stage (PSCS), Works Contractor and Client as required and

- Supporting handover of relevant health and safety information at completion.

The PSDP shall hold relevant statutory accreditation and professional registration appropriate to the role.

This role can be performed by the Architect or by one of the Engineers or be a standalone appointment within the team.

### 4.2 Specialist Services

The Integrated Design Team shall include the following specialist services.

Fire Safety Consultant

The Integrated Design Team shall include a Fire Safety Consultant to support the design process and to ensure that the project is developed and delivered in accordance with all applicable fire safety standards and statutory requirements.

The Fire Safety Consultant shall provide specialist fire safety advice and shall be responsible for the development of an appropriate fire safety strategy for the project.

The Fire Safety Consultant’s services shall include, but not be limited to:

- Reviewing fire safety requirements applicable to the project

- Developing fire safety strategy proposals

- Preparing and managing the Fire Safety Certificate application required under this appointment

- Liaising with relevant statutory authorities

- Reviewing contractor proposals, technical submissions and fire safety-related information during the construction stage

- Monitoring the installation of fire safety-related works on site, as appropriate and

- Providing construction stage fire safety advice and support.

Disability Access Consultant

The Integrated Design Team shall include a Disability Access Consultant to support the design process and to ensure that the project is developed and delivered in accordance with all applicable accessibility standards, universal design principles and statutory requirements.

The Disability Access Consultant shall provide specialist accessibility and universal design advice throughout the project.

The Disability Access Consultant’s services shall include, but not be limited to:

- Reviewing accessibility requirements applicable to the project

- Undertaking universal design assessments and providing recommendations

- Preparing and managing the Disability Access Certificate application required under this appointment

- Liaising with relevant statutory authorities

- Reviewing contractor proposals, technical submissions and accessibility-related information during the construction stage

- Monitoring the installation of accessibility-related works on site, as appropriate and

- Providing construction stage accessibility advice and support.

### 4.3 Additional Specialist Services

Tenderers shall ensure that any additional specialist expertise required for the successful delivery of the project is incorporated within their proposal or made available where required.

Additional specialist services may include, but shall not be limited to:

- Specialist Surveys and Investigations

- Building Control Liaison

- BCAR Compliance Services, where required and

- Other specialist services required to support statutory compliance or project delivery.

The requirement for any additional specialist services shall be identified by the Integrated Design Team and agreed with ERC as the project progresses.

### 4.4 Integrated Design Team Coordination

The Integrated Design Team shall operate as a fully integrated multidisciplinary team.

The Architect, acting as Lead Consultant, shall be responsible for ensuring effective communication, coordination and information sharing between all project participants.

The Integrated Design Team shall ensure that:

- Design information is fully coordinated across all disciplines.

- Statutory requirements are identified and addressed at the earliest opportunity.

- Design development remains aligned with the approved budget and programme.

- Risks are actively identified, monitored and managed.

- All project deliverables are subject to appropriate quality assurance procedures.

## 5. Scope of Services

The Integrated Design Team shall provide all professional services necessary for the successful delivery of the project.

The services described below are indicative of the minimum requirements and shall not be considered exhaustive. The successful Tenderer shall undertake all activities reasonably necessary for the proper review, validation, development, coordination and delivery of the project.

The services shall be delivered in accordance with the relevant stages of the Capital Works Management Framework (CWMF), from Stage 2b / Stage 2c, as applicable, through to completion.

The Integrated Design Team shall be required to review the available design information prepared to date and progress the project through statutory approvals, procurement of the Works Contractor, construction stage services, handover and completion.

### 5.1 Review of Existing Information

At Project commencement, the Integrated Design Team shall review, validate and advise on the available project information prepared to date.

The Integrated Design Team’s services shall include, but not be limited to:

- Reviewing all available project information, reports, drawings, surveys and existing documentation

- Reviewing and validating the existing design proposals and cost estimate information

- Undertaking site inspections and familiarisation visits

- Assessing whether the available design information is sufficient to progress the project from Stage 2b / Stage 2c, as applicable

- Identifying information gaps, design coordination issues and additional survey requirements and

- Advising ERC regarding any additional investigations, surveys or specialist assessments required to support design development, statutory approvals, procurement and delivery of the project.

### 5.2 Design Development

The Integrated Design Team shall further develop the available design information and prepare a coordinated multidisciplinary design solution suitable for statutory approvals, procurement and construction.

The Integrated Design Team’s Services shall include, but not be limited to:

- Reviewing, validating and further developing the existing design proposals

- Developing coordinated architectural, structural and building services design solutions

- Assessing alternative design options where appropriate

- Coordinating accessibility and fire safety requirements within the design development process

- Integrating platform lift, accessible WC/shower, internal alteration and building services requirements into the developed design

- Considering buildability, maintainability, operational requirements and value for money

- Supporting the development of project budget and programme information

- Coordinating stakeholder comments and project requirements and

- Ensuring that the developed design remains aligned with the project objectives, statutory requirements, budget and programme.

### 5.3 Statutory Compliance and Approvals

The Integrated Design Team shall identify, coordinate and manage all statutory approvals and compliance requirements necessary for the delivery of the project.

The Integrated Design Team’s services shall include, but not be limited to:

- Ensuring compliance with applicable Building Regulations

- Preparing and managing the Fire Safety Certificate application required for the project

- Preparing and managing the Disability Access Certificate application required for the project

- Assessing BCAR applicability and managing BCAR compliance requirements, where applicable

- Liaising with Building Control and relevant statutory authorities

- Preparing statutory approval submissions and supporting documentation

- Managing statutory approval processes and associated timelines and

- Responding to requests for further information or clarification from statutory authorities.

The Integrated Design Team shall be responsible for coordinating all information required to support statutory approvals and for ensuring that statutory requirements are integrated into the design, tender documentation and construction-stage information

5.4 Tender Documentation and Procurement Support

The Integrated Design Team shall prepare all design and technical documentation required to support the procurement and appointment of the Works Contractor.

The Integrated Design Team’s services shall include, but not be limited to:

- Preparing coordinated tender drawings

- Preparing technical specifications, schedules and supporting documentation

- Coordinating tender documentation across all design disciplines and specialist services

- Ensuring that tender documentation is complete, coordinated and suitable for Works procurement purposes

- Supporting ERC during the Works tender process

- Responding to tender queries and clarification requests

- Reviewing and technically assessing tender submissions

- Assisting with tender evaluation and preparation of tender reports and

- Supporting contractor appointment in accordance with the Capital Works Management Framework.

The Integrated Design Team shall ensure that all tender documentation is coordinated, complete, buildable and aligned with statutory requirements, budget, programme and the approved design.

5.5 Construction Stage Services

The Integrated Design Team shall provide construction stage services to support the proper delivery of the Works in accordance with the approved design, statutory requirements and Works Contract documentation.

The Integrated Design Team’s services shall include, but not be limited to:

- Attending project meetings and site meetings

- Undertaking site inspections and preparing inspection reports

- Reviewing contractor technical submissions, shop drawings, samples, materials and workmanship proposals

- Responding to queries

- Issuing design clarifications and supplementary information where required

- Monitoring compliance with design requirements, statutory approvals and technical specifications

- Supporting statutory compliance requirements during construction, including FSC, DAC and BCAR requirements where applicable

- Reviewing commissioning, testing and certification information

- Monitoring progress against programme requirements and advising ERC of any technical risks or issues

- Assisting in the resolution of technical issues arising during construction and

- Supporting practical completion inspections, snagging and handover preparation.

The Integrated Design Team shall maintain regular communication with ERC throughout the construction stage and shall provide timely technical advice, reporting and decision-support information as required.

5.6 Handover and Completion

The Integrated Design Team shall support project completion, handover and close-out activities.

The Integrated Design Team’s services shall include, but not be limited to:

- Participating in practical completion inspections

- Preparing, coordinating and managing snagging activities

- Reviewing as-built drawings and record documentation

- Reviewing operation and maintenance documentation

- Coordinating completion of statutory certification requirements

- Supporting commissioning, handover and occupation requirements

- Providing defects period administration and support

- Supporting the resolution of defects during the defects liability period and

- Preparing final project close-out information and reports.

5.7 Sustainability and Accessibility

Throughout all stages of the project, the Integrated Design Team shall support the integration of proportionate sustainability, accessibility and inclusive design considerations into the development and delivery of the project.

The Integrated Design Team’s services shall include, but not be limited to:

- Promoting sustainable design principles appropriate to the scale and nature of the project

- Considering energy efficiency, lifecycle performance, durability and maintainability

- Promoting responsible material selection where appropriate

- Considering circular economy principles, reuse and waste minimisation where feasible

- Ensuring that accessibility, universal design principles and statutory accessibility requirements are incorporated throughout the project lifecycle

- Coordinating accessibility requirements with fire safety, structural and building services design requirements and

- Supporting compliance with applicable sustainability, accessibility and statutory obligations.

## 6. Project Governance

ERC will act as the Contracting Authority and Client for the project.

The project will be managed through an appropriate governance structure to ensure effective coordination between all parties involved in the development and delivery of the project.

The governance structure is expected to include:

- ERC,

- Integrated Design Team (including Fire Safety Consultant and Disability Access Consultant as required),

- Relevant statutory authorities, and

- Any additional consultants appointed separately by ERC, where required.

The Integrated Design Team shall act as the primary design coordinator for the project and shall be responsible for coordinating and integrating the inputs of all core design disciplines and required specialist services.

The Integrated Design Team Lead Architect shall ensure that architectural, structural, building services, fire safety and accessibility requirements are appropriately coordinated and incorporated into the design documentation, statutory approval submissions, tender documentation and construction-stage information.

The Integrated Design Team shall report to ERC and shall support the governance structure through the provision of design coordination, progress reporting, technical advice, risk identification and decision-support information as required.

The Integrated Design Team Lead shall establish and maintain appropriate information management arrangements, including a Common Data Environment (CDE) where required, for the management and sharing of project documentation with ERC and relevant project stakeholders.

## 7. Communications and Reporting

The Integrated Design Team will be required to maintain regular communication with ERC and relevant project stakeholders throughout the design and delivery of the project.

This will include:

- Attendance at project meetings

- Preparation of progress reports

- Programme and risk reporting

- Design coordination updates

- Maintenance of project records and decision logs

- Timely escalation of project risks, issues and matters requiring Client decisions and

- Provision of technical advice and recommendations to support project governance and decision-making.

Fortnightly design team meetings will be held during the design development stages to ensure effective coordination between disciplines. Meeting frequency during later project stages shall be agreed with ERC.

The Integrated Design Team will be required to provide updates on programme, cost, risk and design development throughout the project lifecycle.

The Integrated Design Team shall support the governance structure of the project through the provision of timely reporting, technical advice and design coordination as required by the Contracting Authority.

## 8. Health & Safety (PSDP)

The Integrated Design Team’s Lead Consultant shall undertake or oversee the undertaking of the role of project Supervisor for the Design Process (PSDP) in accordance with the Safety, Health and Welfare at Work Act 2005 and the Safety, Health and Welfare at Work (Construction) Regulations 2013 (as amended).

The PSDP shall coordinate the design process to ensure that safety and health considerations are integrated into the development and delivery of the project.

This will include, but not limited:

- Preparation and maintenance of the Design Risk Register

- Coordination of design risk assessments

- Preparation and updating of the Preliminary Safety and Health Plan

- Coordination with the Project Supervisor for the Construction Stage (PSCS)

- Certification of Design, where required.

The PSDP will ensure that residual risks associated with the design are clearly identified and communicated as part of the project documentation.

## 9. Quality Assurance and Information Management

All deliverables produced by the Integrated Design Team shall comply with the relevant quality standards of ERC and the internal quality management systems of the appointed consultants.

The Integrated Design Team shall demonstrate appropriate quality assurance procedures for the preparation, review and coordination of design documentation.

Design documentation shall be prepared in accordance with:

- Relevant legislation and statutory requirements

- Applicable Irish Building Regulations

- Recognised professional standards and best practice guidance

Where applicable, the Integrated Design Team will be expected to consider sustainable design principles, resource efficiency and lifecycle performance in the development of the design proposals.

Information management processes should ensure that design documentation is coordinated across disciplines and suitable for use throughout the statutory approval, procurement and construction stages of the project.

The Integrated Design Team Lead shall establish and maintain appropriate information management arrangements, including a Common Data Environment (CDE), where required, for the management, coordination and sharing of project documentation.

The Integrated Design Team shall ensure that project information is managed in a structured and controlled manner and that all documentation, drawings, reports, decisions and approvals are appropriately recorded, maintained and made available to ERC and relevant project stakeholders.

The Integrated Design Team shall maintain appropriate project records, revision controls and document management procedures throughout the project lifecycle to support transparency, auditability and effective Project governance

## 10. Statutory Compliance

The Integrated Design Team shall ensure that the project complies with all relevant statutory requirements and applicable legislation.

The Integrated Design Team will be responsible for identifying all statutory approvals required for the delivery of the project and supporting ERC in securing such approvals where required.

This may include, but is not limited to:

- Planning approvals and amendments to existing permissions, where required,

- Building Regulations compliance,

- Fire Safety Certificate (FSC),

- Disability Access Certificate (DAC),

- Compliance with the Building Control (Amendment) Regulations (BCAR), where required, and

- Any other statutory approvals or regulatory requirements necessary for the delivery of the project.

The ERC premises are situated on the Dublin City University (DCU) St Patrick’s Campus. DCU has the right to review, approve and provide formal sign-off for all proposed building works, alterations or other modifications to the premises prior to implementation.

The Integrated Design Team will be required to prepare all necessary documentation to support approvals from Dublin City University DCU, statutory approvals and ensure that the design proposals comply with the relevant regulatory requirements.

## 11. Project Programme

The project will be delivered in accordance with the relevant stages of the Capital Works Management Framework (CWMF), from Stage 2b / Stage 2c, as applicable, through to completion.

The Integrated Design Team shall support ERC in developing, maintaining and monitoring an appropriate programme for the delivery of the project.

The programme shall include key milestones relating to:

- Review and development of the existing design information

- Statutory approval processes

- Preparation of Works tender documentation

- Procurement and appointment of the Works Contractor

- Construction works

- Project completion and handover.

The Integrated Design Team will be required to monitor programme progress and provide updates to ERC throughout the project lifecycle.

As outlined in the ITT, the performance period constitutes 12-18 months from the commencement of the engagement.

## 12. Deliverables

The Integrated Design Team shall be responsible for the production, coordination and submission of all documentation required to support the design development, statutory approvals, procurement and delivery of the project.

All deliverables shall be prepared in accordance with the Capital Works Management Framework (CWMF), applicable statutory requirements and recognised professional standards.

The deliverables shall include, but are not limited to:

### 12.1 Design & Coordination Documents

- Design Reports: Comprehensive reports and supporting documentation prepared at the relevant CWMF stages, including architectural, structural, building services, fire safety and accessibility design information.

- Coordinated Design Documentation: Fully coordinated architectural, structural and building services drawings, schedules and associated design information required to support the development and delivery of the project.

- Design Coordination and Risk Management: Design coordination records, multidisciplinary design reviews, Design Risk Register and associated PSDP documentation.

### 12.2 Statutory & Compliance Documentation

- Statutory Approval Packages: All documentation required to support statutory approvals, including Fire Safety Certificate (FSC) and Disability Access Certificate (DAC) applications.

- Health and Safety Documentation: Preliminary Safety and Health Plan, Design Risk Register and associated PSDP documentation.

- BCAR Documentation: All notices, certificates, inspection plans and associated documentation required to support compliance with the Building Control (Amendment) Regulations, where applicable.

- Regulatory Submissions: Documentation required to support engagement with Building Control and other relevant statutory authorities.

### 12.3 Procurement & Technical Documentation

- Tender Documentation: Comprehensive tender documentation for the procurement of the Works Contractor, including drawings, specifications, schedules and associated technical information.

- Tender Support Services: Responses to tender queries and clarifications, technical assessment of tender submissions and tender evaluation support documentation.

- Project Programme and Design Development Updates: Programme updates, design development reports and other documentation necessary to support the procurement and delivery of the project.

### 12.4 Construction Stage Services Documentation

- Construction Stage Records: Site inspection reports, design clarifications, technical reviews and records associated with construction stage services.

- Contract Administration Documentation: Certification, contract administration records, review of contractor submissions and associated project documentation.

- Progress Monitoring: Progress reports, technical advice and other documentation required to support the delivery of the works.

### 12.5 Handover & Completion Documentation

- As-Built Documentation: Verified as-built drawings and associated record information in electronic format.

- Operation and Maintenance Documentation: Review of operation and maintenance manuals, commissioning information and handover documentation.

- Project Completion Documentation: Practical Completion documentation, statutory close-out documentation, defects period records and final project close-out reporting.

## 13. General Requirements

The scope of services described in this project brief is intended to outline the principal services required for the delivery of the project.

Tenderers shall ensure that their proposals include all services necessary for the successful delivery of the project in accordance with the Capital Works Management Framework (CWMF), applicable statutory requirements and recognised professional standards.

The services described in this project brief shall not be considered exhaustive, and the appointed Integrated Design Team shall undertake all tasks necessary for the proper design, coordination, administration and delivery of the project.

Any ambiguity, omission or apparent gap in the description of the services should be raised through the Tender query process.