## Pre lim H&S , TTM plans
Donegal County Council
Roads and Transportation
Preliminary Health and Safety Plan
for
Fort Dunree - Drill Shed
1.1 Introduction This Preliminary Health and Safety plan has been prepared in accordance with Regulation 12(1) of the Safety, Health and Welfare at Work (Construction) Regulations, 2013 (S.I. No.291 of 2013). This plan will be made available to all parties interested in or tendering for the role of Project Supervisor Construction Stage (PSCS). The purpose of this plan is to identify features of design and construction that may affect health and safety to the PSCS for development of the construction stage health and safety plan. The PSCS once appointed is required prior to commencing works on this project to develop this plan further into the construction stage health and safety plan and update further where required as the project processes.
1.2 Project Description
The works principally comprise the construction of a new shed at Fort Dunree, excavation of foundations and associated groundworks, casting of foundations and the floor slab, and installing a steel structural frame, along with walls, external roof cladding, and gutters. Extension of existing water supply and installation of internal sink. Installation of surface water drainage and external footpaths. Extension of existing power supply and installation of internal sockets and lighting. Installation of doors to openings. Completion of ground works and associated landscaping.
1.2.1 Project Time Scale
1st September 2026 to 31th December 2026 (estimated)
1.2.2 Drawing and Specifications
There are three drawings provided with this contract: 0594-MFA-XX-ZZ-DR-S-600-100 to 102. Standard details and specifications are also attached.
1.3 Site Location
Fort Dunree, Dunree View, Leophin, Linsfort, Co. Donegal. Area highlighted in red - displays building location Area highlighted in yellow - displays compound location Please refer to Drawing DS-01 for further information
1.4 Details of Client, Designer, Project Supervisor Design Process.
Name and Contact details
Client |  | Donegal County Council, County House, Lifford, Co. Donegal
Project Supervisor Design Process (PSDP) |  | Donegal County Council, County House, Lifford, Co. Donegal
Designers |  | Donegal County Council, County House, Lifford, Co. Donegal
Project Supervisor Construction Stage |  | It is intended that the successful tender will be appointed as PSCS in accordance with the Safety Health and Welfare at Work (Construction) Regulations 2013. The PSCS will be required to provide details of their competency to undertake the role of PSCS
1.4.1Arrangements for Liaison Between Parties
The Client recognises the need for effective communication between parties so that health and safety standards can be achieved and maintained. The principle means of communication will be by phone, regular email and scheduled meetings. The PSCS shall bring to the attention of the PSDP any unforeseen eventualities or significant health and safety issues the implications of which the PSCS becomes aware of during the execution of the project. The PSDP will undertake unscheduled visits to review health and safety of the project and compliance with the Regulations.
1.5 Adjacent Land Uses and Site Restrictions
The Fort Dunree site is a live tourist destination and also open to the public 24hrs of the day. All deliveries and removals will enter via Gate A referenced on Drawing XXX. The area where the shed is being constructed will need to be fenced off with 2.4m high fencing. The remaining area of the site is to be preserved for the public.
1.5.1 Site Security
Construction projects and site by their nature can pose risks to third parties, members of the public and adjacent business and residential properties and their occupiers. The PSCS will ensure access to adjacent properties is taken into consideration when planning the works. The PSCS shall ensure that the Works are secure at all times. All areas of the site which are under, construction, investigation or are storing materials shall be secured.
1.6 Works Involving Particular Risks Significant Health and Safety hazards Likely to be encountered
The following information is provided in relation to Particular risks as defined in Schedule 1 of the Safety Health and Welfare at Work (Construction) Regulations 2013 that need to be taken into account by the PSCS and addressed in the construction stage health and safety plan. Information on non scheduled risks which should be considered and addressed in the construction stage health and safety plan is contained under 1.6.11. The PSCS should take full account the principles of prevention as set out in the Safety Health and Welfare at Work Act (2005)
1.6.1 Works which put persons at work at risk of burial under earth falls, engulfment in swampland or falling from a height, were the risk is particularly aggravated by the nature of the work or processes used or by the environment at the place of work or site.
Deep excavations for foundations; trench excavations for drainage, electrical ducts. These are deemed to be within a reasonably competent contractor's ability to foresee and deal with. Locations of risk that do not have an existing fence to be highlighted. Implement safety controls such as movable barrier/guards. Work barriers to be used as appropriate to restrict access.
1.6.2 Works which put persons at risk from chemical or biological substances constituting a particular danger to the safety and health of such persons or involving legal requirements for health monitoring.
The works may involve exposure to wet and cured concrete, cementitious materials and substances, Bitumen & Asphalt, Glues, Solvents and Sealants, Lead, Man Made , Mineral Fibres, Fuel/Oil, Chemicals, Hydraulic Oil and Engine Oil. These are deemed to be within a reasonably competent contractor's ability to foresee and deal with. Adequate personal safety equipment to be worn to eliminate the risk of contact with biological agents. Good personal and occupational hygiene practices should be implemented
1.6.3 Work with ionising radiation requiring the designation of controlled or supervised areas as defined in Directive 96/29/Euratom4.
None envisaged at this stage of the project.
1.6.4 Works near high voltage power lines.
All works that involves a risk from the hazards of underground or overhead cables must be managed in line with H.S.A and ESB Codes of Practice and Guidance Documents
1.6.5 Work exposing persons at work to the risk of drowning, for example: works significantly below water table, work to bridges, culverts, work on or near the sea, lakes, ponds, reservoirs.
None envisaged at this stage of the project.
1.6.6 Work on wells, underground earth work and tunnels, for example: excavated wells, underground earth works, tunnels, underpinning.
None envisaged at this stage of the project.
1.6.7 Divers Requiring Air Supply.
None envisaged at this stage of the project.
1.6.8 Work carried out in a caisson with a compressed-air atmosphere.
None envisaged at this stage of the project.
1.6.9 Work involving the use of explosives.
None envisaged at this stage of the project.
1.6.10 Work involving the assembly or dismantling of heavy prefabricated components for example: heavy steel structural frame elements, heavy pre-cast concrete frame elements or heavy prefabricated plant items.
These are deemed to be within a competent contractor's ability to foresee and deal with.
1.6.11 Other Hazards and Risks
Working in live traffic, existing ground conditions, pedestrian routes, interface with public and potential for noise, vibration, fumes and dust during site works. It is noted the many of these risks will arise out of the work methods used on the project these are deemed to be within a competent contractors ability to foresee and deal with.
1.7 Safety File
The client will make available any existing file to the PSCS for consideration. The PSCS will coordinate arrangements among contractors to ensure the provision of relevant information, necessary for the PSCS to complete the safety file. The PSCS shall provide in writing to the PSDP all relevant information necessary for the PSDP to compile the safety file.
1.8 Asbestos
None envisaged at this area of the site. Should asbestos containing materials be uncovered on site they should be managed in line with H.S.A guidelines. Where asbestos is required to be removed it shall be removed in accordance with the requirements set out in the Safety Health and Welfare at Work (Exposure to Asbestos) Regulations 2006 and the Safety Health and Welfare at Work (Exposure to Asbestos)( (Amendment) Regulations 2010
1.9 Other Works on Site
None envisaged at this stage of the project.
1.10 Site Rules
It shall be the responsibility of the PSCS to ensure that all personnel receive site safety induction training prior to commencing works on this project. The PSCS should develop their own site safety induction, incorporating the following proposed site safety rules.Contractors / Sub-contractors • must provide a copy of their safety statement & method statement and risk assessments for the work they will undertake, to the PSCS, prior to commencing works on site. • must ensure that their employees have Safe pass & Construction Skills cards (CSCS) as required. • must nominate, in writing to the PSCS, a Safety Officer. • Where there will be 100 or more persons on site, the PSCS must nominate a full time Safety Advisor. • Must supply all the Personal Protective Equipment, to your own personnel, that they require to carry out their particular work safely.
All Personnel • You must have a Safepass and/or / Construction Skills Card for specified operations on site. These must be produced to the PSCS before commencing work on site. • You are not permitted to carry out any works on this Project, unless you have been specifically trained to carry out those works, i.e. you have been trained on your company's risk assessments, safe systems of work (method statement) and safety procedures relating to your works on site and have signed-off on same. • Must report any situation / operation / plant / equipment you think is dangerous on this project. • Safety footwear, safety helmets, and high visibility must be worn at all times on site. • Hearing protection must be worn when working with or near noisy machinery. • Eye protection must be worn when cutting, drilling, and using air tools. • Overalls, dust / fume masks, and heavy-duty gloves must be worn when working with / or near chemicals. • Work is not permitted at heights (where you may fall and injure yourself) unless adequate measures are in place to prevent falls, e.g. guardrails, work platforms, MEWP’s, or safety harnesses are used. • Safe access and egress must be maintained at all times, this means ensuring that rubbish and materials are kept clear of access routes at all times. • All accidents must be immediately reported to the contractor/ PSCS. • All tools on site must be 110v or less unless otherwise approved by the contractor /PSCS. • Any person who puts their own health & safety at risk, wilfully endangers others by their actions or neglect, or engages in horseplay will be subject to disciplinary action, up to and including dismissal from site. • Any enquiry from a member of the public must be referred to the contractor/ PSCS. • Any person found to be under the influence of alcohol / intoxicants will be dismissed from site immediately. • All personnel have a responsibility for their own safety and the safety of others. You must ensure that you work safely at all times whilst on site.
1.11 Design Conclusions and Assumptions
A design risk assessment has been completed for the project and action taken to reduce or control the risks. Residual risks will remain as outlined above and hazards and risks will arise out of the work methods employed to execute the works, these are deemed to be within a competent contractors ability to foresee and manage. The PSCS shall bring to the attention of the PSDP any unforeseen eventualities or significant health and safety issues the implications of which the PSCS becomes aware of durian the execution of the project
2.0 Traffic Management
2.1 Introduction The PSCS must ensure that a suitable Traffic Management Plan is prepared and implemented to ensure that the public and other users of the site are not put at risk during the works.
2.2 Site Traffic and Parking The PSCS shall designate an area for staff parking. This area shall: ● Allow safe access and egress of vehicles and personnel, ● Not obstruct other access or sightlines from same, ● Not be located within designated safety zones,
2.3 Construction Traffic The PSCS shall designate an area for collection / drop-off of materials in the plan of Works. This area shall: ● Allow safe access and egress of vehicles and personnel, ● Not obstruct other access or sightlines from same, ● Not be located within public areas ● Be located adjacent to where the materials shall be stored to minimise double-handling and traffic movements on site.
2.4 Site Access and Egress The PSCS shall ensure that the Works are undertaken in a manner which facilitates the safe access and egress of vehicles, pedestrians and cyclists. Furthermore, the PSCS shall ensure that the Works are undertaken in a manner which facilitates the safe access and egress of staff and visitors for the duration of Works, including suppliers of materials to the Works.
2.5 Diversions and Road Closures N/A
2.6 Traffic Control Measures N/A
2.7 Emergency Services N/A
2.8 Vulnerable Road Users Pedestrian movements and other such movements must be expected by the PSCS and must be fully taken into account and safely catered for in the planning and execution of the Works. The PSCS shall ensure that pedestrians are fully considered in the preparation of the Traffic Management Plan and that the Works are safely undertaken in full consideration of same.
2.9 Working Hours The PSCS is to liaise with Donegal County Council regarding restrictions on working hours and must comply with the relevant stipulations detailed in Works contract.
2.10 Safety and Security The PSCS shall ensure that the Works are secure at all times. All areas of the site which are under, construction, investigation or are storing materials shall be secured.
2.11 Traffic Signs Traffic signs and other apparatus for the control of traffic must conform to the requirements of Chapter 8 of the Traffic Signs Manual encapsulated in the W-I-D-E approach to signing at road works: ● Warn the user of the forthcoming works ● Inform the road user of the characteristics (e.g. road narrows, traffic control ahead etc.) ● Direct the road user safely through the site by means of arrows, cones etc ● End clearly sign the end of the road works site
2.12 Variable Message Signs (VMS) N/A
2.13 Carriageway and Verge Maintenance N/A
2.14 Bus Operators N/A
2.15 TVRS or Barriers Systems The provision of TVRS and barrier systems should be subject to further risk assessment by the PSCS and TTM designer.
2.16 Design Speed for TTM N/A
2.17 TTM Inspections N/A
2.18 TTM Maintenance N/A