DEFINITIVE PROJECT BRIEF

| Item No. | Parameter | Description |
| --- | --- | --- |
| 1 | Objective | Provide social housing under the Housing for all housing plan |
| 2 | Purpose | Satisfy the housing need of an appropriate number of applicants on the Councils Housing Waiting List. |
| 3 | Scope | Laois County Council is seeking an architect led design Team to provide the full architectural & engineering & quantity Surveying services required to deliver the Design, the Procurement of a Contractor and Contract Management of the project, including full and detailed Architectural and Engineering drawings, and a complete Bill of Quantities. In addition, Building Energy Rating certificates are to be provided for each individual unit upon substantial completion of the project. The Design Team will utilise the Part 8 planning approval that is in place and progress the scheme to detailed design, tender action, construction stage and handover. Tenders will be invited for the construction of the scheme. The Form of Contract shall be the Public Works Contract for Building Works designed by the Employer – PWCF-1. The procurement of the contractor shall be in compliance with the Government’s Construction Procurement Reform programme and the Capital Works Management Framework. (CWMF) (constructionprocurement.gov.ie.) The design team shall undertake the tender assessment and submit a tender report and recommendation for the appointment of a contractor. The Design Team will manage and supervise the construction of the scheme and handover of the completed scheme to Laois County Council. The scope of the consultancy services required is as follows: Prepare a scheme layout for submission to the Department of Housing, Local Government and Heritage for single stage approval. It should be noted that in order to achieve Departmental Approval, the scheme layout may require a number of revisions. The Council will also request the design team to examine the feasibility of providing an additional apartment on the ground floor. The relevant stages under the CWMF are as follows: - Preliminary Report Stage. (ii) Design Stage (iii) Tender Action, evaluation, award stage (iv) Construction Stage (v) Handover of works stage. The Design Team shall provide the full set of services as set out for Architect, Civil/Structural Engineer, Building Services (M&E) Engineer, Quantity Surveyor, & Project Supervisor Design Process, in the Scope of Services -- Office of Government Procurement Framework -- Agreement for Full, Integrated Design Team. In addition the Design Team shall also prepare Contract Documents to procure site investigation work, including a Site Investigation Report. This Report shall be issued as part of the tender documents for the main contract. The Design Team will produce detailed designs based on the Part 8 layout drawings for the scheme. The detailed drawings have to be agreed with the local authority and be acceptable to the Department of Housing, Local Government and Heritage. Tenders will be invited for the construction of the scheme. The Form of Contract shall be the Public Works Contract for Building Works designed by the Employer PW -CF 1. The procurement of the contractor shall be in compliance with the Government’s Construction Procurement Reform programme and the Capital Works Management Framework. (CWMF) (constructionprocurement.gov.ie.) The design team shall undertake the tender assessment and submit a tender report and recommendation for the appointment of a contractor. The design team will manage and supervise the construction of the scheme and handover of the completed scheme to Laois County Council. A sustainability report shall be provided by the building services consultant at detailed design stage outlining the various options (included estimated cost) with regard to the thermal and renewable properties of the building elements to achieve the required energy rating. BERS will also be provided to the Client at handover stage and the cost of providing these BERs should be allowed for in the % fee quoted/Tender Sum The design shall be in conformance with current Building Regulations and the Design Manual for Quality Housing and shall comply with the internal layout and space provision requirements in this document. The design team will be required to revise the design to incorporate any changes that arise out of the Laois County Council and/or the Department of Housing review of the design. The design team should allow for the cost of up to 4 revisions of the overall scheme layout design. In addition the successful design team will undertake the role of Project Supervisor Design Process in accordance with the Safety, Health and Welfare at Work (Construction Regs.) 2013 for the duration of the project. |
|  | Scope (continued) | An enabling works tender pack will be prepared by the design team to demolish the façade and clear the site. These works will be undertaken in advance of the main contractor’s appointment. The design team’s structural engineering specialist shall design the temporary propping required for the neighbouring buildings and the temporary measures required to weatherproof the exposed party walls after the County Hotel has been demolished. It is envisaged that underpinning will be required to the party walls on both boundaries and the design of this underpinning should be allowed for in the tender sum. The main building contractor will undertake the construction of the scheme in accordance with the drawings prepared by the design team and undertake the role of Project Supervisor Construction Stage in accordance with the Safety, Health and Welfare at Work Act (Construction) 2013 |
| 4 | Deliverables/desired outcomes | Deliver a housing scheme with 11 no. social housing units: construction costs as per the Schedule of Accommodation required: 3 no. 1 bed apartments – ground floor (1 person) 2 no. 1 bed apartments - first floor (1 person) 1 no. 2 bed apartment - first floor (3 person) 2 no. 1 bed apartments - second floor (1 person) 1 no. 2 bed apartment - second floor (3 person) 2 no. 1 bed apartments - third floor (1 person) The works to be undertaken in a safe manner in compliance with all relevant Health and Safety Legislation. |
| 5 | Performance | Housing units to comply with Part L – Conservation of Fuel and Energy of the building regulations. All design work shall comply with the Design Manual for Quality houses (including the requirement for floor area, room sizes etc.) and the specification shall comply with the “Employer’s requirements for detail design of quality housing” |
| 6 | Assumptions | All construction work shall be undertaken during normal working hours. |
| 7 | Governance and reporting | The Department of Housing, Local Government and Heritage is the relevant Government Department providing the funding for this project (the Sanctioning Authority under the Public Spending Code) Laois County Council (the Sponsoring Agency under the Public Spending Code) through its technical staff will be co-ordinating the project. The project is subject to approval from the DHPLG. An outline design and unit types will be submitted for the Single Stage Approval. An outline construction cost estimate and overall budget will be submitted to the DHPLG. The application should be accompanied by a programme setting out the projected tasks and timelines for progression to Contract Award stage. This Capital Appraisal will be prepared by Laois County Council. The design team will provide an estimate of the construction costs for inclusion in this Capital Appraisal. Under the single-stage process, a LA can proceed with the project through to completion, without formal reversion to the Department, provided that the approved budget is maintained. Informal consultation is encouraged as the project is developed before proceeding to tender, and before accepting a Tender and entering into a contract. In the event that the approved budget is not maintained, an optional Supplementary Stage (equivalent to Stage 4) application for a budget revision is permitted, on receipt of tenders for the main contract and prior to contract award. A detailed case must be made for such budget variation under the specified event headings, which are as follows:- - Tender inflation in line with the SCSI tender index, as published periodically; - Unforeseen infrastructural needs. The Design Team shall revise the cost estimate prior to tendering the main contract and following the tender, a tender report shall be prepared for review by Laois County Council and for submission to DHPLG if a supplementary budget is required. The design team fee will be fixed based on the pre-tender construction estimate (the construction sum estimate will be the sum of all enabling works contracts awarded and the main contract construction estimate) and The design team will report directly to the Senior Engineer (S.E.) in the Housing Department. The design team leader shall be made known as part of the tender submission. Laois County Council may, at its discretion appoint a Clerk of Works (CoW) to the project. This role will be limited to keeping some records of the project. The appointed lead architect shall undertake the role of Employers Representative and shall issue any Change Orders in accordance with the contract. Note: additional expenditure over 2.5% of the contract amount will require DHPLG prior approval. The design team will also undertake the role of PSDP for the project. |
| C | Preferred option | To ensure that this site provides a Sustainable and aesthetically pleasing development of social houses for the benefit of the Tenants and the town of Portlaoise, while designing within the parameters of the current Building Regulations, other regulatory requirements and current Dept of Environment Guidance Documents. |
| 9 | Known risks | Single Stage Approval from the DHPLG is required. |
| 10 | Value management strategies | Change Orders will be issued when required by the Employer’s Representative. The Change Orders will be issued following a recommendation by the project quantity surveyor that the contractor’s submission is value for money and in line with the rates submitted at tender stage. If the cumulative value of Change Orders exceeds 2.5% it will be necessary to seek a revised budget from the DHPLG The Design Team shall submit a Monthly Financial Review of the Project. |
| 11 | Project execution plan | Timescale from the issue of the order number to the design team Week 1 – Issue order no. to design team Week 2 – Co-ordination meeting with design team Week 5 – Compile list of surveys/additional consultants required for the detailed design for the scheme. Week 6 – Review Part VIII drawings and examine the feasibility of adding an additional apartment on the ground floor. Week 10 – Submit layout to DHPLG for review and approval. Week 12 – Finalise layout following input from DHPCLG Architectural Advisor &LCC. Week 14 – Finalise enabling works tender pack for the demolition of the hotel. The tender pack shall include for any temporary structural supports and weatherproofing required to buildings either side of the demolished hotel. The tender pack shall also require the appointed contractor to undertake a condition survey of the adjoining properties prior to the commencement of the demolition. The scope of the condition survey and monitoring shall be provided by the design team structural engineering sub-consultant. Week 15 – Issue site investigation tender pack Week 16 – Tender enabling works contract Week 24 – Appoint enabling works contractor Week 24 - Appoint site investigations contractor Week 36 – Complete demolition and structurally support (if required) and weatherproof buildings either side of demolished hotel Week 37 – Assess cleared site and review the site investigation scope of works Week 38 – undertake the site investigation Week 44 – Finalise the foundation design. Prepare underpinning tender pack. Week 52 – Complete underpinning to all walls/party walls where required Week 58 – Finalise main contract tender pack Week 62 – Submit cost plan to Laois County Council Week 63 – Inform DHPLG of the all-in cost estimate Week 65 – Review any comments from the DHPLG Week 66 - Broadcast tender for main contract Week 80 – Issue letters to successful and unsuccessful tenderers Week 84 – Request a revised budget approval if the successful tender received exceeds the Single Stage budget approval Week 90 – Award main contract Week 92 – issue commencement notice Week 94 – Manage and Supervise Construction Week 166 – Substantial completion and handover Week 218 – Release contract retention |
| 12 | Expected functional life | 100 years |
| 13 | Design restrictions/requirements | The Part 8 planning permission and layouts shall be the basis for the detailed design. |
| 14 | Location | 102 Main Street, Portlaoise |
| 15 | Budget | €5,200,000 euros ex VAT for the construction of the apartments. |
| 16 | Constraints | Financial – work to approved budget. |