Quality & Technical Merit Assessment

Cahir Market House Business Centre – Phase 2

IMPORTANT notes to tenderer on Quality Assessment:

The Quality Assessment Submission should be completed using this original Quality Assessment Submission Microsoft Word template FORM only, with no additional pages to be included, except where requested.

Any additional pages, where not requested, over and above this Form or those attached separately will not be evaluated.

Contract Award Criterion:

This document should be completed in accordance with the Instructions to Tenderers, as set out in the ITT – W1 v3.0 18/11/2024 and be read in conjunction with the other tender documents which form part of the RFT.

The contract award criterion and weightings are predetermined, based on the Most Economically Advantageous Tender (MEAT) with a Price : Quality Ratio of 80 : 20 as set out in Section 9 of document ITT – W1 v3.0 18/11/2024 - Instruction to Tenderers.

Price score: 		800 marks (Based on Comparative Cost Analysis)

Quality Score: 	200 marks

Total Score: 		1000 marks

Quality Assessment:

The tenderers are required to provide a comprehensive service delivery proposal answering the quality questions (Criterion 1, 2, 3, 4 and sub criterion) as set out below and submitted as per the Instruction to Tenderers with the relevant documents attached as detailed.

The scored Quality Assessment Criterion, (maximum marks available 200 marks) is split into the following:

Criterion 1 – Approach and Methodology 		40 marks

Criterion 2 – Contractor’s Programme 		80 marks

Criterion 3 – Quality Assurance and BC(A)R 	40 marks

Criterion 4 – Health and Safety 			40 marks

Total Marks Available 				200 marks

IMPORTANT NOTE:

• Minimum Quality Threshold for each individual criterion: 40%

• Minimum overall Quality Threshold: 50%

Any Tenderer, achieving less than 40% on an individual ‘quality’ criterion or less than 50% overall will be deemed non-compliant and excluded from further consideration.

The Methodology for evaluating Qualitative [Technical Merit] criterion is detailed below:

Band 5 (80 - 100%):

Excellent response with very few or no weaknesses that fully meets or exceeds requirements, and provides comprehensive, detailed, and convincing assurance that the Tenderer will deliver to an excellent standard.

Band 4 (60 - 79%):

A very good response that demonstrates real understanding of the requirements and assurance that the Tenderer will deliver to a good or high standard.

Band 3 (40% - 59%:

A satisfactory response which demonstrates a reasonable understanding of requirements and gives reasonable assurance of delivery to an adequate standard but does not provide sufficiently convincing assurance to award a higher mark.

Band 2 (20% - 39%):

A response where reservations exist, and which have not been addressed by clarification. Lacks full credibility/convincing detail, and there is a significant risk that the response will not be successful.

Band 1 (1% - 19%):

A response where serious reservations exist. This may be because, for example, insufficient detail is provided (even post clarification), and the response has fundamental flaws, or is seriously inadequate or seriously lacks credibility with a high risk of non-delivery.

Band 0 (0%):

No response or a response which completely fails to address the criterion under consideration.

Criterion 1: Approach and Methodology (40 Marks)

Tendering Contractors are to provide a method statement addressing the specific challenges present by the proposed development. These include but are not limited to:

•	Working on a confined restricted site

•	Restricted access for plant and material to site

•	Demolitions and alterations within a protected structure

•            Conservation works to existing fabric of a protected structure

•            Protection of elements of architectural and historic significance as the works proceed

•            Lime plaster works

•	Removal of hazardous materials from site

•	Proposed waste management

•	Maintenance of third party right of way across site

•	Liaising with residents of neighbouring buildings

•	Excavations under Archaeological Supervision

•	Excavation next to and underpinning existing structures

•	Demonstrate experience in low carbon construction methods

Insert Text below: (Max 8,000 Characters, Calibri size 12 font)

Criterion 2: Contractor's Programme (80 Marks)

Provide a detailed PW-CF5 (clause 4.9.1) compliant programme in the form of an A1 Critical Path Gantt chart that demonstrates how you will manage the programme, including pre-construction and construction sequencing requirements. The programme should clearly indicate key tasks during pre-construction, works delivery and handover stages and show the critical path, float, time risk allowances, dependent tasks and resource allocations having regard to the requirements of the Inspection Plan and Inspection Notification Framework. The programme shall be of a quality that will permit effective monitoring of the Works in accordance with the project duration set out in the Tender and Schedule and shall include details of all of the following:

(1) when the Contractor will require any instructions, Works Items or other things to be given by the Employer, or anything else the Contract requires the Employer, the Employer’s Representative or others to give the Contractor

(2) the order in which and times at which the Contractor proposes to execute the Works, including details of procurement, manufacture, delivery, installation, construction, testing, commissioning and trial operation of Works Items and the sequencing and timing of inspections and of tests

(3) when Contractor’s Documents will be submitted to the Employer’s Representative

(4) the Contractor’s estimate of each category of Contractor’s Personnel and Contractor’s Things expected to be on Site for each period

(5) work to be carried out at the Site by Employer’s Personnel and others as provided in the Works Requirements

(6) current critical path, critical resources, floats and other flexibility

(7) allowance for co-ordination with M&E services

(8) Date for all fabrication drawings including for precast, steelwork, roof details, windows including drawings of all junctions, stairs, furniture etc.

(9) Inputs from Services Providers (ESB, EIR, IW etc)

(10) anything else required by the Works Requirements.

(11) reasonable periods of time for the Employer and the Employer’s Personnel to comply with their obligations under the Contract.

The Gantt chart, responding to this Criterion 2 should be provided as a separate PDF attachment.

Tenderers are to base their programme on an INDICATIVE letter of acceptance date of 1st October 2026 and identify any annual holidays within same. On appointment, the programme will be adjusted to reflect the contract award date and start on site date.

NOTE: Tenders will be assessed on how their programme demonstrates operational rationale, completeness and approach, and viability of the programme deliverables.

Criterion 3: Quality and Compliance (40 Marks)

The Tenderer is requested to provide a statement outlining the intended approach to quality management and building control requirements for this project. This statement should clearly describe the tenderer’s approach to quality, compliance, co-ordination and collaboration with the Design Team to ensure the quality of materials and finishes is not compromised and the successful delivery of the works requirements. This statement should outline the following, at a minimum (but not limited to): -

- Tests and procedures for productions and workmanship

- Protocol and procedures regarding material/system proposals, sampling and substitution (datasheets, DOPs & testing information, etc)

- Selection of subcontractors

- Proposed procedure for information control on site

- Site specific methodology of information storage and transfer, examples of proposed folder structures/ storage strategy

- Control of workmanship and identify procedure for dealing with non-compliant work identified in inspection reports

- Methodology for the ancillary certifiers in carrying out inspections, recording and reporting on matters identified in the PIP.

- Handover methodology including the contractor’s approach to the coordination of Testing and Commissioning

Insert Text below: (Max 8,000 Characters, Calibri size 12 font)

Criterion 4: Health and Safety (40 Marks)

Sub Criterion 4a: (10 marks)

Provide details of your company’s existing Health and Safety systems

Insert Text below: (Max 4,000 Characters, Calibri size 12 font)

Sub Criterion 4b: (30 marks)

The Tenderer is requested to demonstrate their approach to Health & Safety on site, particularly the relevant H&S challenges within this site, under the Safety Health and Welfare at Work (Construction) Regulations 2013

Insert Text below: (Max 4,000 Characters, Calibri size 12 font)