Background and Introduction

Coolcormack Valley GWS comprises of a single drilled and lined borehole well, secured pumphouse, water treatment equipment and approximately 750m of 110 mm water distribution pipework serving 35 houses. Approximately 25 of these houses are permanently occupied. While there are no individual water metres installed at each connection, there is a bulk metre located within the pumphouse.

Coolcormack Valley GWS requires the services of a competent and experienced Consulting Engineer (“the Engineer”) with experience in Civil Engineering works in water distribution systems in Group Water Schemes and Public Water Schemes.

The Engineer will carry out the assessment, design, procurement, and project manage the necessary works, as described below.

Connection of the Group Water Scheme mains to Uisce Eireann network.

An options report identified the connection of the GWS to Uisce Eireann’s network as the preferred solution from an economical and practical point of view. Coolcormack Valley GWS is within sufficient proximity to the public mains and with favourable topography for their connection to be technically and economically viable.

Uisce Eireann has confirmed that a connection is feasible by letter dated 3rd March 2023 with UE ref number CDS23000444 Pre-Connection Enquiry, Coolcormack Valley, Dungarvan, Co. Waterford.

Scope of Works

The Engineer is required to submit a Fee Proposal for the following works.

- The Scheme has 35 domestic connections; with c. 25 of the houses permanently occupied. Basic bulk metered water demand information is available from the single bulk metre installed in the pumphouse. Average GWS water usage is recorded by the GWS SCADA System.

- Flows will need to be monitored and assessed for a timeframe to identify overall unaccounted for water.

- An assessment of the scheme’s infrastructure is required, identifying if any additional infrastructure is required to meet Uisce Eireann’s Taking in Charge requirements.

- The design of the connection pipework will also consider pressure assessments, and capacity to deal with additional demand at peak periods.

- The length of pipework required to join both networks is estimated to be 1260 linear metres.

- At all process stages the protocols and procedures of Uisce Erinn must be adhered to for this scheme to be taken in charge to include but not limited to Irish Water Connections and Developer Services Standard Details and Codes of Practice.

The identified works to be the basis of the Fee Proposal

- Assess daily water demand, UFW and existing GWS infrastructure.

- Replacement of existing, or installation of new, valves, meters etc. Where required to meet Uisce Eireann’s requirements.

- Complete all paperwork required for the Take Over process.

- Laying new interconnecting pipework between the GWS mains and Uisce Eireann’s network.

- Installation of booster pumps if required, (subject to network analysis by the Engineer).

- Decommissioning of existing pumphouse and water treatment equipment.

- Finalise the handover of the scheme along with all required documents, drawings for UE taken in charge protocols

Scope of Services of the Consulting Engineer

An Consulting Engineer is required for all stages of the project as set out below, the project stages consist of the following: -

- Preliminary;

- Design;

- Tender Activation, Evaluation and Award;

- Construction

- Handover and Final Completion

For all stages the Engineer will be required to engage with the Group Water Scheme and the Rural Water Section of Waterford County Council as necessary for the proper completion of the project.

The scope of the anticipated services required under each stage are set out under.

Stage 1 – Preliminary.

- Carry out as necessary an assessment of existing data.

- Work with the local authority and group water scheme to verify the details of all existing water mains, valves, meters and consumer connections. Ensure that GPS co-ordinates are recorded and available for all valves, meters and consumer connections. Update scheme mapping where required.

- Collate all the existing bulk meter and water consumption data for the scheme network and assess the requirement for additional valves, meters etc. that are required for the TIC by UE. Update scheme mapping where required.

- Carry out pressure monitoring at various locations to identify if the proposed connection will supply minimum required pressure to all connections.

- Prepare estimated project costs.

Stage 2 – Design.

- Procure and manage the required Site Investigation works, if required.

- Carry out the detailed design and prepare detailed projected costs.

- Fulfil all obligations under current Health & Safety legislation. Carry out role of Project Supervisor Design Process (PSDP).

- Prepare a Preliminary Health and Safety Plan and develop the Safety File in accordance with Safety, Health & Welfare at work Act 2005 and Safety, Health and Welfare at Work (Construction) Regulations 2013 and all other relevant legislation, regulations and codes of practices.

Stage 3 – Tender Activation, Evaluation and Award.

- Manage the tender process generally in line with current procurement legislation.

- Preparation of tender documents for construction works for approval by Waterford County Council.

- Preparation Notices and advertisements.

- Procurement of civil contractor, mechanical and electrical contractor, (if required), respond to all reasonable queries from tenderers, preparation of tender assessment reports and recommend an appointment based on the most economically advantageous tender for consideration and approval by Waterford County Council;

- Assessment of insurances and contract signing.

Stage 4 - Construction.

- Transfer the role of PSDP to the successful contractor in accordance with Safety, Health & Welfare at work Act 2005 and Safety, Health & Welfare at Work (Construction) Regulations 2013 and all other relevant regulations and legislation.

- Carryout a supervisory role on behalf of the GWS for the duration of the construction and commissioning of the works, including administration of the contract, approval of all materials, site visits and meetings and certification of works; and certification of payments.

- Advise on any claims and settlement thereof.

Stage 5 - Handover and Final Completion

- Develop the Safety File in accordance with Safety, Health & Welfare at work Act 2005 and Safety, Health and Welfare at Work (Construction) Regulations 2013 and all other relevant legislation, regulations and codes of practices.

- This shall include the provision of As-Constructed Drawings which must include all pipe networks with GPS coordinates of all valves, meters and customer meters etc. The template to be agreed with Uisce Eireann.

- Prepare detailed customer database to be provided to Uisce Eireann, template provided by Local Authority.

- Preparation of Handover Report.

- Preparation of Final Account.

- Decommissioning of existing GWS pumphouse, treatment and source.

Fee proposal

The price provided by the Engineer for the project must be given as a Lump Sum Fixed Price. The Lump Sum Price to include any other item of work or service that the Engineer deems necessary or desirable for the purposeful delivery of all stages of the project.

Design works should be completed within three months from appointment to facilitate completion of the project within a desired timeframe.

1. Site Investigation and Design – 40%

2. Tender Activation, Evaluation and Award – 25%

3. Construction – 30%

4. Handover & Defects Resolution – 5%

5. TECHNICAL PROPOSAL

A technical proposal shall be submitted in accordance with the Award Criteria Document.

The Key Team Members submitted as part of the Technical Proposal shall be responsible for the Project delivery. The Consultant may not make changes to Key Team Members without the prior approval of the Client. Any changes shall demonstrate an equivalent level of experience, knowledge and training as the original resource.

Application to the Client for approval must be made no later than a month before the proposed change is to occur, unless the Client agrees to a shorter notice period. The Consultant must provide the name and curriculum vitae of the proposed substitute personnel together with any other details requested by the Client.

The Client may refuse to accept any proposed substitute and in such a case, the Consultant shall submit to the Client further names and curricula vitae of other proposed substitute personnel within a period specified by the Client but no proposed substitute shall be engaged in respect of the Services unless and until approved by the Client.

- TIMESCALE

The following are the specified timescales for delivery of services, all timescales from award date:

• Preliminary route assessment, SI assessment and site investigation – 2 months.

• Completion of detailed design – 3 months

• Completion of tender documents and issue of documents to the market – 4months

• Contract Award – 5 months

• Contract Completion 18 months

- INSURANCE

The following Limits (of Indemnity) shall be in place by the Consultant’s and copies of insurance certificates shall be provided if requested:

• Public Liability - €6,500,000 Any One Claim

• Employer’s Liability - €13,000,000 Any One Claim

• Professional Indemnity Insurance – A sum not less than €1,000,000 Any one claim and unlimited in the period of insurance

- PSDP ASSESSMENT

It is a requirement of the Local Authority acting as Client to make reasonable enquiries to determine the suitability of the Consultant to be appointed as Project Supervisor Design Process (PSDP). The proposed Consultant will have to complete a PSDP questionnaire prior to award being made to demonstrate they have the required knowledge, training and experience to fulfil the role. If the Consultant fails to satisfactorily complete this questionnaire, the tenderer will be excluded from the tender competition.

- AWARD CRITERIA

The Award Criteria for the contract shall be the Most Economically Advantageous Tender (MEAT). The Most Economically Advantageous Tender is the tender with the highest score once the marks awarded under all award criteria are totalled in accordance with the Award Criteria document.

The tender shall be awarded on 40:60 Quality: Price ratio with 6000 marks for price and 4000 marks for Quality

Tenders will be evaluated against the quality criteria set out in the Particulars.

Any Tenderer:

(i) Not passing on a ‘pass / fail’ criterion, or

(ii) achieving less than 40% of the maximum marks on an individual ‘quality’ criterion or

(iii) achieving less than 50% of the total available quality marks will be excluded from further consideration