## Pricing Summary
Rossmore Memorial Fountain — Remedial Conservation Works
Pricing Summary — Schedule of Works and Pricing Document
Contracting Authority: Monaghan County Council ¦ Conservation Consultant: Carrig Conservation International
Rates to be completed by the tenderer in the 'Schedule of Works' sheet; the amounts below link automatically.
Section | Description | Amount (€)
A | Preliminaries And Site Establishment (Contractor'S General Items)
B | Recording, Investigation, Analysis And Trials
C | Priority 1 — Safety-Critical Stabilisation: Vault Soffit
D | Priority 1 — Safety-Critical Stabilisation: Heraldic Plaques
E | Priority 2 — Lower Internal Capitals
F | Priority 2 — Column Bases, Plinth Interface And Drainage
G | Priority 3 — Planned Conservation Works
H | Completion, Records And Handover
TOTAL (excl. VAT)
VAT at 13.5%
TOTAL (incl. VAT)
Tenderer:
Signed / Date:
Green figures link from the 'Schedule of Works' sheet. Complete the yellow Rate cells on that sheet; all totals calculate automatically.

## Schedule of Works
Rossmore Memorial Fountain, The Diamond, Monaghan — Remedial Conservation Works
Schedule of Works and Pricing Document — items in order of priority. To be read with the Conservation Specification and Outline Conservation Method Statement.
LEGEND — Yellow cells: to be completed by the tenderer (rates). Amounts and subtotals calculate automatically. Items marked 'Rate only' will be executed only as instructed by the Employer's Representative; the tendered unit rates will apply.
EXAMPLE (format only — not part of the tender): Unit 'Item', Qty 1, Rate €5,000.00 → Amount shows €5,000.00 automatically.
Item | Element / Location | Description of Works | Spec ref | Unit | Qty | Rate (€) | Amount (€)
SECTION A — PRELIMINARIES AND SITE ESTABLISHMENT (CONTRACTOR'S GENERAL ITEMS)
A1 | Whole site | Site establishment: compound, welfare, storage, licences, utilities; management and supervision for the contract duration | MS 5.3 | Item | 1
A2 | Whole site | PSCS role: construction stage safety & health plan, coordination, safety file contributions | Spec 2.4 | Item | 1
A3 | Vaulted interior | Interim overhead protection (crash deck or equivalent) to the vaulted interior — FIRST SITE ACTIVITY, before scaffold erection; maintain until release at Hold Point H7 | Spec 4.2 | Item | 1
A4 | Whole monument | Independent free-standing scaffold: erection, fully boarded lifts, debris netting, weather protection, controlled access, alarm; no ties/fixings into historic fabric; adaptation for phased works; hire for contract duration; dismantling | Spec 4.1, 4.3 | Item | 1
A5 | Public square | Hoarding, pedestrian barriers, signage, lighting; maintenance of safe public circulation routes for contract duration | Spec 4.1 | Item | 1
A6 | Polished stone & paving | Protection of polished granodiorite and granite elements (steps, columns, basin, central column) and limestone paving throughout the works | Spec 4.4 | Item | 1
A7 | Whole site | Water management: control, collection and lawful disposal of cleaning water; screening of dust/spray | Spec 4.5 | Item | 1
A8 | Whole site | Insurances and bond as required by the Contract | Contract | Item | 1
A9 | Whole site | Demobilisation: removal of all temporary works, completion cleaning, making good, joint completion inspection | Spec 7.14 | Item | 1
Subtotal — Section A
SECTION B — RECORDING, INVESTIGATION, ANALYSIS AND TRIALS
B1 | Whole monument | Photographic recording before/during/after; detailed recording of each carved capital and heraldic plaque; photogrammetry where directed | Spec 5.1 | Item | 1
B2 | Vault soffit | Facilitation of and attendance on conservation-accredited structural engineer's inspection [engineer appointment side TBC] | Spec 5.2 | Item | 1
B3 | Superstructure | Moisture ingress investigation: tracing of water pathways to vault soffit and plaque recesses; minimal approved opening-up and reinstatement | Spec 5.3 | Item | 1
B4 | Whole monument | Mortar analysis to I.S. EN 17187 — rate per sample; number of samples as directed | Spec 5.4a | No. | Rate only
B5 | Whole monument | Petrographic examination of detached fragments to confirm stone types | Spec 5.4b | Item | 1
B6 | Heraldic plaques | Analysis of historic 1905 surface treatment: composition and moisture behaviour | Spec 5.4c | Item | 1
B7 | Various | Trials T1–T8 complete as Appendix A of the Conservation Specification, including making good | Spec App A | Item | 1
Subtotal — Section B
SECTION C — PRIORITY 1 — SAFETY-CRITICAL STABILISATION: VAULT SOFFIT
C1 | Vault soffit | Slab-by-slab recording of crack patterns, delamination planes and bearings | Spec 5.1 | Item | 1
C2 | Vault soffit | Controlled hand removal of loose and imminently unstable fragments; cataloguing and secure storage of retained fragments | Spec 7.9.1, 3.5 | Item | 1
C3 | Vault soffit | Localised consolidation of friable/delaminating sandstone with approved mineral consolidant, following trial T5 | Spec 7.6 | m² | Rate only
C4 | Vault soffit | Pinning/dowelling of cracked slabs in grade 316 stainless dowels set in lime grout, to engineer's design | Spec 7.9.2 | No. | Rate only
C5 | Above vault | Raking out and lime repointing of joints above vault slabs; repair of identified moisture ingress pathways | Spec 7.4, 7.5 | Item | 1
C6 | Vault soffit | Stone replacement (last resort only, as directed): matched stone incl. Y-profile — rate per stone | Spec 7.10 | No. | Rate only
Subtotal — Section C
SECTION D — PRIORITY 1 — SAFETY-CRITICAL STABILISATION: HERALDIC PLAQUES
D1 | Heraldic plaques | High-resolution recording and specialist condition assessment of each plaque ('blue Cumberland stone') | Spec 5.1 | Item | 1
D2 | Heraldic plaques | Careful hand removal of delaminating, imminently unstable fragments; retention and cataloguing | Spec 7.9.1 | Item | 1
D3 | Heraldic plaques | Trial-led reduction/removal of historic surface treatment ONLY if directed following analysis | Spec 7.8 | m² | Rate only
D4 | Heraldic plaques | Localised consolidation with approved mineral consolidant following trial | Spec 7.6 | m² | Rate only
D5 | Heraldic plaques | Discreet lime/mineral infill of voids and water-traps only (no re-carving); toned to adjacent stone | Spec 7.7 | Item | 1
D6 | Above plaques | Discreet water-shedding improvements above plaque level (joints; lead or stone details as approved) | Spec 7.11 | Item | 1
Subtotal — Section D
SECTION E — PRIORITY 2 — LOWER INTERNAL CAPITALS
E1 | Internal capitals | Controlled low-impact cleaning of 8 no. carved foliate capitals (soft brush, low-pressure misting), fragile areas under conservator supervision | Spec 7.1 | No. | 8
E2 | Internal capitals | Measures to improve drying potential at internal faces, as directed | MS 5.6 | Item | 1
E3 | Internal capitals | Localised consolidation of friable areas following trial | Spec 7.6 | m² | Rate only
E4 | Internal capitals | Minimal edge-protection plastic repairs to vulnerable arrises/undercuts only (no replication of lost detail) | Spec 7.7 | Item | 1
Subtotal — Section E
SECTION F — PRIORITY 2 — COLUMN BASES, PLINTH INTERFACE AND DRAINAGE
F1 | Base interfaces | Investigation of ground levels, falls and water pathways at column bases | Spec 5.3 | Item | 1
F2 | Base interfaces | Careful hand removal of failed/cementitious patch repairs | Spec 7.3 | Item | 1
F3 | Base interfaces | Raking out and lime repointing of open/defective joints at bases and plinth interface | Spec 7.4, 7.5 | m | Rate only
F4 | Base interfaces | Discreet lime/mineral repairs to localised losses; retention of sound sympathetic repairs | Spec 7.7 | Item | 1
F5 | Base interfaces | Subtle reversible drainage improvements to falls/joint profiles at plinth-column interface | Spec 7.11 | Item | 1
F6 | Base cracks / vault | Supply and install crack monitoring (tell-tales); baseline readings | Spec 7.13 | Item | 1
Subtotal — Section F
SECTION G — PRIORITY 3 — PLANNED CONSERVATION WORKS
G1 | Outer arches & gables | Conservative cleaning; hand removal of vegetation with full root extraction; localised lime repointing | Spec 7.1, 7.2, 7.5 | Item | 1
G2 | Outer arches & gables | Re-bedding/re-fixing of displaced hemispherical bosses; limited evidence-based repair of boss detail | Spec 7.7.3 | No. | Rate only
G3 | Outer arches & gables | Discreet water-shedding details at gable junctions (lead or stone, as approved by mock-up) | Spec 7.11 | Item | 1
G4 | Upper body & shields | Gentle cleaning; localised lime repointing of open joints; record mechanically-keyed historic repair locations | Spec 7.1, 7.5 | Item | 1
G5 | Fountain assembly | Record and discreet make-good at missing spout location; trial cleaning of basin staining (retain patina) | Spec 7.7, 7.1 | Item | 1
G6 | Fountain assembly | Survey, drain, cap and make safe redundant pipework without disturbance of fabric | Spec 7.12 | Item | 1
G7 | Pinnacle & colonnade | Light conservative cleaning where visually intrusive; inspection of earlier repairs and stainless tie | Spec 7.1 | Item | 1
G8 | Plinth & paving | Careful cleaning avoiding joint damage; minor maintenance repairs | Spec 7.1 | Item | 1
Subtotal — Section G
SECTION H — COMPLETION, RECORDS AND HANDOVER
H1 | Whole monument | Repairs register, final photographic record, as-executed schedules, product/batch data, analysis and trial results, fragment catalogue | Spec 7.15 | Item | 1
H2 | Whole monument | Contribution to 10-year cyclical inspection and maintenance plan | Spec 7.15 | Item | 1
Subtotal — Section H
TOTAL CARRIED TO SUMMARY (excl. VAT)
Notes: Items marked 'Rate only' will be instructed only as directed during the works; the tendered unit rates will apply. No provisional sums or contingency sums are included in this pricing document.