## Trade Breakup Showing Markup
Bill Ref. | Description | Quantity | Unit | Rate | Markup (%) | Total
(00) PRELIMINARY PARTICULARS
PROJECT, PARTIES AND CONSULTANTS
Name, nature and location of the Project
1A | Kilglass National School is located at Ahascragh, Ballinasloe, Co. Galway, H53 PC94. The works are situated to the rear of the existing building |  | note |  | 0 | 0
General Description of the Works
1B | The works will include the proposed alterations to existing treatment systems and sequential installation of new PE26 Proprietary Wastewater Treatment Plant and TER3 Packaged Tertiary Treatment system to design; all necessary site works and services |  | note |  | 0 | 0
The works are constructed in 1 phase, to the following sequences
1C | 1) Site setup and full panel hoarding of the new site compound. |  | note |  | 0 | 0
1D | 2) Existing Septic Tank to be decommissioned |  | note |  | 0 | 0
1E | 3) Existing trees and tree roots to be removed |  | note |  | 0 | 0
1F | 4) Existing percolation area to be removed |  | note |  | 0 | 0
1G | 5) Construct PE26 Proprietary Wastewater Treatment system |  | note |  | 0 | 0
1H | 6) Construct a new TER3 Packaged Tertiary Treatment system together with a full percolation area to design; all necessary site works and services |  | note |  | 0 | 0
2A | 7) Test and commission system. Reinstate entrance surfacing on completion |  | note |  | 0 | 0
Names and addresses of the Employer and Consultants
2B | Employer: Board of Management, Kilglass National School, Ahascragh, Ballinasloe, Co. Galway, H53 PC94. |  | note |  | 0 | 0
2C | Employers Representatives: Coyle Environmental Limited, Kilmurry House, Main Street, Castlerea, County Roscommon |  | note |  | 0 | 0
2D | Tel: + (0)94 9621258 |  | note |  | 0 | 0
2E | E-mail: info@coyleenv.ie |  | note |  | 0 | 0
2F | Architect: Not applicable |  | note |  | 0 | 0
2G | Structural Engineers: Coyle Environmental Limited, Kilmurry House, Main Street, Castlerea, County Roscommon |  | note |  | 0 | 0
2H | Tel: + (0)94 9621258 |  | note |  | 0 | 0
2J | E-mail: info@coyleenv.ie |  | note |  | 0 | 0
2K | Service Engineers: Not applicable |  | note |  | 0 | 0
2L | Quantity Surveyors: Modern Eco Projects Ltd., Drummin South, Crossboyne, Claremorris, Co. Mayo |  | note |  | 0 | 0
2M | E-mail: info@modernecoprojects.ie |  | note |  | 0 | 0
Convenience of Others
3A | The Contractor shall consult all persons who may be affected by the work, with regard to suitable times for making deliveries and all other matters affecting them.The existing entrance and tarmac playground area of the existing school will remain clear, free and unobstructed for the duration of the project. Limited access may be agreed with the Employers Representative to utilise the area during the holidays. All access to the existing school or its environs is strictly prohibited, except by controlled and prearranged permission, to include as a minimum Garda Vetting under the Childcare and Welfare Act. |  | item |  | 0 | 0
3B | The contractor is further reminded that the existing school building will remain in use during the proposed works. The contractor is to remain cognisant of this when preparing and scheduling deliveries and removals from the site. The extent of limitations, arising from the daily school program, is identified in the Employer's Obligation and Restrictions sections |  | item |  | 0 | 0
Preliminary Investigation
4A | Contractors shall be deemed to have visited the site before submitting their tender and to have satisfied themselves as to the means of communication, access, extent of the work, nature of the site and the existing services and buildings and all conditions under which the works will be carried out together with the conditions effecting the supply of labour and materials and all other matters which may effect the tender. No claims based on the lack of any such knowledge will be entertained. The Contractor should visit the site to ascertain site conditions. |  | note |  | 0 | 0
DESCRIPTION OF THE SITE
Boundaries
4B | The building work will be contained to within the confines of the existing site boundaries as indicated on the Engineers site layout drawings. The Contractor is obliged to establish all work perimeters by visiting this site. |  | item |  | 0 | 0
Location of and Access to Site
4C | The site is situated to the rear of the school building. Access to the site for the work shall be via the gate on the roadside; as per Site Location Drawing 01 and Site Layout drawing 02. |  | item |  | 0 | 0
Protection of Existing Building and Adjoining Properties
5A | The Contractor should note the proximity of existing buildings, roadways and ongoing developments etc. and allow for any additional costs associated for restrictions/difficulties as a consequence of working adjacent to same |  | item |  | 0 | 0
5B | The Contractor shall be held solely responsible for the safety of the existing and adjoining properties and the safety of all temporary work that may be necessary for the protection, safety and stability of the existing properties while carrying out the works. The Contractor shall be responsible for making good any damage caused and to minimise disturbance to the activities and occupants from dust, excessive noise and other interference arising from the works. |  | item |  | 0 | 0
5C | Particular attention will be required to abutments with existing buildings, paths, roads, adjoining walls, fences etc during the course of the work. |  | item |  | 0 | 0
Existing Services
6A | The information in the Contract as to the existence and whereabouts of existing services and mains is believed to be correct but the Contractor shall not be relieved of his obligations under the Contract. The Contractor shall include in his rates and prices for locating and taking measures for the support and full protection of pipes, cables and other apparatus during the progress of the works obtaining the written consent of the appropriate authority to interrupt the service or supply and for keeping the relevant Local Authorities informed of all arrangements he makes with the owners of privately owned services or supplies, Statutory Undertakers and Public Authorities as appropriate. |  | item |  | 0 | 0
6B | The Contractor shall allow in his rates and prices for taking measures to deal with overhead power cables, and the like. |  | item |  | 0 | 0
6C | The Contractor shall do everything necessary to avoid damage to any services and structures below, on or above the ground, which are manifestly put at risk by the execution of the works. |  | item |  | 0 | 0
7A | The Contractor shall fully satisfy himself as to the exact location of all existing services. The Contractor should contact the Electricity Supply Board, Bord Gais, Telecom Eireann and Local Authorities in relation to power cables, gas pipes, telephone cables, cable T.V. routes, drains and watermains in advance of any excavation or opening up work and formulate a contingency plan to ensure an immediate emergency response by the relevant bodies in the event than such services are damaged. |  | item |  | 0 | 0
7B | The contingency plan must be approved in advance by the Engineer and will include the names and contact numbers to affect immediate responses to restore and maintain services. The Contractor will advise the relevant bodies in advance of commencing excavation or opening up work of the dates on which such services may be risk. Where deemed necessary a representative or emergency crew as appropriate will be in attendance where any particular service is at risk. |  | item |  | 0 | 0
DRAWINGS AND OTHER DOCUMENTS
The following will form part of the Contract and a copy of each is issued with the tender documents
Drawings and other documents from which tenders are requested
7C | Preliminary Health and Safety Plan |  | item |  | 0 | 0
7D | Pricing document |  | item |  | 0 | 0
7E | Programme |  | item |  | 0 | 0
7F | Model forms |  | item |  | 0 | 0
8A | Additional work items |  | item |  | 0 | 0
Architect's Drawings and Documents
8B | Not applicable |  | item |  | 0 | 0
Structural Engineers Drawings and Documents
8C | Drawings; See Engineers tender list |  | item |  | 0 | 0
8D | Structural Engineer's Specification |  | item |  | 0 | 0
CONTRACT
FORM, TYPE AND CONDITIONS OF CONTRACT
Standard Forms of Contract
8E | There should be no amendments made to any of the five public works contracts, or the contract Model Forms except to fill in the blank spaces provided. The Department of Finance's circular 33/06 7(a) states: 'In line with Government policy, the new Forms of Construction Contracts are to be the norm and no amendments should be made to them. In this context, the new Forms of Construction Contracts have been drafted in a way that better protects the public sector client's interest in order to achieve value for money outcomes from public expenditure on public works projects.' |  | note |  | 0 | 0
Conditions of Contract
8F | The Conditions of Contract are the current edition of the short form Public Works Contract |  | note |  | 0 | 0
8G | Reference: PWC CF6 V1.15 - 25th November 2025 |  | note |  | 0 | 0
9A | The Contractor must fill in the appropriate sections of the Contract Schedule as detailed in same in order to submit a bonafide Tender. The Tenderer must return a fully priced Pricing Document in INK with the Form of Tender. |  | note |  | 0 | 0
9B | The successful Contractor shall execute an agreement with the Employer in the Form of the Articles of Agreement exhibited to tenders as detailed in the short public works contract |  | note |  | 0 | 0
CONTRACTORS LIABILITY
Particular Insurance Requirements
9C | Public and employers Liability insurance for a minimum limit of indemnity of: See Schedule 10.3 and 10.4 |  | item |  | 0 | 0
9D | The Contractor shall secure prior to commencement and maintain for the duration of the Contract or up to Substantial Completion or the making good of defects at Final Completion as the case may be, all of the insurance to be provided by virtue of his obligation under the Conditions of Contract and to values not less than those designated. |  | item |  | 0 | 0
9E | The Contractor shall submit evidence to the Employer in accordance with the provisions of the Contract that the required Insurance are in effect prior to commencement of the works. |  | item |  | 0 | 0
9F | The Contractor shall cover for loss due to malicious damage in the scope of the All Risks Insurance required in the Conditions of Contract |  | item |  | 0 | 0
CONSENTS, FEES AND CHARGES
10A | The Contractor is to include for all costs associated with all Consents required to complete the works |  | item |  | 0 | 0
10B | The contractor is to provide all necessary traffic management systems in accordance with the Engineers specifications while working on public roads, or accessing the site. |  | item |  | 0 | 0
10C | The contractor is to source all licences, charges and permissionsand pay all costs in relation to those licences, charges and permissions required to facilitate the progress of the works. We refer to specifically but not exclusively to Road Opening Licences, Rates, Hoarding Licences, Parking Space Charces, Temporary Road closures, service connections, waste management licences and the like |  | item |  | 0 | 0
OBLIGATIONS AND RESTRICTIONS IMPOSED BY THE EMPLOYER
Building Regulations
10D | The Contractor shall carry out the works in accordance with the provisions of the current Building Regulations incorporating any amendment thereto which shall relate to the works. The Contractor shall inform the Engineer of any specific requirement of the drawings or specification which he considers to be in contravention of the Building Regulations and the Engineer shall take account of the Contractors submission and issue instructions accordingly as he shall see fit. |  | note |  | 0 | 0
Limitations of the Site
11A | The Contractor must confine his operation within the immediate area covered by the works as shown on drawing Site Layout Plan and will make good at his own expense any damage to buildings, grounds, roads, or shrubbery occasioned through negligence or non-observance of this clause. |  | item |  | 0 | 0
11B | See convenience of occupants above |  | item |  | 0 | 0
11C | The contractor must ensure that adequate safety precautions are taken when working in the vicinity of overhead lines. These may include the provision of goal-post type barriers on each side of the overhead line and the non-use of scaffolding or ladders within 10 meters of the overhead line. |  | item |  | 0 | 0
11D | The Contractor shall be responsible for the maintenance and upkeep of the entrance road, existing footpath and environs, and shall at all times leave the road and footpath at the entrance free and unobstructed. No materials will be stored, temporarily placed or discarded outside the site boundary at any time, where this would cause obstruction to residents or those using the locality. The Contractor will be required to brush and hose down the access road and footpath at regular intervals and as instructed or directed by the Engineer. |  | item |  | 0 | 0
12A | In order to comply with the adjoining residents rights to quiet enjoyment of their building and to keep any disruption to a minimum, advanced notice must be given where the noise levels will cause disruption |  | item |  | 0 | 0
12B | The works shall be carried out in such a way as to cause the minimum of inconvenience to the general public and the neighbouring residents. |  | item |  | 0 | 0
12C | The statutory requirements relating to control levels of noise of the works must be strictly observed (see BS8233). The acceptable internal noise level between 8am to 6pm is restricted to 55dB(A). |  | item |  | 0 | 0
12D | Note: Work above 55dB (A) will have to be undertaken outside normal working hours which will have to be included in the tender sum |  | item |  | 0 | 0
Limitations of Working Hours
Scheduled School Times
12E | Monday to Friday: 9.00am - 4.15pm |  | note |  | 0 | 0
12F | Lunchtime: Children remain in school grounds |  | note |  | 0 | 0
Scheduled School Holidays
12G | Summer Offical Closing: TBC |  | note |  | 0 | 0
12H | Working hours are at the discretion of the Contractor but should be agreed with the Employer before commencement of the works and should comply with the noise and vibration restrictions above. |  | note |  | 0 | 0
13A | The Contractor shall herewith allow for any costs involved in complying with the limitations previously noted under convenience of occupants |  | item |  | 0 | 0
STATUTORY OBLIGATIONS
Tax Clearance
13B | It will be a condition for the award of this Contract that a firm must comply with the Tax Clearance Procedures for Public Sector Contracts, Ref Contract Conditions for full details of compliance requirements |  | note |  | 0 | 0
13C | It will be a condition for the award of this contract that a firm must be able to produce promptly a Tax Clearance Certificate (unless he has a sub-contractors C2 Certificate). In the case of a non-resident, a statement from the Revenue Commissioners will be required. |  | note |  | 0 | 0
MANAGEMENT OF WORKS
General
13D | The Contractor is to note and to comply with all the statutory obligations and regulations in connection with all items as noted in the Preliminaries, Agreed Rules of Measurement 4 |  | item |  | 0 | 0
Supervision and Co-ordination of the Works
13E | Provide for all on and off site management costs |  | item |  | 0 | 0
14A | The Contractor will be required as one of the Conditions of Contract to appoint on a full time basis an experienced and competent Project Manager, approved by the Employer's Representative, whose sole duties will be the management of the job on the Contractor's behalf. The person selected by the Contractor for this position will be a member of the Contractor's staff who has already had experience of acting in a similar capacity on a job of similar size and complexity to that of this development. |  | item |  | 0 | 0
His duties will include the following:
14B | (a) The preparation and keeping up to date of a programme which will incorporate the activities of all those participating in the Contract, this programme to be continuously developed and amended as the list of Sub-Contractors grows and agreements on dates and times are made. |  | item |  | 0 | 0
14C | (b) The organisation of formal site meetings which will be attended by the Employer's representative, Consultants and any Sub-Contractor whose presence for the discussion of some particular aspect of the job would be desired. The Employer's Representative will be responsible for calling and chairing the formal site meetings and will keep and circulate the minutes. |  | item |  | 0 | 0
15A | (c) The organisation of ad hoc informal meetings attended by all or some of the main participants in the project. Such meetings may be called at the instigation/request of the Engineer for the purpose of dealing with problems which may require immediate attention or are of too detailed a nature to be discussed at the site meetings. |  | item |  | 0 | 0
15B | (d) Liaison between the Employer's Representative and Sub-Contractors |  | item |  | 0 | 0
Site Administration
15C | Provide for all necessary on and off site administration costs including the keeping of all statutory records |  | item |  | 0 | 0
Transport for Workpeople
15D | Provide all necessary transport for workpeople and temporary carparking onsite. |  | item |  | 0 | 0
MATERIALS
Site Records
15E | The Contractor shall keep fully detailed daily records of all plant and labour force, identifying their occupation, trade and status and materials used on site (including manufacturers certificates). |  | item |  | 0 | 0
15F | The Contractor shall keep detailed dated records of the progress of the works, and where directed by the specification, of dimensions of completed works. |  | item |  | 0 | 0
16A | The Contractor shall keep a daily record of weather conditions including the maximum, minimum and average outside shade temperatures, humidity and wind speed. Records should record changes in conditions which occur within any one day. |  | item |  | 0 | 0
16B | The Contractor may be required to liaise with local contractors, organizations / residents, etc., during the course of the works. The Contractor is to include here for all costs involved in this regard. |  | item |  | 0 | 0
As Built Drawings
16C | Upon completion of the works the Contractors will be required to furnish our clients with a full set of 'As Built Drawings' complete in hard and soft copy format. This documentation is deemed to include all associated manuals, instructions, guarantees etc. |  | item |  | 0 | 0
Taking in Charge
16D | It is intended at some future date that the works will be formally taken in charge by the Primary School Board of Management. Accordingly the contractor is required to liaise with the Primary School Board of Management during the course of the works to ensure that the works are in compliance with the relevant the Primary School Board of Management standards for the purpose of taking in charge. |  | item |  | 0 | 0
Access to site and workshops for Employer's Representative
17A | The Employer's Representative and any person authorised by him shall at all reasonable times have access to the works and to the site and to all workshops and places where work is being prepared or where materials, manufactured articles and machinery are being obtained for the works, and the Contractor shall afford every facility for and every assistance in or in obtaining the right to such access. |  | item |  | 0 | 0
LABOUR
Disbursements arising from the Employment of Workpeople
Provide for all costs in respect of all workmen for:-
17B | (a) Pay Related Social Insurance Contributions |  | item |  | 0 | 0
17C | (b) Pensions |  | item |  | 0 | 0
17D | (c) Annual and Public Holidays |  | item |  | 0 | 0
17E | (d) Travelling time, expenses, fares and transport |  | item |  | 0 | 0
17F | (e) Guaranteed time |  | item |  | 0 | 0
17G | (f) Non-productive overtime and other expenses in connection with overtime |  | item |  | 0 | 0
17H | (g) Incentive and bonus payments |  | item |  | 0 | 0
17J | (h) Sick Pay Disbursements |  | item |  | 0 | 0
17K | (i) Country Money, Subsistence Payments |  | item |  | 0 | 0
17L | (j) Fas Levy |  | item |  | 0 | 0
17M | (k) Redundancy Scheme |  | item |  | 0 | 0
18A | (l) Tool Money |  | item |  | 0 | 0
18B | (m) Any other disbursements arising from employment of labour |  | item |  | 0 | 0
Pension Fund
18C | the Contractor and Sub-Contractors shall be a fully paid up members of the CIF pension/Sick Pay Scheme. Before the awarding of this contract, evidence of membership will be sought from the Contractor. |  | item |  | 0 | 0
Trade union membership, pension fund, tax, PRSI, part-time working
18D | Every possible means must be availed of on the part of the Contractor and his Foreman in charge of the Works to ascertain that the clauses in the General Conditions of Contract with reference to Trade Union and Local Labour are complied with. |  | item |  | 0 | 0
18E | The Contractor shall be a fully paid up member of the CIF Pension and Mortality Fund or an equivalent benevolent fund. |  | item |  | 0 | 0
18F | All workers employed by the Contractor and his Sub-Contractors shall be registered for and paying Pay Related Social Insurance. |  | item |  | 0 | 0
18G | The Contractor and his sub-Contractors shall, where appropriate comply in all respects with the terms of the Worker Protection (Regular Part-time Workers) Act 1991 and the Social Welfare (Employment of Inconsiderable Extent) (no. 2) Regulations, 1991 (S.I. NO 72 of 1991) updated to date of tender. |  | item |  | 0 | 0
PLANT
Scaffolding and Plant
Plant
19A | Allow for bringing to site and removing from site all plant required for the Works |  | item |  | 0 | 0
19B | Allow for maintaining on site all plant required for the Works |  | item |  | 0 | 0
Plant Return
19C | Provide each week for the Engineer a daily return of the number, type and capacity of all plant excluding hand tools and scaffolding, currently in operation on the Works |  | item |  | 0 | 0
General Scaffolding
19D | Provide as necessary all general scaffolding required for the execution of the works |  | item |  | 0 | 0
HEALTH AND SAFETY
Safety Health and Welfare at Work (Construction) regulations 2006
The Contractor is to allow for the following items in connection with Safety Health and Welfare at Work provisions:
19E | i) The operation of the requirements of the SAFE PASS and CONSTRUCTION SKILLS CERTIFICATES Schemes |  | item |  | 0 | 0
19F | ii) Safety Officers and all safety supervisors, first aiders, inspectors and certifiers required |  | item |  | 0 | 0
19G | iii) Tests and Certificates on plant and equipment |  | item |  | 0 | 0
19H | iv) Safety signs and signals |  | item |  | 0 | 0
20A | v) Provision of Personal Protective Clothing and Personal Protective Equipment |  | item |  | 0 | 0
20B | vi) Provision and maintenance of Emergency routes and exits and designated personnel responsible for emergency procedures |  | item |  | 0 | 0
20C | vii) Energy distribution installations |  | item |  | 0 | 0
20D | viii) Temporary Fire detection and fire fighting systems |  | item |  | 0 | 0
20E | ix) Maintenance of appropriate working conditions and work stations |  | item |  | 0 | 0
20F | x) Provision and maintenance of on site traffic routes |  | item |  | 0 | 0
20G | xi) Provision of first aid equipment and first aid room as appropriate |  | item |  | 0 | 0
Safety Statement
20H | The Health and Safety section of the preliminaries must be read in conjunction with the Preliminary Health & Safety Plan (by the Health & Safety Supervisor;) which is to form part of the Tender documents. |  | item |  | 0 | 0
20J | The contractor shall include for complying with the Safety Health and Welfare at Work Acts and Regulations current at the date of tender. |  | item |  | 0 | 0
20K | The Contractor shall include for complying with the Safety, Health and Welfare at Work (Construction) Regulations and Acts current at the date of tender. |  | item |  | 0 | 0
Project Supervisor for Construction Stage
21A | The Contractor shall include for a competent person to act as and carry out the duties of Project Supervisor for the duration of the Construction stage as set out in the current Safety, Health and Welfare at work (Construction) Regulations. |  | item |  | 0 | 0
21B | The Contractor and Project Supervisor (Construction Stage) are required to confirm in writing that they will be fully responsible for any temporary works design and construction and the completion of the entire safety file documentation for this project, not withstanding any provisions relating to these issues under the current Safety, Health and Welfare Regulations. |  | item |  | 0 | 0
TEMPORARY BUILDINGS
Temporary Buildings for use by the Contractor
Provide all Welfare facilities for work people in compliance with the current schedule of the Safety Health and Welfare at Work (Construction) regulations to include the following:
21C | (a) Provide and maintain temporary office accommodation for the Contractor's staff and watertight sheds for the use of workmen employed on the site and the storage of materials, tools and tackle, in positions to be agreed with the Employer's representative. Alter, shift and adapt same as necessary from time to time and remove on completion. |  | item |  | 0 | 0
22A | (b) Provide suitable common toilet block for all workers in an appropriate place on the site and to the approval of the Employer's Representative. They shall be maintained by the Contractor at all times in a clean and hygienic condition and removed on completion of the works, the site being made good and deodorised where necessary. |  | item |  | 0 | 0
22B | (c) Allow for re-locating as necessary during the course of the Contract. |  | item |  | 0 | 0
22C | (d) On completion, any temporary offices including hardcore areas and temporary fencing, shall be removed and the site made good. |  | item |  | 0 | 0
PROTECTION
Hoarding
22D | Provide and maintain all necessary temporary fencing / hoardings for the protection of the public, the site and the works against trespass and interference etc; include for shifting and adapting from time to time as necessary; remove on completion; all to the satisfaction of the Employers Representitive |  | item |  | 0 | 0
22E | Provide, maintain and clear away all temporary shoring, trench boxes, screens, fans, planked footways, guardrails, gantries, floor protection, stair protection, roof edge protection, protection of openings, safety nets and similar items |  | item |  | 0 | 0
Protection of the Works
23A | The Contractor's attention is drawn to the necessity to provide adequate protection to all new works |  | item |  | 0 | 0
23B | Prevent damage to existing buildings, fences, gates, walls, roads, services, sewer pipes, tanks etc, paved areas and other site features, which are to remain in position during execution of the Works. |  | item |  | 0 | 0
Watching and Lighting
23C | Provide watching and lighting etc necessary for the protection of the public, the site and the works against interference etc. |  | item |  | 0 | 0
Protection Against Weather
23D | Protect the works, materials and plant from the weather and make good any damage caused |  | item |  | 0 | 0
Existing Features
23E | Protect existing buildings, fences, gates, walls, power lines and other site features, which are to remain in position during the execution of the works, from damage by site operations. Make good any damage to existing features resulting from the works. |  | item |  | 0 | 0
23F | The Contractor's attention is directed to the listing presently imposed on the building and it's environs. Details are available from the Employer's representative on request. |  | item |  | 0 | 0
24A | The Contractor is to provide all necessary protection to the existing buildings while demolitions and alterations are taking place and for the duration of the contract. |  | item |  | 0 | 0
Pollution
24B | Do not deposit deleterious material into surface water channels or lakes. Comply with the requirements of the Rivers Pollution Protection Act, the Public Health (Ireland) Acts, and the Fisheries Acts |  | item |  | 0 | 0
Storage of Materials
24C | Store materials in a tidy manner. Separate different materials and protect them from dirt, physical damage, reaction with other materials markings or staining, micro organisms, mildew, fungus and vermin. Do not store materials in ways which may cause damage to the works, people or property. |  | item |  | 0 | 0
24D | The contractor is to include the cost of storage of any and all materials noted in the Works Requirement required to be transported to storage and replaced to the completed school on completion. The contractor must indemnify the Employer against any and all damage through removal and transportation |  | item |  | 0 | 0
24E | The contractor is to include for all costs associated with the transporation of retained items, noted in the Works Requirements, to storage as directed by the Employer. The contractor must indemnify the Employer against any and all damage through removal and transportation |  | item |  | 0 | 0
Security
25A | The main contractor must provide security to the site for the duration of the contract |  | item |  | 0 | 0
TEMPORARY SERVICES
Water for the Works
25B | The Contractor shall allow for all temporary plumbing work, storage facilities, connections etc necessary and shall make his own arrangements for the supply of water for the works. Clean fresh water to be provided for use and clearing away and making good on completion. Pay all charges in connection with same. |  | item |  | 0 | 0
Temporary Services
25C | The Contractor shall provide all necessary supplies of electricity, temporary lighting, power and other services necessary for the execution of the works, shall pay all charges in connection therewith and shall ensure that all temporary installations are made in a safe and proper manner and cleared away and made good on completion |  | item |  | 0 | 0
25D | Provide all necessary power, light and water for the Works and pay all charges |  | item |  | 0 | 0
Works Outside the Boundaries
26A | Where work is descrided as being executed beyond the boundary of the site or in the public highway the Contractors price shall be deemed to include for the following as required; adequate watching and lighting, traffic signalling, temporary barricades, walking platforms and warning notices sufficient to ensure the safety of all persons and removing same on completion givig notice to all Local Authority paying their fees and charges and carrying out the work to their satisfaction. The Contractors prices shall also include for maintaining in working order all services, conduits, telephone cables etc. and for making good any damage done thereto by reason of the works to the satisfaction of the Authority concerned |  | item |  | 0 | 0
CLEANING
Interim Cleaning
26B | Remove all rubbish from the works as it accumulates and maintain the works in a clean and tidy condition for the duration of the Contract |  | item |  | 0 | 0
26C | Allow for cleaning roads and carparks by brushing and hosing at regular intervals as instructed by the Employers representative. |  | item |  | 0 | 0
Cleaning of the Substantial Completed Works
27A | (a) On completion of the works and as and when directed by the Employer's representative, the Contractor shall clear away and remove from the site all construction plant, surplus materials, rubbish and temporary works of every kind and leave the whole of the site and works clean and in a neat condition to the satisfaction of the Employers representative. |  | item |  | 0 | 0
27B | (b) Provide for cleaning the buildings inside and out, removing stains and touching up paintwork and polished work, washing all floors and glass and leaving the whole of the works clean to the satisfaction of the Employer's Representative on completion. Use cleaning materials only as recommended by the relevant manufacturers and in the absence of such recommendations, the materials and methods must be approved by the Employers representative. |  | item |  | 0 | 0
27C | (c) On completion, remove all temporary markings, coverings and protective wrappings unless otherwise instructed. |  | item |  | 0 | 0
27D | (d) Touch up minor faults, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks of junctions. |  | item |  | 0 | 0
27E | (e) Adjust, ease and lubricate all doors, windows, drawers, ironmongery, appliances controls and other moving parts as necessary to ensure easy and efficient operation. |  | item |  | 0 | 0
28A | (f) Clean all access roads to the site, all temporary roadways within the site as the works necessitates |  | item |  | 0 | 0
Waste management
28B | Materials excavated from the site shall unless expressly stated otherwise be removed from site and disposed of at a tip/waste facility to be provided by the Contractor. The Contractor shall ensure that all waste is removed from site by approved waste disposal contractors, to approved and licensed facilities. |  | item |  | 0 | 0
28C | The Contractors attention is drawn to the document "Best Practice Guidelines for the Prepation of Waste Management Plans for Construction and Demolition Projects". The Contractor shall take these guidelines as mandatory and include in his tender for complying with them in full. |  | item |  | 0 | 0
(10) SITE PREPARATION
ELEMENT NOTES
31A | Contractor to include for moving plant and machinery to and from site as necessary, between site locations in line with programme requirements, including transport, fuel costs, insurances, tools and other relevant statutory or local authority fees and charges. No change order variation will be entertained in this regard |  | note |  | 0 | 0
31B | The contractor's attention is drawn to ARM4 S152.3 "Deemed to be Included - reference 1 - 4" to remark on cutting and fitting around objects, fitting and cutting into shape inserts, fair edges and angles are deemed to be included in the rates. |  | note |  | 0 | 0
31C | Whilst the contractor is obliged to protect all existing structures, the Bill of Quantities will identify certain limited items to be retained and protected during the works. General protection of the works will be covered under B10 and B12 of the Agreed Rules of Measurement. Annotation of particular items to be protected does not relieve the tendering contractor from their obligation to protect and repair/ replace, if damaged, the works |  | note |  | 0 | 0
DEMOLITIONS AND ALTERATIONS
ALTERATIONS
Repairs: Protect
32A | Protect existing retained in position items, marked in particular on drawings, for the duration of the works; erect necessary protection barriers, adapt and adjust during the works; remove and make good on completion |  | item |  | 0 | 0
EXCAVATION AND EARTHWORKS
Excavation
32B | Excavate grassed percolation area; dispose off site to a suitably licensed waste facility |  | item |  | 0 | 0
32C | Excavate topsoil and existing pipework within gravel; existing percolation area; separate in line with waste management requirements; dispose off site to a suitably licensed waste facility |  | item |  | 0 | 0
Filling
32D | Existing percolation area not covered by new attenuation layer to be filled with suitable topsoil, graded and seeded to match surrounding field |  | Item |  | 0 | 0
(30) BOUNDARY WALLS AND FENCES
SURFACE PAVING, FENCING AND LANDSCAPING
Fencing
Palisade pale fencing; to IS EN 1722-12 and IS EN 1461; galvanised mild steel, all members hot dip galvanised to IS EN 1461 : 2009; factory polyester powder coated to IS EN 13438; Colour: RAL 6005 (green); w-section pale profile, splayed trefoil spiked head – 2.0 – 3.0mm thick; 17nr pales per panel; standard panels at 2750mm long; cutting as necessary on site, zinc etch primer, top coat polyurethane repair paint; securely fixed to rolled steel angle RSJ 50 x 50 x 2.75mm thick; 127 x 76; 102 x 44 RSJ galvanised steel upright intermediate posts, 2750mm centres; post fixed, pre-drilled 8mm diameter holes; M8 x 40mm zinc plated anti-tamper bolts; composition to meet LPCB standard LPS 1175 security provision SR1; posts set in 350 x 350mm concrete foundations, 600mm deep, to IS EN 206-1, excavation of post pits and disposal off site in line with waste management requirements; panels fixed and fitted plumb and lined; all in accordance with Engineers specification
34A | Install new fencing 2100mm high to receive new access gates | 60 | m |  | 0 | 0
Gates
Palisade gates; to IS EN 1722-12 and IS EN 1461; galvanised mild steel, all members hot dip galvanised to IS EN 1461: 2009; factory polyester powder coated to IS EN 13438; Colour: RAL 6005 (green); w-section pale profile, splayed trefoil spiked head – 2.0 – 3.0mm thick; 60 x 60mm, 3mm thick standard hollow section frame, 50 x 50mm, 5mm thick standard hollow section frame; mild steel pre-treated to IS EN 13438; mitred joints, welds ground smooth to IS EN 1011; 150 x 150mm, 5mm thick standard hollow section frame; post fixed, pre-drilled 8mm diameter holes; M8 x 40mm zinc plated anti-tamper bolts; adjustable steel hinges; sliding latch, heavy duty padlock, composition to meet LPCB standard LPS 1175 security provision SR1; posts set in 600 x 600mm concrete foundations, 600mm deep, to IS EN 206-1, excavation of post pits and disposal off site in line with waste management requirements; panels fixed and fitted plumb and lined; all in accordance with Engineers specification
Access Gate
35A | overall opening size 1800mm high x 4000mm wide; double leaf gates 2000 x 1750mm high - 1nr | 1 | Item |  | 0 | 0
(50) DRAINAGE
ALTERATIONS TO EXISTING TREATMENT PLANT; REFER TO DRG NO. 01
DESLUDGING OF WASTEWATER TREATMENT SYSTEM
Handling and disposal of contaminated or hazardous material
37A | De-sludge and Remove approximately 15tns semi treated sewage on three separate occasions and dispose off site to a suitable licensed facility (submit proof by way of dockets & invoice) |  | item |  | 0 | 0
ALTERATIONS TO EXISTING TREATMENT PLANT
37B | Decommission existing septic tank system complete and existing percolation area complete including existing outlet pipe from existing manhole to existing septic tank; grub up existing pipework, fittings and the like; dispose of all surplus materials off site to a suitably licienced facility (submit proof by way of dockets & invoice), backfilling with imported hardcore material to be obtained off site; Clause 505 20mm clean, washed crushed limestone rock; IS EN 13242: 2002 and to SR21:2004_Annex_E and A1:2007 (Limiting Pyrite-certification required); Type B to IS EN13285; depositing in layers of maximum 150mm thickness; surface finish to match existing surrounding area |  | item |  | 0 | 0
38A | Collapse, excavate and backfill the existing waste water treatment system, percolation area and general area complete including all pipework, tanks, pits, holes and the like with suitable uncontaminated surplus spoil as agreed and directed by the Employers Representative or with imported hardcore material to be obtained off site; Clause 505 20mm clean, washed crushed limestone rock; IS EN 13242: 2002 and to SR21:2004_Annex_E and A1:2007 (Limiting Pyrite-certification required); Type B to IS EN13285; depositing in layers of maximum 150mm thickness; surface finish to match existing surrounding area |  | item |  | 0 | 0
Extra over trench excavation irrespective of depth
38B | Saw cutting and breaking out existing paving/tarmac surfaces; reinstating on completion including filling joints with suitable material; to be approved by the Employers Representitive |  | Item |  | 0 | 0
38C | Excavating around existing pipework or ductwork crossing trenches |  | Item |  | 0 | 0
38D | Excavating below ground water level including work outside boundary of site |  | Item |  | 0 | 0
Other Items
38E | Provide for all labour, materials, plant and all items which are not specifically allowed for in this section of the works but which can be reasonably inferred from a site inspection and the works requirements as being necessary for the execution and completion of the works. - (List items below) |  | Item |  | 0 | 0
39A | 1). |  |  |  | 0 | 0
39B | 2). |  |  |  | 0 | 0
DRAINAGE - GRAVITY PIPE (ALL PROVISIONAL)
Below Ground
Excavation starting from top of existing ground level; filling in with imported graded stone filling compacted in layers 100 - 150 maximum thickness
pipes not exceeding 250mm diameter
39C | average depth not exceeding 1000mm | 37 | m |  | 0 | 0
Extra over excavating trenches irrespective of depth
39D | breaking up rock; 500mm deep |  | item |  | 0 | 0
Disposal
39E | ground water |  | item |  | 0 | 0
39F | surface water |  | item |  | 0 | 0
Extra over trench excavation irrespective of depth
39G | Saw cutting and breaking out existing paving/tarmac surfaces; reinstating on completion including filling joints with suitable material; to be approved by the Employers Representitive |  | Item |  | 0 | 0
39H | Excavating around existing pipework or ductwork crossing trenches |  | Item |  | 0 | 0
39J | Excavating below ground water level including work outside boundary of site |  | Item |  | 0 | 0
Disposal
Water
40A | surface |  | Item |  | 0 | 0
40B | ground |  | Item |  | 0 | 0
Beds and surrounds
Graded Gravel; 14mm - 5mm (d/D 2/14) graded aggregate or 10mm (d/D 4/10) single sized aggregate to IS EN 13242; compacted in 100mm layers all in accordance with E.R.s Drawing
40C | 500 x 600mm to 100mm dia. pipe | 37 | m |  | 0 | 0
uP.V.C. pipes and fittings, as E.R.s specifications; ring seal joints
Pipework in trenches
40D | 100 nominal size | 37 | m |  | 0 | 0
40E | ^^Extra; short lengths |  | item |  | 0 | 0
Connections
40F | connecting pipework to pump tank | 1 | Nr |  | 0 | 0
40G | connecting pipework to existing manhole | 1 | Nr |  | 0 | 0
Testing
Allow for testing drains and manholes, to I.S. E.N.1610; as work proceeds and on completion with smoke and water
40H | generally |  | item |  | 0 | 0
DRAINAGE - RISING MAINS
Below Ground
Excavation starting from top of existing ground level; filling in with imported graded stone filling compacted in layers 100 - 150 maximum thickness
pipes not exceeding 250mm diameter
41A | average depth not exceeding 1500mm | 116 | m |  | 0 | 0
Extra over excavating trenches irrespective of depth
41B | breaking up rock; 500mm deep |  | Item |  | 0 | 0
41C | Saw cutting and breaking out existing paving/tarmac surfaces; reinstating on completion including filling joints with suitable material; to be approved by the Employers Representitive |  | Item |  | 0 | 0
41D | Excavating around existing pipework or ductwork crossing trenches |  | Item |  | 0 | 0
41E | Excavating below ground water level including work outside boundary of site |  | Item |  | 0 | 0
Disposal
41F | ground water |  | item |  | 0 | 0
41G | surface water |  | item |  | 0 | 0
Beds and surrounds
Graded Gravel; 14mm - 5mm (d/D 2/14) graded aggregate or 10mm (d/D 4/10) single sized aggregate to IS EN 13242; compacted in 100mm layers all in accordance with Engineers Drawing
41H | 400 x 400mm to 32mm dia. pipe | 116 | m |  | 0 | 0
Graded gravel; pea gravel; clause 503; I.S. EN 13242:2002 + A1 2007; nominal aggregate size 6 - 10mm
Covering layer
42A | 400mm wide to 32mm dia. pipe | 116 | m |  | 0 | 0
Pipes: HDPE
Pipework; high density polyethylene (HDPE), material strength PE100; blue colour; below ground pressurised pipework – standard dimension ratio SDR 17 – 10 bar; 6.6mm wall thickness, minimum required strength 10.0MPa; ; to IS EN 12201; plain end, - 2nr; smooth wall internal and external pipework; to meet Irish Water requirements; electro diffusion fittings 16bar couplers, to IS EN 12201:2003; laid in trenches on bed (e/m); bedded and surrounded in clean stone or pea gravel (e/m); laid to falls as work proceeds
42B | 33mm diameter pipe | 116 | m |  | 0 | 0
Connections
42C | connecting pipework to pump tank | 1 | Nr |  | 0 | 0
42D | connecting pipework to 4 TER3 system | 1 | Nr |  | 0 | 0
Testing
Allow for testing drains and manholes, to I.S. E.N.1610; as work proceeds and on completion with smoke and water
42E | generally |  | item |  | 0 | 0
DRAINAGE - PE18 PROPRIETARY WASTEWATER TREATMENT SYSTEM
EXCAVATION AND EARTHWORKS
Excavation
Reduce Levels
43A | Average thickness not exceeding 2.0m | 90 | m3 |  | 0 | 0
Filling with hardcore material to be obtained off site; Clause 505 20mm clean, washed crushed limestone rock; IS EN 13242: 2002 and to SR21:2004_Annex_E and A1:2007 (Limiting Pyrite-certification required); Type B to IS EN13285; depositing in layers of maximum 150mm thickness
To make up levels; Attenuation Layer
43B | Average thickness not exceeding 350mm | 9 | m3 |  | 0 | 0
Filling with loam material to be obtained off site, to BS 3882 (Table 1); composite mix: sand (35-60%), silt (30-50%), clay (10-25%) organic topsoil (0-4%); depositing in layers of maximum 150mm thickness maximum
To make up levels
43C | Average thickness not exceeding 250mm | 79 | m3 |  | 0 | 0
WASTIC ASPHALT, WATERPROOF AND GAS PROOF NON-METAL FLEXIBLE SHEET COOVERINGS
Geotextile separator membrane; Terram T1000 geosynthetic grid, UV stabilised, high tenacity, virgin polypropylene fibres, mechanically and thermally bonded; to IS EN 13249: 2016; tensile strength MD 8.0kN/m and tensile elongation 60%, to IS EN 10319; CBR resistance 1500N to IS EN 12236; all necessary laps, end laps and joints; to manufacturer’s instructions; laid on and including levelling existing in preparation for membrane; to E.R.s specification and contracting authority's approval
Geotextile membranes
44A | horizontal; pipe wrapping, 100mm diameter pipework; girth not exceeding 300mm | 91 | m |  | 0 | 0
44B | vertical; 1nr layer; width over 300mm wide | 85 | m2 |  | 0 | 0
DRAINAGE - PE18 PROPRIETARY TREATMENT PLANT UNITS
Below Ground
PE18 Eurotank BAF2 Units by specialist
SewageSystems (FIEA Ltd) (Concrete Units)
45A | Supply assembly complete; take delivery and install, hoisting, off loading and craning into final position; stilling chamber and the following concrete tank/chambers; primary, reactor and clarifier/pump chambers, 2500mm diameter x 1950mm deep tanks; laid on 300mm of compacted clause 808 broken stone; opening lid; flange adaptors bends and tees fittings to design; backfilling to excavations with clean washed 20mm maximum pea gravel, disposal of ground and surface water for duration; finishing flush with surfaces; include for connection of rising mains; include for connection of power supply | 1 | item |  | 0 | 0
Electrical Kiosk and Foundations
Galvanised Steel, lockable Electrical Kiosk by specialist Contractor
45B | 1250 x 650 x 1180mm high, bolted to concrete plinth, to be approved by E.R. | 1 | Nr |  | 0 | 0
Excavation and disposal; in-situ concrete grade C35N to IS EN 206; reinforcement; formwork complete
45C | Electrical Kiosk; 2000 x 2000mm x 200mm deep plinth; all as per drawing 03 | 2 | Nr |  | 0 | 0
Sundries
46A | Supply and install Siemens digital Flow meter & complete including all pipework, fittings, earthworks, backfilling and the like | 1 | item |  | 0 | 0
Connections
46B | Supply and install internal rising main plumbing complete including all pipework, fittings, earthworks, backfilling and the like | 1 | item |  | 0 | 0
Testing
Allow for testing drains and manholes, to I.S. E.N.1610; as work proceeds and on completion with smoke and water
46C | generally | 1 | item |  | 0 | 0
DRAINAGE - 4 TER3 PACKAGED TERTIARY TREATMENT SYSTEM
EXCAVATION AND EARTHWORKS
Excavation
Reduce Levels
46D | Average thickness not exceeding 2.0m | 42 | m3 |  | 0 | 0
Filling with hardcore material to be obtained off site; Clause 505 20mm clean, washed crushed limestone rock; IS EN 13242: 2002 and to SR21:2004_Annex_E and A1:2007 (Limiting Pyrite-certification required); Type B to IS EN13285; depositing in layers of maximum 150mm thickness
To make up levels; Attenuation Layer
46E | Average thickness not exceeding 350mm | 63 | m3 |  | 0 | 0
Filling with loam material to be obtained off site, to BS 3882 (Table 1); composite mix: sand (35-60%), silt (30-50%), clay (10-25%) organic topsoil (0-4%); depositing in layers of maximum 150mm thickness maximum
To make up levels
47A | Average thickness not exceeding 300mm | 126 | m3 |  | 0 | 0
WASTIC ASPHALT, WATERPROOF AND GAS PROOF NON-METAL FLEXIBLE SHEET COOVERINGS
Geotextile separator membrane; Terram T1000 geosynthetic grid, UV stabilised, high tenacity, virgin polypropylene fibres, mechanically and thermally bonded; to IS EN 13249: 2016; tensile strength MD 8.0kN/m and tensile elongation 60%, to IS EN 10319; CBR resistance 1500N to IS EN 12236; all necessary laps, end laps and joints; to manufacturer’s instructions; laid on and including levelling existing in preparation for membrane; to Engineers specification and contracting authority's approval
Geotextile membranes
47B | horizontal; pipe wrapping, 100mm diameter pipework; girth not exceeding 300mm | 107 | m |  | 0 | 0
47C | horizontal; 1nr layer; width over 300mm wide | 180 | m2 |  | 0 | 0
DRAINAGE - PERCOLATION PIPEWORK
Pipes: uPVC
Pipework; Unplasticised polyvinyl chloride (uPVC), red/brown colour; below ground non pressurised pipework; to IS EN 1401-1:2018 and IS EN 13476-2:2007; Spigot and socket ring seal push fit end, to IS EN 681-1-1 nr, plain end, chamfered - 1nr; smooth wall internal and external pipework; to meet Irish Water requirements; lateral deflection nominal stiffness SN4 (4000N/m/m); laid in trenches on bed (e/m); bedded and surrounded in clean stone or pea gravel (e/m); laid to falls as work proceeds
48A | 100mm perforated pipe; 0.6mm - 4.0mm slots | 107 | m |  | 0 | 0
48B | 100mm perforated pipe; 0.6mm - 4.0mm slots; vertical with vent cap[Number of: 4] | 4 | m |  | 0 | 0
Extra over pipes on which they occur for
Vent covers
48C | 100mm diameter pipe | 4 | Nr |  | 0 | 0
branches
48D | 100mm diameter pipe | 8 | Nr |  | 0 | 0
bends - 90 degree
48E | 100mm diameter pipe | 8 | Nr |  | 0 | 0
DRAINAGE - TER 3 UNITS
Below Ground
TER 3 Units
SewageSystems (FIEA Ltd) TER III (Concrete Units)
49A | Supply assembly complete; take delivery and install, hoisting, off loading and craning into final position; concrete modular chamber, 2500mm x 1200mm cuboid tanks, 1000mm deep; laid on Attenuation Layer (measured elsewhere) opening uPVC lid; flange adaptors bends and tees fittings to design; backfilling to excavations with clean washed 20mm maximum pea gravel, disposal of ground and surface water for duration; finishing flush with surfaces; include for connection of rising mains; include for connection of power supply | 4 | Nr |  | 0 | 0
Connections
49B | Supply and install internal rising main plumbing complete including all pipework, fittings, earthworks, backfilling and the like |  | item |  | 0 | 0
Testing
Allow for testing drains and manholes, to I.S. E.N.1610; as work proceeds and on completion with smoke and water
49C | generally |  | item |  | 0 | 0
(60) SITE SERVICES (ELECTRICAL)
ELECTRICAL INSTALLATIONS
51A | Note: existing power supply to be altered to provide power supply to new treatment plant system |  | note |  | 0 | 0
Excavated trenches
pipes not exceeding 250mm diameter
51B | average depth not exceeding 1000mm | 50 | m |  | 0 | 0
Extra over excavating trenches irrespective of depth
51C | breaking up rock; 500mm deep |  | item |  | 0 | 0
51D | excavating existing paved areas, replacement of paving with suitable materials to match existing; to be approved by the Employers Representitive |  | item |  | 0 | 0
51E | next to existing roadways/paths/sports facilities and the like; contractor to include for all necessary security, watching, lighting, hoarding, insurances and licences to cover works outside the boundary in the public domain, adjacent neighbouring properties or within the site demise during traffic control interventions; include for laying and backing filling trenches for the duration of the pipelaying works |  | item |  | 0 | 0
Disposal
51F | ground water |  | item |  | 0 | 0
51G | surface water |  | item |  | 0 | 0
Beds and surrounds
10mm (d/D 4/10) single sized aggregate to IS EN 13242; compacted in 100mm layers all in accordance with Engineers Drawing
52A | 450 x 375mm to 100mm dia. pipe | 50 | m |  | 0 | 0
Cover layer
Graded gravel; pea gravel; clause 503; I.S. EN 13242:2002 + A1 2007; nominal aggregate size 6 - 10mm
52B | 450 x 600mm to 100mm dia. pipe | 50 | m |  | 0 | 0
Pipes
Ductwork; unplasticised polyvinyl chloride (uPVC), red / black colour; below ground non pressurised pipework; to IS EN 1401-1:2018 and IS EN 13476-2:2007; Spigot and socket ring seal push fit end, to IS EN 681-1-1 nr, plain end, chamfered - 1nr; smooth wall internal and external pipework; to meet ESB requirements; laid in trenches on bed (e/m); bedded and surrounded in clean stone or pea gravel (e/m); laid to falls as work proceeds
52C | 125mm dia. pipe | 50 | m |  | 0 | 0
Pipe accessories
Micro Pillars and Foundations
Excavation and disposal; in-situ concrete grade C35N to IS EN 206; reinforcement; formwork complete
52D | ESB Micropillar & draw chamber; 766 x 766mm x 900mm deep vault; 200 diameter sump; 150mm thick sand / concrete surround and base; including cast iron lid; all as per engineers detail or ESG for Housing Schemes - rev 2; 2004 | 1 | Nr |  | 0 | 0
Electrical Kiosk and Foundations
Galvanised Steel, lockable Electrical Kiosk
53A | 1400 x 1400 x 600mm deep, bolted to concrete plinth, to be approved by Engineer | 1 | Nr |  | 0 | 0
Excavation and disposal; in-situ concrete grade C35N to IS EN 206; reinforcement; formwork complete
53B | Electrical Kiosk; 2500 x 2500mm x 200mm deep plinth; all as per engineers drawing 03 | 1 | Nr |  | 0 | 0
Mains Supply
53C | Connect mains power supply to new Electrical Kiosk and new Treatment Plant |  | item |  | 0 | 0
Sundries
Coloured polyethylene warning mesh; 440mm wide; laid at a depth not exceeding 350mm below finished ground level; clause 804 backfill above
continous strip, laid during trench backfill
53D | 100mm above 100mm dia. pipe | 50 | m |  | 0 | 0
Nylon draw-in wire
53E | laid in ducts, 100mm dia. pipe (EIR) | 50 | m |  | 0 | 0
(80) LANDSCAPING
SURFACE PAVINGS, FENCING AND LANDSCAPING
GRASSING & PLANTING
Topsoil
taken from off site; select topsoil only; imported preserved topsoil
55A | average thickness not exceeding 300mm | 80 | m3 |  | 0 | 0
Grading irregular levels; in preparation for cultivating
55B | over 300mm wide | 264 | m2 |  | 0 | 0
Cultivating
Final cultivation; after grading and fertilising; reduce to fine, firm tilth with good crumb structure, particles 2-8mm; depth of 25mm; include for removal of stones / earth sods exceeding 15mm (fine lawn areas); extend cultivation in marrying with existing areas
55C | to grassed area location | 264 | m2 |  | 0 | 0
Surface applications
Fertilizer; spread at the rate of 0.05 kg to the square meter and harrowed in; all as Engineers Specification
55D | to grassed area location | 264 | m2 |  | 0 | 0
Seeding
Seed with Barenbrug E3 - universal turf; seeding spread at the rate of 35g/m3; mixture 40% (Perennial Ryegrass), 40% (Strong Creeping Red Fescue), 20% (Chewings Fescue), low maintenance; in two number applications, applied at right angles to each other; slightly raking and consolidating surface after seeding with a light roller; all as Engineers Specification
56A | to grassed area location | 264 | m2 |  | 0 | 0
| Subtotal |  |  |  |  | 0
| VAT |  |  |  |  | 0
| Total |  |  |  |  | 0

## Trade Summary
Description | Job % | Cost per Unit | Total
(00) PRELIMINARY PARTICULARS |  |  | 0
(10) SITE PREPARATION |  |  | 0
(30) BOUNDARY WALLS AND FENCES |  |  | 0
(50) DRAINAGE |  |  | 0
(60) SITE SERVICES (ELECTRICAL) |  |  | 0
(80) LANDSCAPING |  |  | 0
Subtotal |  |  | 0
VAT |  |  | 0
Total |  |  | 0