## Pricing Schedule
LEAD CONSULTANT NAME: |  | XXXXX
BID HOURS REQUIRED TO ENSURE PROJECT DELIVERY
Principal Service being provided |  | Architecture |  |  | Stage (ii) Design
|  |  |  | Stage (i) | Stage (ii)a | Stage (ii)b | Stage (ii)c | Stage (iii) | Stage (iv) | Stage (v)
| Resource | Individual / Company name | RATE | Preliminary Design | Scheme Design Development | Developed Design & Statutory Approvals | Detailed Design | Tender | Construction | Handover | Sum (Hrs)
ARCHETICTURAL | Senior Project Architect (Project Lead) | xxx | 0 | STAGES COMPLETE | [6 empty] | 0
| Assigned Certifier | xxx | 0 | [7 empty] | 0
| Employer's Representative | xxx | 0 | [7 empty] | 0
| Architectural Assistant / Technician | xxx | 0 | [7 empty] | 0
| Other resources as required | xxx | 0 | [7 empty] | 0
| Other resources as required | xxx | 0 | [7 empty] | 0
SUB-CONSULTANTS | Civil & Structural Engineer | xxx | 0 | [7 empty] | 0
| Building Services Engineer | xxx | 0 | [7 empty] | 0
| Quantity Surveyor | xxx | 0 | [7 empty] | 0
| PSDP Services | xxx | 0 | [7 empty] | 0
| Other resources as required | xxx | 0 | [7 empty] | 0
| Other resources as required | xxx | 0 | [7 empty] | 0
| Other resources as required | xxx | 0 | [7 empty] | 0
| Other resources as required | xxx | 0 | [7 empty] | 0
[5 empty] | ∑ | 0 | 0 | 0 | 0 | 0
TVRS Funding Apportionment
|  | OVERALL COMMISSION |  |  |  |  | TVRS Portion (Community Facility) |  | Non-TVRS Portion (Apartment Shell)
| STAGE | SUB-TOTAL |  | NOTES |  |  | % | SUB-TOTAL | % | SUB-TOTAL
| Stage (i) Preliminary | Stage (i) and (ii)a complete |  | To form of tender |  |  | Stage (i) and (ii)a complete
| Stage (ii)a Scheme Development |  |  | To form of tender
| Stage (ii)b Developed Design | 0 |  | To form of tender |  |  | 75% | 0 | 25% | 0
| Stage (ii)c Detailed Design / specifications / tender pack | 0 |  | To form of tender |  |  | 75% | 0 | 25% | 0
| Stage (iii) Tender | 0 |  | To form of tender |  |  | 75% | 0 | 25% | 0
| Stage (iv) Construction | 0 |  | To form of tender |  |  | 75% | 0 | 25% | 0
| Stage (v) Handover | 0 |  | To form of tender |  |  | 75% | 0 | 25% | 0
| TOAL TENDER AMOUNT | 0 |  |  |  |  | TOTAL | 0 | TOTAL | 0
IMPORTANT NOTE:
The Lead Tenderer, with input from their Specialist Skills Providers, shall review the default apportionment percentages in the "TVRS Funding Apportionment" table and amend percentages (pale yellow boxes) as necessary to reasonably reflect the scope of services. Refer to section 1.4.1 of "Vol B Annex 2 - Brief of Services" for guidance.
GENERAL NOTES:
1 | All rates provided are to be exclusive of VAT.
2 | Rates used deemed to be inclusive of all resource employment overheads, office overheads, travel, subsistence, consumables etc.
3 | Whole numbers only shall be used for hours and rates, no 0 (Zero) rates, 'n\a' or 'incl' annotation to be entered.
4 | Tenderers are responsible for all necessary arithmetical checks on this document. Please advise of any errors or corrections required.
5 | There is no recourse to the Contracting Authority should the actual hours required to deliver the Project Scope are higher than the hours set out in this document.
6 | Failure of Tenderers to comply with these tendering requirements may result in their exclusion from further involvement in this tender competition.