## 00 Cover Page
Document Control Sheet
Dublin District Heating Project - Site Investigation Works Schedules
Client | Dublin City Council
Project Title | Dublin District Heating Project
Document Title | Dublin District Heating Project - Site Investigation Works Schedules
Document No. | MDR1597-RPS-01-SI-DH-L-G-0001
Document status
Version | Purpose of document | Authored by | Reviewed by | Approved by | Review date
S3 P01 | Draft for review | IB | DC | DC | 2025-08-08
S3 P02 | Draft for review | IB | DC | DC | 2025-09-22
S3 P03 | Draft for review | COC | CB | CB | 2026-02-26

## Glossary
List of Abbreviations
BH | Borehole
BSI | British Standard Institution
CP | Cuting Process
CPT | Cone Penetration Test
DDHP | Dublin District Heating Project
DL | Deep Load
DPC | Dublin Port Company
DWtE | Dublin Waste to Energy
GS | Geophysical Surveys
GBS | Grab Samples
ITM | Irish Transverse Mercator
IGB | Irish Glass Bottle
MDR | Reference Project
PAS | Publicly Available Specification
SP | Soil Pipe
SPT | Standard Penetration Test
SIW | Site Investigation Works
ST | Slit Trench
TP | Trial Pit
TS | Topography Survey
PG | Perforating Gun
RC | Rotary Core
UE | Uisce Éireann
US | Utility Survey
Glossary of Terms
Borehole | A borehole is a narrow shaft bored in the ground, either vertically or horizontally.
Cone Penetration Test (CPT) | The cone penetration or cone penetrometer test (CPT) is a method used to determine the geotechnical engineering properties of soils and delineating soil stratigraphy.
Geophysical Surveys | Geophysical surveys are ground-based physical sensing techniques that produce a detail image or map of an area. Ground-based surveys may include: Seismic surveys - vibrations are recorded with geophones to provide information about the properties of rocks.
Grab Samples | A grab sample is a sample of sediment taken from the seabed.
Irish Transverse Mercator (ITM) | Irish Transverse Mercator (ITM) is the geographic coordinate system for Ireland. It was implemented jointly by the Ordnance Survey Ireland (OSi) and the Ordnance Survey of Northern Ireland (OSNI) in 2001. The name is derived from the Transverse Mercator projection it uses and the fact that it is optimised for the island of Ireland. ITM95 (EPSG:2157) is used to map the project area for the Licence Map.
Publicly Available Specification (PAS 128) | British standard developed by the British Standards Institution (BSI) in collaboration with industry experts. It provides a structured approach to underground utility detection, verification, and location, aiming to improve the accuracy and reliability of utility surveys.
PAS 128 - Type A | Verification - which is the most detailed and accurate survey type, involves physically exposing and verifying the location and depth of utilities.
PAS 128 - Type B | Detection - Utilities are detected by geophysical methods, such as Ground Penetrative Radar (GPR) to get an exact horizontal position and vertical position i.e depth. Category B Surveys are carried out to one of four levels of accuracy with each requiring a different survey type.
PAS 128 - Type C | Site Reconnaissance - Underground utility are plotted based only on utility record data, but with on-site investigation to match physical indicators above ground with the records as a best fit.
PAS 128 - Type D | Desktop Utility Record Search - Underground utilities are plotted based only on record data, otherwise known as desktop survey.
Soil Pipe | Vertical pipe that connects a building’s drainage system to the outside environment. Its primary purpose is to remove wastewater and sewage from the building, while also providing ventilation to the drainage system. Soil pipes are designed to carry soiled water (blackwater) from toilets and similar fixtures. They are typically made of materials like clay, concrete, or PVC, which can withstand the corrosiv
Standard Penetration Test | in-situ dynamic penetration test used to assess the geotechnical properties of soil, primarily for foundation design and subsurface exploration.
Site Investigation Works | Part of the planning stage of any urban development project. It involves a geotechnical engineer looking at the soil composition of the area and the strength of the soil and rock there, as well as some other characteristics that could affect construction or building safety.
Slit Trench | Slit Trenches are generally long narrow trenches. They are commonly excavated in urban environments and on roadways to determine the position of existing underground services and the soil profile prior to carrying out planned developments.
Trial Pit | Trial pits are excavated holes used in site investigations to assess ground conditions, soil profiles, and groundwater conditions before construction.
Topography Survey | Detailed mapping process that captures both natural and man-made features of a specific area. This includes elevations, contours, vegetation, bodies of water, roads, and buildings. These surveys create detailed three-dimensional maps that illustrate the location, size, height, and elevation changes of these features, playing a crucial role in urban planning, civil engineering, and construction
Rotary Core | Based on the friction caused by an abrasive tool called core bit, installed at the lower end of a sampler tube or corebarrel, which abrades away the surface to be drilled by rotation friction.

## Boreholes
Cable Percussion Boreholes & Rotary Drilling / Geobor-S Polymer Gel Wireline Coring Drillholes
Reference Number | Reference Drawing | Location | Type | Scheduled Depth (m) |  |  |  |  | Remarks | Coordinates (ITM Grid) |  | Access | Purpose
Scheduled Depth (m bGL)
[5 empty] | CP | RO | PG | RC |  | Easting | Northing
MDR1597 BH/RC01 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DWtE Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719897.754 | 733509.302 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site. A pipe bridge with foundations is planned in this location.
MDR1597 BH/RC02 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DWtE Area | CP & RC | 10 | 8 | - | - | 0 to10 | Rotary core follow on required SPT, SP, DL | 719851.343 | 733428.237 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site. A trenchless crossing is planned in this location.
MDR1597 BH/RC03 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 10 | 8 | - | - | 0 to10 | Rotary core follow on required SPT, SP, DL | 719846.426 | 733406.906 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site. A trenchless crossing is planned in this location.
MDR1597 BH/RC04 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 50 | 20 | - | - | 35 to 50 (15m into rock) | Rotary core follow on required SPT, SP, DL | 719807.423 | 733387.763 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A heavy thermal tank is planned for this location. Need to determine rock level and rock properties.
MDR1597 BH/RC05 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 50 | 20 | - | - | 35 to 50 (15m into rock) | Rotary core follow on required SPT, SP, DL | 719811.739 | 733381.306 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A heavy thermal tank is planned for this location. Need to determine rock level and rock properties.
MDR1597 BH/RC06 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 25 | 8 | - | - | 0 to 25 | Rotary core follow on required SPT, SP, DL | 719780.382 | 733363.803 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 25m piezometer need to be on place. In this location. PVC75mm
MDR1597 BH/RC07 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719790.657 | 733339.419 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A heavy thermal tank is planned for this location. Need to determine rock level and rock properties.
MDR1597 BH/RC08 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719790.475 | 733314.131 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, rock level, groundwater, and potential contaminated areas on the site. An industrial building is planned for this location.
MDR1597 BH/RC09 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/UE Area | CP & RC | 25 | 8 | - | - | 0 to 25 | Rotary core follow on required SPT, SP, DL | 719794.393 | 733291.499 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 25m piezometer need to be on place. In this location. PVC75mm
MDR1597 BH/RC10 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC South Bank Road | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719755.423 | 733427.901 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC11 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC South Bank Road | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719659.331 | 733451.141 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC12 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC South Bank Road | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719559.784 | 733474.937 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC13 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/ECOCEM Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719388.913 | 733404.72 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC14 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg - DPC/Bisset Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719267.836 | 733417.51 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC15 | MDR1597-RPS-01-M2-XX-D-C-0201 | Poolbeg IGB Site Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 719227.495 | 733442.258 | Via South Bank Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC16 | MDR1597-RPS-01-M2-XX-D-C-0202 | Sean Moore Road | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 718896.493 | 733709.32 | Sean Moore Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC17 | MDR1597-RPS-01-M2-XX-D-C-0202 | Sean Moore Road | CP & RC | 15 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 718828.296 | 733673.405 | Sean Moore Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC18 | MDR1597-RPS-01-M2-XX-D-C-0202 | IrishTown Parking Area | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 718489.127 | 733699.629 | Irishtown Stadium | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A trenchless crossing is planned
MDR1597 BH/RC19 | MDR1597-RPS-01-M2-XX-D-C-0202 | Ringsend Park | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 718481.44 | 733851.051 | Ringsend Park | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A trenchless crossing is planned.
MDR1597 BH/RC20 | MDR1597-RPS-01-M2-XX-D-C-0202 | Ringsend Park | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 718340.153 | 733919.151 | Ringsend Park | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A trenchless crossing is planned.
MDR1597 BH/RC21 | MDR1597-RPS-01-M2-XX-D-C-0202 | Ringsend Park | CP & RC | 10 | 8 | - | - | 0 to 10 | Rotary core follow on required SPT, SP, DL | 718334.23 | 733945.218 | Ringsend Park | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A trenchless crossing is planned.
MDR1597 BH/RC23 | MDR1597-RPS-01-M2-XX-D-C-0203 | Ringsend Rowing Club | CP & RC | 35 | 8 | - | - | 20 to 35 (10 into rock) | Cable percussion with rotary coring follow on. Ground water monitoring standpipe SPT, HPD, PT, SP, VHP, DL | 717971.125 | 734201.313 | Via Thorncastle St | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A launch shaft, 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC28 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Wall Quay | CP & RC | 20 | - | - | - | 20 | Cable percussion with rotary coring follow on. PVC lined full depth min internal diameter 75mm - SPT, PVC75 | 717829.116 | 734232.102 | Via Sir John Rogerson Quay Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site. Strengthen the geotechnical knowledge of the strata near the west quay wall using the parallel seismic method.
MDR1597 BH/RC29 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Wall Quay | CP & RC | 20 | - | - | - | 20 | Cable percussion with rotary coring follow on. PVC lined full depth min internal diameter 75mm - SPT, PVC75 | 717829.8 | 734236.1 | Via Sir John Rogerson Quay Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site. Strengthen the geotechnical knowledge of the strata near the west quay wall using the parallel seismic method.
MDR1597 BH/RC30 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Wall Quay | CP & RC | 20 | - | - | - | 20 | Cable percussion with rotary coring follow on. PVC lined full depth min internal diameter 75mm - SPT, PVC75 | 717830.169 | 734239.748 | Via Sir John Rogerson Quay Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site. Strengthen the geotechnical knowledge of the strata near the west quay wall using the parallel seismic method.
MDR1597 BH/RC31 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Campshires | CP & RC | 35 | - | - | - | 20 to 35 (10 into rock) | Cable percussion with rotary coring follow on. Ground water monitoring standpipe SPT, HPD, PT, SP, VHP, DL | 717825.156 | 734231.6 | Via Sir John Rogerson Quay Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A reception shaft, 600/900mm pipes network / valves chambers are planned.
MDR1597 BH/RC32 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Campshires | CP & RC | 35 | - | - | - | 20 to 35 (10 into rock) | Cable percussion with rotary coring follow on. Ground water monitoring standpipe SPT, HPD, PT, SP, VHP, DL | 717822.379 | 734234.94 | Via Sir John Rogerson Quay Road | Conduct controlled drilling to identify the type and properties of strata, groundwater, and potential contaminated areas on the site.A reception shaft, 600/900mm pipes network / valves chambers are planned.
.

## Slit Trench-Trial Pit
SITE INVESTIGATION (SLIT TRENCH & TRIAL PIT)
Reference Number | Reference Drawing | Location | Type | Scheduled Length (m) | Scheduled Depth (m) | ITM Reference |  |  |  | Remarks | Purpose | Surface Material
[6 empty] | Proposed Start Point |  | Proposed End Point
[6 empty] | Easting (m) | Northing (m) | Easting (m) | Northing (m)
MDR1597 ST01 | MDR1597-RPS-01-M2-XX-D-C-0201 | Private Area DWtE | Slit Trench | 6 | 3 | 719893.257 | 733451.581 | 719887.405 | 733452.903 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Storm Water, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Soil/Grass/Unmade Ground
MDR1597 ST02 | MDR1597-RPS-01-M2-XX-D-C-0201 | Private Area DWtE | Slit Trench | 4 | 1.5 | 719844.381 | 733414.212 | 719845.224 | 733418.122 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of HP Gas, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Gravel/Hardstanding
MDR1597 ST03 | MDR1597-RPS-01-M2-XX-D-C-0201 | Public Road | Slit Trench | 8 | 1.5 | 719485.156 | 733490.736 | 719486.445 | 733498.631 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of HP Gas, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST04 | MDR1597-RPS-01-M2-XX-D-C-0201 | Public Road | Slit Trench | 6 | 3 | 719267.036 | 733435.71 | 719262.401 | 733439.519 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Storm Water and 110kV UG, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST05 | MDR1597-RPS-01-M2-XX-D-C-0202 | Sean Moore Road | Slit Trench | 8 | 3 | 718834.286 | 733671.187 | 718828.598 | 733676.813 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, HP Gas, Storm Water and Water Mains, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST06 | MDR1597-RPS-01-M2-XX-D-C-0202 | Bremen Road | Slit Trench | 8 | 3 | 718766.55 | 733602.542 | 718760.581 | 733607.868 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, Storm Water and Water Mains, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST07 | MDR1597-RPS-01-M2-XX-D-C-0202 | Irishtown Leasure Parking | Slit Trench | 4 | 1.5 | 718514.157 | 733678.851 | 718516.332 | 733682.208 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Soil/Grass/Unmade Ground
MDR1597 ST08 | MDR1597-RPS-01-M2-XX-D-C-0202 | Ringsend Park | Slit Trench | 21 | 3 | 718583.709 | 733800.074 | 718568.52 | 733814.575 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Storm Water, 110kV UG, Foul Water, Water Mains and 38kV UG, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. Confirm the location of the toe of the historic quay wall. | Gravel/Hardstanding Soil/Grass/Unmade Ground
MDR1597 ST09 | MDR1597-RPS-01-M2-XX-D-C-0202 | Ringsend Park | Slit Trench | 14 | 3 | 718331.375 | 733919.036 | 718330.244 | 733932.99 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Storm Water, Foul Water, 38kV UG and 110kV UG, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Gravel/Hardstanding Soil/Grass/Unmade Ground
MDR1597 ST10 | MDR1597-RPS-01-M2-XX-D-C-0202 | Cambridge Road | Slit Trench | 10 | 3 | 718249.563 | 734038.826 | 718245.905 | 734048.133 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, Foul Water, Storm Water and Water Mains, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST11 | MDR1597-RPS-01-M2-XX-D-C-0202 | York Road | Slit Trench | 15 | 3 | 718351.956 | 734093.337 | 718355.949 | 734107.796 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of HP Gas, Foul Water, 38kV UG, 110kV UG, Storm Water and LP Gas, and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST13 | MDR1597-RPS-01-M2-XX-D-C-0202 | York Road | Slit Trench | 7 | 1.5 | 718130.322 | 734151.548 | 718131.828 | 734158.384 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST14 | MDR1597-RPS-01-M2-XX-D-C-0203 | Ringsend Rowing Club | Slit Trench | 10 | 1.5 | 718029.651 | 734188.408 | 718031.794 | 734198.175 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of HP Gas, and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST15 | MDR1597-RPS-01-M2-XX-D-C-0203 | Ringsend Rowing Club | Slit Trench | 6 | 3 | 717987.406 | 734192.203 | 717989.817 | 734197.697 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Foul Water and Water Mains, and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST16 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Wall Quay | Slit Trench | 3 | 1.5 | 717940.174 | 734199.721 | 717940.968 | 734202.614 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position, depth, width and material of the quay wall plus any commentary as well as any existing underground services within range of slit trench and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST17 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Garden Quay | Slit Trench | 5 | 1.5 | 717827.71 | 734225.235 | 717828.56 | 734230.162 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position, depth, width and material of the quay wall plus any commentary as well as any existing underground services within range of slit trench and the soil profile. Including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST18 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Garden Quay | Slit Trench | 5 | 1.5 | 717811.894 | 734240.715 | 717812.428 | 734245.687 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diamter and material of Water Mains, and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt Soil/Grass/Unmade Ground
MDR1597 ST19 | MDR1597-RPS-01-M2-XX-D-C-0203 | John Rogerson Quay Road | Slit Trench | 10 | 1.5 | 717782.049 | 734258.946 | 717783.465 | 734268.845 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diamter and material of Water Mains, LP Gas and MP Gas and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST20 | MDR1597-RPS-01-M2-XX-D-C-0204 | Castleforbes Road | Slit Trench | 13 | 3 | 717705.88 | 734590.158 | 717716.849 | 734589.333 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Storm Water, HP Gas, LP Gas and Foul Water , and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST21 | MDR1597-RPS-01-M2-XX-D-C-0204 | Castleforbes Road | Slit Trench | 17 | 3 | 717715.19 | 734722.934 | 717732.142 | 734721.659 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Storm Water, Water Mains, Eir Comms, HP Gas, LP Gas and Foul Water , and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST22 | MDR1597-RPS-01-M2-XX-D-C-0204 | New Wapping Street | Slit Trench | 16 | 3 | 717481.04 | 734540.525 | 717496.995 | 734539.325 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, Water Mains, Storm Water and Foul Water , and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST23 | MDR1597-RPS-01-M2-XX-D-C-0204 | New Wapping Street | Slit Trench | 17 | 3 | 717492.325 | 734685.338 | 717509.277 | 734684.063 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, HP Gas, Water Mains, Storm Water, Eir Comms, Virgin Media Comms and Foul Water , and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST24 | MDR1597-RPS-01-M2-XX-D-C-0204 | North Wall Quay | Slit Trench | 10 | 3 | 717433.391 | 734448.476 | 717433.919 | 734458.463 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, Storm Water and Water Mains and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST25 | MDR1597-RPS-01-M2-XX-D-C-0204 | North Wall Quay | Slit Trench | 12 | 3 | 717357.051 | 734458.502 | 717358.548 | 734470.408 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, Storm Water and Water Mains and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST26 | MDR1597-RPS-01-M2-XX-D-C-0204 | Park Line Road | Slit Trench | 10 | 1.5 | 717329.879 | 734586.681 | 717319.902 | 734587.348 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of LP Gas, Virgin Media and Water Mains, and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 ST27 | MDR1597-RPS-01-M2-XX-D-C-0204 | Park Line Road | Slit Trench | 10 | 1.5 | 717338.055 | 734680.433 | 717328.102 | 734681.392 | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | Determine the position of existing underground services, including line, invert level, diameter and material of Eir Comms, Virgin Media and Water Mains, and the soil profile. including a detailed log of each trench (in plan and cross section) and comprehensive as-built plans, compiled in accordance with the requirements. | Tarmacadam/Asphalt
MDR1597 TP01 | MDR1597-RPS-01-M2-XX-D-C-0201 | Private Area DWtE | Trial Pit | 1 | 1.5 | 719893.324 | 733521.876 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Gravel/Hardstanding Area
MDR1597 TP02 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC / Public Road | Trial Pit | 1 | 1.5 | 719906.272 | 733522.2024 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Tarmacadam/Asphalt
MDR1597 TP03 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC / PUBLIC ROAD | Trial Pit | 1 | 1.5 | 719380.952 | 733508.9848 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Tarmacadam/Asphalt
MDR1597 TP04 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC/Richard Nolan | Trial Pit | 1 | 1.5 | 718508.0409 | 733703.6177 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Tarmacadam/Asphalt
MDR1597 TP05 | MDR1597-RPS-01-M2-XX-D-C-0202 | Irishtown Leasure Parking | Trial Pit | 1 | 1.5 | 718483.669 | 733704.301 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. Determine toe of historic quay wall. | Soil/Grass/Unmade Ground
MDR1597 TP06 | MDR1597-RPS-01-M2-XX-D-C-0202 | DCC Ringsend Park | Trial Pit | 1 | 1.5 | 718274.943 | 733986.837 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Tarmacadam/Asphalt
MDR1597 TP07 | MDR1597-RPS-01-M2-XX-D-C-0203 | Ringsend Rowing Club | Trial Pit | 1 | 1.5 | 717977.591 | 734204.71 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Soil/Grass/Unmade Ground
MDR1597 TP08 | MDR1597-RPS-01-M2-XX-D-C-0203 | West Garden Quay | Trial Pit | 1 | 1.5 | 717815.973 | 734262.916 | - | - | The soil is logged in accordance with Eurocode 7 Part 2 Ground Investigation and Testing (ISEN 1997-2:2007) and BS5930:2015 and soil samples are taken according to specification. | A clearer understanding of thin strata’s and provides a better knowledge of weathering characteristics applicable to rock formations. | Soil/Grass/Unmade Ground

## Utility Survey
UTILITY SURVEY (PAS128:2022)
Reference Number | Reference Drawing | Location | Type | Scheduled Length (m) | Scheduled Width (m) | Scheduled Depth (m) | Scheduled Area (m2) | Area Delivered (m2) | Scheduled Volume (m3) | ITM Reference |  |  |  | Approximate Ground Level (mOD) | Remarks | Access | Purpose
[10 empty] | Proposed Start Point |  | Proposed End Point
[10 empty] | Easting (m) | Northing (m) | Easting (m) | Northing (m)
MDR1597 US01 | MDR1597-RPS-01-M2-XX-D-C-0201 | DWtE PRIVATE AREA | PAS 128 (Type: A-B-C-D) |  |  |  | 116.056 |  |  | 719832.932 | 733470.149 | 719889.703 | 733397.847 |  |  |  | Confirm the existence of telecom, gas pipes, electric cables, drainage pipes, and other utilities in the indicated industrial area.
MDR1597 US02 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC / UE | PAS 128 (Type: A-B-C-D) |  |  |  | 951.612 |  |  | 719848.986 | 733395.891 | 719774.923 | 733297.554 |  |  |  | Confirm the existence of high-pressure gas pipelines, 110kV and 220kV electrical cables, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US03 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC / SOUTH BANK ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 7019.2 |  |  | 719720.424 | 733450.998 | 719715.199 | 733427.966 |  |  |  | Confirm the existence of utilities and temporary underground infrastructure networks due to the execution of projects on the site.
MDR1597 US04 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC / SOUTH BANK ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 97.78 |  |  | 719451.235 | 733450.988 | 719715.199 | 733427.966 |  |  |  | Confirm the existence of telecom, gas pipes, electric cables, drainage pipes, and other utilities in the indicated industrial area.
MDR1597 US05 | MDR1597-RPS-01-M2-XX-D-C-0201 | DPC / BISSET | PAS 128 (Type: A-B-C-D) |  |  |  | 951.108 |  |  | 719263.863 | 733461.998 | 719219.542 | 733421.459 |  |  |  | Confirm the existence of 38kV, 110kV and 220kV electrical cables, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US06 | MDR1597-RPS-01-M2-XX-D-C-0202 | SEAN MOORE ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 97.89 |  |  | 718835.668 | 733664.278 | 718825.481 | 733671.397 |  |  |  | Confirm the existence drainage infrastructure and other utilities in the indicated area.
MDR1597 US07 | MDR1597-RPS-01-M2-XX-D-C-0202 | BREMEN ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 254.67 |  |  | 718670.838 | 733637.81 | 718627.072 | 733635.337 |  |  |  | Confirm the existence of electric cables, telecoms, drainage infrastructure and other utilities in the indicated area.
MDR1597 US08 | MDR1597-RPS-01-M2-XX-D-C-0202 | RINGSEND PARK | PAS 128 (Type: A-B-C-D) |  |  |  | 317.51 |  |  | 718344.564 | 733919.656 | 718334.046 | 733951.261 |  |  |  | Confirm the existence of 38kV, 110kV electrical cables, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US09 | MDR1597-RPS-01-M2-XX-D-C-0202 | CAMBRIDGE ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 101.9 |  |  | 718253.049 | 734034.149 | 718249.051 | 734047.208 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, and other utilities in the indicated industrial area.
MDR1597 US10 | MDR1597-RPS-01-M2-XX-D-C-0202 | YORK ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 1215.82 |  |  | 718344.97 | 734079.11 | 718189.932 | 734140.994 |  |  |  | Confirm the existence of high-low pressure gas pipelines, 38kV, 110kV and 220kV electrical cables, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US11 | MDR1597-RPS-01-M2-XX-D-C-0202 | YORK ROAD / TOOL PLAZA | PAS 128 (Type: A-B-C-D) |  |  |  | 104.2 |  |  | 718139.192 | 734151.805 | 718125.997 | 734154.506 |  |  |  | Confirm the existence of high-low pressure gas pipelines, 38kV, 110kV and 220kV electrical cables, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US12 | MDR1597-RPS-01-M2-XX-D-C-0203 | RINGSEND ROWING CLUB | PAS 128 (Type: A-B-C-D) |  |  |  | 2379.46 |  |  | 718051.666 | 734176.644 | 717951.347 | 734205.559 |  |  |  | Confirm the existence of high-low pressure gas pipelines, 38kV, 110kV and 220kV electrical cables, telecoms, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US13 | MDR1597-RPS-01-M2-XX-D-C-0203 | WEST GREEN WALL QUAY | PAS 128 (Type: A-B-C-D) |  |  |  | 495.72 |  |  | 717831.837 | 734234.419 | 717812.091 | 734266.419 |  |  |  | Confirm the existence of high-low pressure gas pipelines, 38kV, 110kV and 220kV electrical cables, telecoms, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US14 | MDR1597-RPS-01-M2-XX-D-C-0203 | NORTH WALL QUAY | PAS 128 (Type: A-B-C-D) |  |  |  | 182.28 |  |  | 717839.492 | 734413.09 | 717826.872 | 734416.446 |  |  |  | Confirm the existence of high-medium,low pressure gas pipelines, 38kV, 110kV and 220kV electrical cables, telecoms, drainage infrastructure, and other utilities in the indicated area.
MDR1597 US15 | MDR1597-RPS-01-M2-XX-D-C-0204 | CASTLEFORBES ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 131.936 |  |  | 717712.622 | 734592.384 | 717713.889 | 734605.774 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US16 | MDR1597-RPS-01-M2-XX-D-C-0204 | CASTLEFORBES ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 158.288 |  |  | 717718.152 | 734680.175 | 717719.022 | 734694.292 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US17 | MDR1597-RPS-01-M2-XX-D-C-0204 | CASTLEFORBES ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 95.69 |  |  | 717725.01 | 734755.598 | 717723.638 | 734763.326 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US18 | MDR1597-RPS-01-M2-XX-D-C-0204 | NORTH WALL QUAY | PAS 128 (Type: A-B-C-D) |  |  |  | 364.84 |  |  | 717483.407 | 734437.525 | 717486.083 | 734464.065 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US19 | MDR1597-RPS-01-M2-XX-D-C-0204 | NEW WAPPING STREET | PAS 128 (Type: A-B-C-D) |  |  |  | 220.23 |  |  | 717494.975 | 734606.736 | 717493.03 | 734622.543 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US20 | MDR1597-RPS-01-M2-XX-D-C-0204 | NEW WAPPING STREET | PAS 128 (Type: A-B-C-D) |  |  |  | 116.36 |  |  | 717500.922 | 734695.555 | 717501.408 | 734712.713 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US21 | MDR1597-RPS-01-M2-XX-D-C-0204 | NEW WAPPING STREET | PAS 128 (Type: A-B-C-D) |  |  |  | 86.66 |  |  | 717509.571 | 734761.09 | 717505.388 | 734761.09 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US22 | MDR1597-RPS-01-M2-XX-D-C-0204 | NORTH WALL QUAY | PAS 128 (Type: A-B-C-D) |  |  |  | 450.72 |  |  | 717418.662 | 734423.827 | 717390.888 | 734470.392 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US23 | MDR1597-RPS-01-M2-XX-D-C-0204 | SPENCER PLACE | PAS 128 (Type: A-B-C-D) |  |  |  | 157 |  |  | 717411.461 | 734590.973 | 717410.608 | 734609.636 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US24 | MDR1597-RPS-01-M2-XX-D-C-0204 | SPENCER PLACE | PAS 128 (Type: A-B-C-D) |  |  |  | 200.26 |  |  | 717414.742 | 734639.786 | 717415.901 | 734656.816 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US25 | MDR1597-RPS-01-M2-XX-D-C-0204 | SPENCER PLACE | PAS 128 (Type: A-B-C-D) |  |  |  | 101.3 |  |  | 717417.893 | 734772.54 | 717419.036 | 734784.933 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US26 | MDR1597-RPS-01-M2-XX-D-C-0204 | NORTH WALL QUAY | PAS 128 (Type: A-B-C-D) |  |  |  | 561 |  |  | 717314.84 | 734454.283 | 717315.378 | 734474.175 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US27 | MDR1597-RPS-01-M2-XX-D-C-0204 | PARK LINE ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 74 |  |  | 717328.849 | 734597.123 | 717330.604 | 734608.129 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US28 | MDR1597-RPS-01-M2-XX-D-C-0204 | PARK LINE ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 164.88 |  |  | 717331.252 | 734650.504 | 717331.145 | 734668.68 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
MDR1597 US29 | MDR1597-RPS-01-M2-XX-D-C-0204 | PARK LINE ROAD | PAS 128 (Type: A-B-C-D) |  |  |  | 82.04 |  |  | 717338.623 | 734760.348 | 717338.025 | 734766.713 |  |  |  | Confirm the existence of telecom, low pressure gas pipes, electric cables, drainage pipes, telecoms, and other utilities in the indicated industrial area.
|  |  | Total Area (m2) |  |  |  | 17250.41

## Topography Survey
TOPOGRAPHYCAL SURVEY (PAS128:2022)
Reference Number | Complete | Reference Drawing | Location | Type | Scheduled Length (m) | Scheduled Width (m) | Scheduled Depth (m) | Scheduled Area (ml) | Area Delivered (m2) | Scheduled Volume (m3) | ITM Reference |  |  |  | Approximate Ground Level (mOD) | Remarks | Access | Purpose
[11 empty] | Proposed Start Point |  | Proposed End Point
[11 empty] | Easting (m) | Northing (m) | Easting (m) | Northing (m)
MDR1597 TS01 |  | MDR1597-RPS-01-M2-XX-D-C-0231 | DWtE / DPC SOUTH BANK ROAD | Topography |  |  |  | 23780.801 |  |  | 719237.347 | 733441.069 | 719879.113 | 733530.105 |  |  | Via North Road | Produce a three-dimensional model of a piece of land. It includes all natural and man-made features (e.g. trees, buildings, roads, footpaths, manholes, utility poles, retaining walls etc.)
MDR1597 TS02 |  | MDR1597-RPS-01-M2-XX-D-C-0231 | DPC - UE | Topography |  |  |  | 7019.2 |  |  | 719798.47 | 733391.069 | 719842.813 | 733291.305 |  |  |  | Produce a three-dimensional model of a piece of land. It includes all natural and man-made features (e.g. trees, buildings, roads, footpaths, manholes, utility poles, retaining walls etc.)
MDR1597 TS03 |  | MDR1597-RPS-01-M2-XX-D-C-0232 | PUBLIC ROAD/GREEN AREA | Topography |  |  |  | 37168.1 |  |  | 718780.231 | 733593.317 | 717966.367 | 734208.438 |  |  | Via North Road | Produce a three-dimensional model of a piece of land. It includes all natural and man-made features (e.g. trees, buildings, roads, footpaths, manholes, utility poles, retaining walls etc.)
MDR1597 TS04 |  | MDR1597-RPS-01-M2-XX-D-C-0233 | NORTH DOCKLANDS PUBLIC ROAD | Topography |  |  |  | 55638.3 |  |  | 718049.395 | 734550.503 | 717337.031 | 734775.608 |  |  | Via North Road | Produce a three-dimensional model of a piece of land. It includes all natural and man-made features (e.g. trees, buildings, roads, footpaths, manholes, utility poles, retaining walls etc.)
|  |  |  | Total Area (m2) |  |  |  | 123606.401
|  |  |  | Total Area (ml) |  |  |  | 7212